| DOCUMENT APPROVAL |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Name | Designation | Signature | Date |
| Prepared by | Kunle Awolowo | Consultant |  |  |
| Reviewed by | Hadiza Abubakar | National Coordinator |  |  |
| Reviewed by |  |  |  |  |
| Approved by |  |  |  |  |

| REVISION HISTORY |  |  |  |
| --- | --- | --- | --- |
| REV | Description of Change | Author | Effective Date |

Contents

INTRODUCTION	4

PROCESS DOCUMENT CHANGE MANAGEMENT	6

1.	STAKEHOLDER ENGAGEMENT AND MEETING COORDINATION	10

2.	PROPOSAL WRITING & PARTNERSHIP BIDDING	13

3.	STRATEGIC PROJECT PLANNING & BUDGETING	16

4.	HUB ESTABLISHMENT & LAUNCH	19

5.	DAILY HUB OPERATIONS MANAGEMENT	22

6.	BOOKING, SCHEDULING & SERVICE FULFILMENT	26

7.	EQUIPMENT USAGE & OPERATOR MANAGEMENT	29

8.	SERVICE COMPLETION VERIFICATION & CLOSE-OUT	32

9.	CUSTOMER FEEDBACK & COMPLAINT MANAGEMENT	35

10.	REVENUE COLLECTION & VERIFICATION	38

11.	REVENUE SHARING & DISBURSEMENT	42

12.	BUDGET DEVELOPMENT & FINANCIAL CONTROL	45

13.	FINANCIAL ACCOUNTABILITY & INTERNAL CONTROLS	48

14.	COST OPTIMISATION & EXPENSE APPROVAL	51

15.	EQUIPMENT ALLOCATION & DEPLOYMENT	54

16.	EQUIPMENT MAINTENANCE & DOWNTIME MANAGEMENT	57

17.	ASSET & INVENTORY CONTROL	61

18.	EQUIPMENT INCIDENT & DAMAGE REPORTING	65

19.	HUB REGISTER & RECORD-KEEPING	68

20.	STATE/ZONAL REGISTER (RECORD) OVERSIGHT	71

21.	DATA COLLECTION, VALIDATION & SUBMISSION	74

22.	DIGITAL SYSTEM USAGE & DATA GOVERNANCE	77

23.	SUPERVISION OF COMMUNITY & SUB-COMMUNITY LEADS	80

24.	STATE/ZONAL OPERATIONAL OVERSIGHT	83

25.	COMPLIANCE MONITORING & FIELD AUDIT	86

26.	ISSUE ESCALATION & RISK REPORTING	89

27.	KPI & INDICATOR MANAGEMENT	92

28.	PERFORMANCE MONITORING & REPORTING	95

29.	LEARNING, ADAPTATION & CORRECTIVE ACTION	98

30.	SAFE PARTICIPATION & SAFEGUARDING	101

31.	EQUAL ACCESS TO MECHANISATION SERVICES	105

32.	GENDER-BASED RISK IDENTIFICATION & RESPONSE	108

List of Abbreviations

- INTRODUCTION

  - Definitions in the Process Document

For purposes of the Process Document, unless the context otherwise indicates:

- “Document” in this introduction portion means “Process Document”

- “Association” refers to Women in Mechanized Agriculture (WIMA)

- Process Owner: The staff/partner who is responsible for the performance of certain tasks or activities intended to achieve a result.

- Process Administrator: The staff/partner who manages the function in which the process owner handles and is accountable in ensuring the process owner carries out their tasks.

  - Main Principles

The Procedures prescribe operation-level guidelines for WIMA in managing, controlling and accounting for its operations in a timely, efficient and orderly manner, with the aim of delivering on the conceptual objectives of the Association. The Procedures are intended to be read in conjunction with the Policies, Manual and other related documents.

  - Disclaimer

This document presents WIMA Procedures solely for use by WIMA. No assurance is provided that all WIMA-related matters are addressed. Furthermore, the document should not be considered to result in the Association complying with any standards. In addition to these procedures, employees/partners should comply with all applicable laws and regulations, respect local social norms, ethics and business practices.

  - Objectives of the Process Document

- To provide best practice procedures appropriately suited for WIMA in dealing with the core functions of the Association as it relates with its scope of operations.

- To establish appropriate documentation and control for core processes and procedures.

- To provide management with a reference for proper control and follow up.

- Properly define and document procedures and process flows.

- Familiarize employees and partners with procedures related to their role/function.

- Ensure efficiency and effectiveness of WIMA operations and controls across the various levels.

- Ensure reliability of information and facilitate decision making process in WIMA.

- Limit disputes between personnel/partner in regard to procedures.

- Eliminate non-value-added activities and duplication of effort.

- To be used as a training tool for current and newly recruited staff/partners.

- To provide guidance on policies and procedures to direct its operational functions.

- To standardise key processes, forms, reports and files.

The Processes have been developed to be in line with WIMA-specifics and project requirements.

  - Access to the Process Document

This Document has been prepared to guide both management and all concerned staff/partners. The following position holders shall have a copy of this Document:

- President

- National Coordinator

- Internal Auditor/Control/Compliance

All employees/partners within WIMA shall have access to this Document to assist with execution or performance of daily tasks. The National Coordinator/HR may choose to make copies of any part of this Document for any concerned staff/function within the Association, as it relates to their role.

  - Control of the Process Document

- Each distributed copy of the Document shall have a serial number. The Internal Auditor shall maintain a record of these copies.

- Recipients of the Document shall sign the record confirming receipt.

- The recipient will not remove, amend or make a copy of any part of the Document without approval of the President and/or Board of Trustees.

- This Process Document should always be kept in a safe place.

- Contents of the Document are confidential and are intended for internal use only. Under no circumstance shall the contents of this document be revealed to third parties without the express written permission of the President and/or Board of Trustees.

  - Amendments to the Process Document

- Any concerned employee/partner can suggest modification to the approved processes, by writing a memo to the President.

- Proposed amendments are to be submitted to the National Coordinator for review and evaluation of the suggested modifications.

- Upon completion of the review and further consultation with the Internal Auditor, the President will make recommendations on the suggested modifications.

- The amendments are then submitted to the President and/or Board of Trustees for approval.

- The approved amendments shall then be issued in writing by the President to WIMA in the form of new or replacement pages.

- Holders of the Document are responsible for incorporating the amendments as specified in the list of amendments

  - Roles and Responsibilities

The President and National Coordinator have the overall responsibility for the:

- Implementation of the procedures contained in this Document.

- Approval of alterations to any part of the Document after due consultations

- Issuance of revised procedures to any part of the Document considering changing circumstances.

- Custody and distribution of the Document

- Maintenance of a register of the holders of the Document

  - Elasticity

Since covering all possible conditions and circumstances in a Document such as this is impractical, when activities, services or transactions that are not specifically covered in this Process Document occur, they should be reviewed with authoritative literature and classified as near as possible within the context of the Process Document.

- PROCESS DOCUMENT CHANGE MANAGEMENT

Scope

Standard Processes in WIMA are designed to provide guidance on how activities and processes within the Association are to be performed. It also identifies minimum controls and appropriate approvals required to effectively operate the processes to ensure that perceived risks and exposure to the Association are reduced and mitigated.  Each process consists of a set of related processes which are to be complied with in the course of the day-to-day operations of the Association. However, where the processes are to be updated or amended, a formal request (for the update/amendment) will be sent to the Process Administrator. All requests for updates/amendments to an existing process must be duly approved by the relevant Process Owner and/or the relevant Top Management personnel (National Coordinator/President and the Board of Trustees). Only approved and authorised updates/amendments to processes must be implemented.

Objective of this section

The objective of this section is to provide guidelines and the step-by-step process through which amendments/updates to existing procedures may be identified and effected. It also aims at ensuring that all identified changes to current procedures are properly reviewed and duly approved for incorporation into the existing procedure.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Request for Process Update/Amendment - Process document | - Approved Change Request - Updated Process(es) |
| Process Trigger | Process Owner(s) |
| - As the need arises (when there is a need for amendment(s) to an existing procedure). | - Process Administrator |
| Tools Required | Key Performance Indicators |
| - Memo | - Only updates/amendments approved by Process Owner(s) and Management, are implemented - Only current revisions of procedures are operational - A log of requested and approved updates/amendments to procedures is maintained |

Business Process Flow Diagram

Business Process Flow Description: Process Document Change Management

| No. | Activity | Task/Description | Responsibility |
| --- | --- | --- | --- |
| Amendments/Updates Proposed by the Process Owners |  |  |  |
|  | Send request for an amendment | Whenever there is a need to update/amend a procedure, the Process Owner sends a request (via e-mail) for an amendment to an existing procedure (stating the name of the procedure, the details of the changes to be made, justification for the amendment and any other relevant details) to the Process Administrator for necessary action. The need for amendment(s) to an existing procedure could arise due to the emergence of new policies, government legislation, changes in operational/business realities, etc. | Process Owner |
|  | Check details of proposed amendment(s) and forward along with the original procedure | Check the details of the proposed amendment(s) and forward it along with the original process document to the relevant Management personnel for review and approval (with the relevant Process Owner in copy). Key control: Request for updates/amendments to procedures are channelled through the Process Administrator | Process Administrator |
|  | Review proposed amendments, approve and authorise revision | Review the proposed amendments, approve and authorise the revision of the current process via a return e-mail to the Process Administrator (with the relevant Process Owner in copy). Key control: Changes to a procedure must be approved by the relevant Process Owner and/or Management personnel (President). | Management |
|  | Effect necessary changes to the current process | Effect the necessary changes to the current process by incorporating the approved amendments to the existing document. Forward the revised process to the relevant Management personnel (President) for approval to publish (via e-mail) with the relevant Process Owner in copy. | Process Administrator |
|  | Review the revised process vis-à-vis the approved amendments | Review the revised process vis-à-vis the approved amendments and authorise the circulation of the revised procedure via a return e-mail to the Process Administrator (with the relevant Process Owner in copy). | Management |
|  | Update the log of requested and approved updates | Update the log of “Requested and Approved Updates to Process”. | Process Administrator |
|  | Publish the revised process to all concerned | Publish the revised process via e-mail and broadcast to all staff concerned. Archive the previous version and file all the relevant documentation including the revised process as evidence of performance of control. | Process Administrator |
| Amendments/Updates Proposed by Others – Other than the Process Owner |  |  |  |
|  | Send request for an amendment | Whenever there is a need to update/amend an existing process/procedure, the relevant requestor sends a request (via e-mail) for an amendment to the Process Administrator stating the following: - Name of the procedure - Details of the changes to be made - Justification for the amendment and - Any other relevant details The need for amendment(s) to an existing procedure could arise due to the emergence of new policies, government legislation, changes in operational/business realities, etc. | Requestor |
|  | Check details of the proposed amendment(s) and forward it along with the original procedure | Review details of proposed amendment(s) and forward it along with the original procedure document to the relevant Process Owner for review and approval. Key control: Request for updates/amendments to procedures are channelled through the Process Administrator | Process Administrator |
|  | Review justification and appropriateness of proposed amendments, approve and authorise revision | Review the justification and appropriateness of the proposed amendments and confirm approval or disapproval to the Process Administrator via e-mail. Where the proposed amendment is considered appropriate proceed to step 6. Otherwise continue with step 4. Key control: Changes to a procedure must be approved by the relevant Process Owner and/or Management personnel (President). Adequate justification is provided for the requested amendment before they are approved for implementation. | Relevant Process Owner |
|  | Decline proposed amendment and notify Process Administrator | Decline the proposed amendment and notify the Process Administrator of the decline via e-mail (stating the reasons for the decline). | Relevant Process Owner |
|  | Notify Requestor of disapproval | Verify the validity of the reason for decline. Where valid, notify the Requestor of disapproval. However, if the reason, is invalid, the process continues | Process Administrator |
|  | Communicate approval to make changes | Send an e-mail to the relevant Process Administrator communicating approval of the proposed amendment(s) to the existing procedure. | Relevant Process Owner |
|  | Forward approved amendment to Management for final approval and authorisation | Forwards the approved amendment(s) to the relevant Management personnel for final approval and authorisation (with the relevant Process Owner in copy). | Process Administrator |
|  | Review proposed amendments, approve and authorise revision | Review the proposed amendments, approve and authorise the revision of the current process via a return e-mail to the Process Administrator (with the relevant Process Owner in copy). Key control: Changes to a procedure must be approved by the relevant Process Owner and/or Management personnel (President). | Management |
|  | Effect necessary changes to the current process | Effect the necessary changes to the current process by incorporating the approved amendments to the existing document. Forward the revised process to the relevant Management personnel (President) for approval to publish (via e-mail) with the relevant Process Owner in copy. | Process Administrator |
|  | Review the revised process vis-à-vis the approved amendments | Review the revised procedure vis-à-vis the approved amendments and authorise the circulation of the revised process via a return e-mail to the Process Administrator (with the relevant Process Owner in copy). | Management |
|  | Update the log of requested and approved updates | Update the log of “Requested and Approved Updates to Process”. | Process Administrator |
|  | Publish the revised process to all concerned | Publish the revised process via e-mail broadcast to all staff concerned. Archive the previous version and file all the relevant documentation including the revised process as evidence of performance of control. | Process Administrator |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Unapproved changes | Unapproved and/or unauthorised approval of changes to an existing procedure | Internal auditor shall vet to see that the process was duly followed and appropriate sign off obtained for circulated process document |

Policy Guidelines

- A formal request (for the update/amendment) must be put forward to the Process Administrator before any amendment/update can be processed.

- All requests for updates/amendments to an existing process must be duly approved by the relevant Process Owner and/or the relevant Top Management personnel (President).

- Only approved and authorised updates/amendments to processes must be implemented.

- All updates and amendments must be documented in a log on the process document with details of the changes filed properly.

- Request for process amendment/update can come from the Process Owner or any other parties

- Where a request is from another party other than the Process Owner, appropriate justification must be provided for the proposed amendment/update, which shall be reviewed by the Process Owner.

- In the event a proposed amendment/update has been declined by the Process Owner, the reason shall be clearly stated and the validity of the reason shall be verified by the Process Administrator.

- Internal Control/Audit/Compliance is expected to verify if appropriate steps were taken to update or amend previously approved processes.

- Internal Control/Audit/Compliance shall be made aware of any intention of make changes to already established processes. They are expected to assess the proposed changes against possible risks that may arise as a result of changes.

- Internal Control/Audit/Compliance shall support management in assessing the impact of such changes on the operations of the Association.

- This manual is not meant to be exhaustive but represents the minimum mandatory requirements. It is expected that this manual will be revised and updated periodically to reflect WIMA’s current realities, new developments and changes impacting WIMA.

- The National Coordinator is responsible for ensuring the manual is updated as and when required.

STAKEHOLDER ENGAGEMENT AND MEETING COORDINATION

Overview of Process

The “Stakeholder Engagement and Meeting Coordination” process details the sequence of activities for planning, approving, conducting, documenting and following up on stakeholder engagements and meetings at national, state/zonal and community levels. It ensures that WIMA’s engagements with government institutions, partners, donors, traditional authorities, private sector actors and community stakeholders are strategic, well-coordinated, consistent and aligned with WIMA’s objectives, governance standards and public positioning.

Scope

This process applies to all formal and informal stakeholder engagements and meetings involving WIMA, including advocacy meetings, partnership discussions, donor engagements, community sensitisation meetings, coordination forums and internal-external interface meetings.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - WIMA Strategic Plan & Pillars - Advocacy & Policy objectives - Meeting Request Memos/Letters - He4She Charter & localized guidelines - Approval from President/National Coordinator - Stakeholder mapping and engagement plan - Engagement requests or invitations - Approved agendas and briefing notes - Communication and protocol guidelines | - Meeting agendas and briefing notes - Attendance registers - Stakeholder Engagement Register (Master Data) - Meeting Minutes and Action Point Trackers - Other related outputs such as: - Signed Memorandums of Understanding (MoUs) - Policy Influence Reports - Community Endorsement Pledges |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Identification of a stakeholder engagement need - Invitation received from an external stakeholder - Requirement to support project implementation, advocacy, or partnership development - Strategic expansion into a new state/zone - Requirement for policy advocacy or land access - Hub establishment or local conflict resolution | - National Coordinator / Project Lead: Strategic oversight, approval of high-level engagements - President: Approval and participation in priority or high-level engagements - State/Zonal Coordinator: Coordinate state/regional engagements and meetings - Community Lead (CL): Coordinate local and community-level engagements - MEL Coordinator / Data Officer: Documentation, reporting and follow-up tracking |
| Tools Required | Key Performance Indicators (KPIs) |
| - ERP (Stakeholder/Partner Records) - Official WIMA Letterhead and Manuals - Business Intelligence Dashboards - Communication Protocols (Emergency/Safeguarding) | - No. of formal MoUs/partnerships secured. - % of engagements aligned with approved plans - No. of policies influenced (e.g., subsidies). - % of members reporting improved land access. - Stakeholder satisfaction and partnership outcomes - Hub audit scores. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Stakeholder Identification | Identify relevant stakeholders based on level (Federal, State, LGA, or Village). Differentiate between government MDAs, traditional rulers and donor partners. Define purpose, objectives and stakeholder. | Initiator (CL/State/ National/ President) | Immediate |
|  | Obtain Internal Approval | Draft engagement memo. High-level meetings require President’s approval; state meetings require National Coordinator approval. Key control: Approval required for external engagements. Utilise approval hierarchy | National/State Coordinator/CL | 48 Hours |
|  | Develop Engagement Strategy | Prepare engagement brief i.e., Develop agenda, key messages and talking points. As applicable, align engagement with WIMA’s pillars (e.g., He4She Charter or Hub Service Monetization) to ensure value proposition is clear. | National/State Coordinator/CL | 1-3 Days |
|  | Schedule Meeting | Coordinate dates, venue and participants. | National/State Coordinator/CL | Immediate |
|  | Formal Invitation | Send formal invitations and confirmations. Where appropriate, enlist the assistant of the KM/Comms manager to transmit typed letters in local languages if necessary. Use radio/multimedia jingles to sensitise communities before the meeting. | National/State Coordinator/CL | At least 5 Days prior |
|  | Conduct Engagement | Hold meeting following approved agenda. Present WIMA vision. For rural areas, use Village Stakeholder Dialogues to address cultural barriers and secure local buy-in. Where applicable facilitate formal pledges from stakeholders | Respective Owner | As scheduled |
|  | Document Proceedings | Record minutes, attendance and decisions. Key control: All meeting must be documented and circulated | Assigned Officer | Immediate |
|  | Validate Minutes | Review and approve meeting records. Key control: To check accuracy | Meeting Lead | 24 Hours post-meeting |
|  | Update ERP and Track Action Points | Log meeting outcomes, stakeholder contact details and any "incident reporting" (e.g., pushback or security threats) into the ERP. Assign responsibilities and timelines using the action tracker. All learnings must be documented and shared for future engagements. | MEL Coordinator/ Data Officer | Immediate |
|  | Follow-Up & Report | Send appreciation and summary of action points. Track progress. Follow up on commitments and report outcomes. | National/State Coordinator |  |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Inconsistent messaging | Conflicting statements to stakeholders | Approved briefs |
| Commitment gaps | Stakeholders fail to support strategy implementation after the meeting. | Conduct frequent engagement and provide performance reports/M&E dashboards to maintain visibility. |
| Unauthorized commitments | Commitments made without mandate. | Approval controls. |
| Poor documentation | Loss of decisions and actions. | Standard minutes. |
| Security conditions | Conducting meetings in volatile "red-zone" areas. | Engage local consultants and abide by Emergency Community Response guidelines. |
| Reputational risk | Poor conduct or protocol breaches. | Representation guidelines. |
| Missed follow-up | Commitments not implemented. | Action tracking. |
| Advocacy pushback | Resistance from male-dominated structures or cultural norms. | Use He4She Champions (husbands/fathers) and traditional leader endorsements to legitimize operations. |

Policy Guidelines

- No stakeholder engagement without prior approval.

- No coordinator may engage a new state or high-level government body without a signed-off strategic plan and national-level approval.

- All engagements must include specific targets for women, youth and persons with disabilities.

- All MoUs must be captured in the central Partnership Registry and updated quarterly.

- Awareness materials (videos/radio series) must be disseminated in local languages to mitigate misconceptions.

- Every engagement must be backed by a record in the WIMA master register at the LGA/State level.

- All WIMA commitments require internal clearance either prior or post engagement.

- This process shall be reviewed periodically or following reputational incidents, partnership disputes or changes in WIMA’s engagement strategy approved by leadership.

PROPOSAL WRITING & PARTNERSHIP BIDDING

Overview of Process

The “Proposal Writing and Partnership Bidding” process defines a standardized and controlled process for identifying funding and partnership opportunities, developing competitive proposals, submitting bids, negotiating partnerships and securing approvals for engagement. It ensures that all proposals and bids submitted by WIMA are strategically aligned, technically sound, financially viable, compliant with donor and partner requirements and authorized by appropriate governance levels.

Scope

This process applies to all proposal development, grant applications, partnership bids, expressions of interest (EOIs), concept note and commercial or non-commercial partnership submissions initiated or submitted by WIMA at national, zonal/state, or programme levels.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Call for proposals / bid documents - Strategic plan and priority programs - Technical concept notes - Cost and pricing assumptions | - Due Diligence Reports on Partners - Approved Bid/Tender Documents/Technical & Financial Proposals - Submitted applications and acknowledgements - Proposal tracking and outcomes register - Signed Partnership agreements and MoUs - Partnership Registry update |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Identification of a funding or partnership opportunity - Announcement of a relevant RFP or grant cycle - Invitation to submit a proposal, bid, or concept note - Strategic decision to pursue a partnership or funding opportunity - Partner-initiated interest in WIMA services | - National Coordinator / Project Lead: Strategic oversight, opportunity approval, final proposal endorsement - President / Governing Body: Approval of high-value or strategic partnerships - State/Zonal Coordinator: Provide field inputs and implementation insights - Finance & Operations Officer: Budget development, cost validation, compliance checks - MEL Coordinator / Data Officer: Indicator design, results framework and evidence inputs |
| Tools Required | Key Performance Indicators (KPIs) |
| - Proposal and concept note templates - Budgeting and costing tools - Proposal review checklists - Partnership approval matrix - ERP (M&E/Results data for evidence-based bids) - WIMA Profile and Hub Achievement Reports - Pricing Models (for commercial/service bids) - Approved Budget Templates | - Number of partnerships secured (against target) - Value of funding secured (against target) - Bid Success Rate (%). - % of Capex covered by external partners. - Compliance issues identified post-submission |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Opportunity Identification | Scan and log funding or partnership opportunities. Identify opportunities (Grant, CSR, PPP). Screen for alignment with WIMA’s four pillars and expansion parameters. | National / State Coordinator | Ongoing |
|  | Strategic Fit Assessment | Assess alignment with WIMA strategy and capacity. Key Control: Conduct vetting to ensure partners comply with WIMA’s Anti-Corruption and Bribery Policy. Avoid PEP-related risks. | National Coordinator | 48 Hours |
|  | Approval to Proceed | Obtain formal approval to develop proposal. Key Control: Evaluate the risk of "Over-expansion" and ensure the opportunity meets minimum operation demand thresholds. Mandatory strategic fit and Go/No-Go decision | Board of Trustees /President |  |
|  | Assign Proposal Lead | Designate lead and contributors. | National Coordinator | Immediate |
|  | Develop Technical Concept | Draft approach, methodology and workplan. Draft technical solution based on successful hub models. Differentiate between service management and contract farming where applicable. | Proposal/ Intervention Development Lead | As per RFP |
|  | Develop Budget | Prepare detailed, compliant budget. | CFO/Proposal Lead |  |
|  | Internal Review | Review technical, financial and compliance aspects. A review team is appointed to have a second/independent assessment of the proposal. | Review Team | 3 Days prior |
|  | Revise & Finalize | Incorporate feedback and finalize documents. | Proposal/ Intervention Development Lead |  |
|  | Obtain Final Approval | Secure final sign-off for submission. Key Control: Proposals and partnership agreements must be approved by the President and/or BOT for strategic alignment. | Board of Trustees /President | 48 Hours |
|  | Submit Proposal/Bid | Submit through approved channel. Submit bid via appropriate channel. MEL Coordinator updates the Partnership Registry to track lead status. Provide submission evidence | Authorized Officer | Deadline |
|  | Clarifications & Negotiation | Respond to donor or partner queries. | National Coordinator / CFO | As per schedule |
|  | Award Acceptance | Review and accept award or partnership terms. Key Control: All service agreements and MoUs must be reviewed by the Legal Advisor before execution. A risk assessment should be done | Board of Trustees /President/ Legal Advisor | Post-award |
|  | Archive & Track | Archive proposal in proposal database and track outcomes. | Data Officer / MEL Coordinator |  |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Mission drift | Pursuing misaligned opportunities. | Strategic fit assessment. |
| Under-costing | Financial losses during implementation. | Budget validation. |
| Non-compliance | Proposal rejection or sanctions. | Compliance checklists. |
| Dependency Risk | Relying on a limited number of income/funding sources. | Use proposal writing to diversify into non-donor revenue, such as consultancy and machinery sales. |
| Corruption/Kickback Pressure | Pressure to pay "facilitation payments" to win bids in high-risk zones. | Enforce Zero-Tolerance Policy. Refuse requests politely and report through the Whistle Blower channel. |
| Unauthorized submissions | Reputational risk. | Approval matrix. |
| Reputational Damage | Partnering with entities that violate ethical standards. | Mandatory Sexual Abuse, Exploitation and Harassment prevention clauses in all contracts. |
| Capacity overreach | Inability to deliver. | Capacity assessment. |
| Commitment Gaps | Partner fails to provide co-funding after the bid is won. | Secure signed MoUs with advance payment structures or clear milestone triggers. |

Policy Guidelines

- All proposals require approval before submission.

- Budgets must be reviewed by Finance.

- Proposal development must follow due process and internal quality assurance before submission.

- Budgeting and risk assessment must be carried out adequately and highlighted for consideration by approving authority.

- High-value partnerships require governing body approval.

- Signed agreements precede implementation.

- WIMA will not participate in any bid that requires kickbacks, bribery, or unethical influence. All bids must be made on merit.

- Every proposal must include a clear path to profitability or cost-sharing to reduce dependence on the donor cycle.

- Proposals must explicitly target female and youth-led participation.

- No coordinator is authorized to sign a partnership agreement or MoU that has not been vetted by the WIMA Legal Advisor and approved by the President.

- All partner and member data used in proposals must comply with the Nigeria Data Protection Regulation.

- This process shall be reviewed periodically or following major proposal failures, audit findings, or changes in donor and partnership requirements approved by leadership.

STRATEGIC PROJECT PLANNING & BUDGETING

Overview of Process

The “Strategic Project Planning and Budgeting” process outlines the annual cycle and project-specific workflows for designing, costing and approving WIMA’s initiatives. It describes how to translate WIMA’s strategy, approved proposals and partnership commitments into well-structured project plans and realistic budgets. It ensures projects are strategically aligned, operationally feasible, financially sound and approved before implementation. This reduces execution risk and strengthening accountability across national, state/zonal and hub levels.

Scope

This process applies to WIMA projects, programmes, pilots and business initiatives funded through grants, partnerships, internally generated revenue or donor support at national, state/zonal and hub-levels.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved proposals, grants, or partnership agreements - WIMA strategic and operational plans - Stakeholder commitments and timelines - Cost assumptions and resource availability data - Hub performance data and analytics - Market intelligence and crop calendars - National and sub-national policy alignment - Stakeholder and member feedback | - Approved project implementation plans - Approved project budgets and cashflow projections - Results frameworks and implementation schedules - Project approval and authorization records - Resource Allocation Schedule - Monitoring & Evaluation (M&E) Framework |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Approval or award of a proposal, grant, or partnership - Strategic decision to initiate an internal or pilot project - Annual or multi-year strategic plan implementation cycle - Expansion into a new state or region | - National Coordinator / Project Lead: Overall project prioritization, approval and resource alignment - President / Governing Body: Approval of strategic, high-value, or high-risk projects - State/Zonal Coordinator: Development of state/zonal project plans and budgets - CFO: Budget structuring, costing validation and affordability checks - MEL Coordinator / Data Officer: Results framework, indicators and implementation assumptions |
| Tools Required | Key Performance Indicators (KPIs) |
| - Project planning and workplan templates - Budgeting and cashflow tools - Results framework and indicator matrices - Project approval and sign-off forms - ERP Business Intelligence Toolkit - Executive Dashboards - Financial Modelling Spreadsheets - Implementation Roadmap | - Percentage of projects aligned with strategic priorities - Budget variance during implementation - Timeliness of project start-up - Project delivery against planned milestones - % of initiatives informed by M&E data (Target: 100%). - Budget variance vs. actual spend (<5%). - % cost recovery/breakeven rate of hubs. - Number of hubs established (as per target) |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Baseline & Performance Review | Analyse performance on previous plan. Analyse existing hub data, yield impacts and revenue flow using the ERP dashboard to identify gaps. | National Coordinator / MEL Coordinator | 2nd week of the year (Annual) |
|  | Priority Setting | Align project goals with the four strategic pillars: Expansion, Revenue, Structure and Digital Transformation. Validate project(s) scope, objectives and funding conditions. Translate strategy into clear project goals and outputs. Develop result framework by defining outcomes, outputs, indicators and targets | Executive Team | 2nd – 3rd week of the year |
|  | Develop workplan & Resource Planning | Break project into activities, timelines and responsibilities. Submit needs assessments based on local crop calendars and equipment gaps. Identify staffing, equipment and hub requirements. Draft technical plans and ensure the little or no donor dependency as applicable. | State Coordinators | 3rd week of the year |
| 3a | Project Design & Costing | Draft technical plans and ensure the little or no donor dependency as applicable. | National Coordinator / Intervention Development Lead |  |
|  | Budget Consolidation | Prepare detailed, activity-based budget. Develop disbursement and expenditure timelines. Carry out liquidity checks. Key Control: CFO reviews all costs for efficiency and ensures availability of funding. Activity-based budgeting and cashflow planning | CFO | 4th week of the year |
|  | Internal Review | Review plan and budget for quality and feasibility. Identify operational, financial and delivery risks | Executive Team | 48 Hours |
|  | Strategic Review Retreat | Convene BOT, President and all State leads to review the annual plan and expansion metrics (density of women farmers, stability). Make necessary adjustments based on agreed and accepted feedback. | National Coordinator | 5th week of the year |
|  | Final Approval | Grant formal approval to implement. Key Control: Formal sign-off on the budget and implementation plan by the President. | President | 6th week of the year |
|  | Handover for Implementation | Transition project to execution team i.e., State Coordinators. | National Coordinator |  |
|  | Resource Mobilisation | Activate financing partnerships and allocate equipment/resources based on the approved schedule. | National Coordinator / CFO | Immediate |
|  | Adaptive Planning | Conduct quarterly reviews to adjust budgets and strategies based on real-time field evidence. | National Coordinator / MEL Coordinator | Quarterly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Scope creep | Uncontrolled expansion of activities. | Approved scope baseline. |
| Under-budgeting | Insufficient funds for delivery. | Cost validation. |
| Revenue Shortfalls | Budgeted income from hiring or rental fees is not met. | Use diversified revenue streams (equipment sales, consultancy) and maintain a contingency funding reserve. |
| Over-ambitious plans | Unrealistic timelines or targets. | Capacity assessment. |
| Policy Reversals | Sudden changes in government subsidies or land access laws. | Utilize the policy advocacy capacity of the National Coordinator/President to influence gender-responsive mechanization policies in at least 5 states. |
| Cashflow mismatch | Inability to fund activities. | Cashflow planning. |
| Poor alignment | Project deviates from strategy. | Strategy check. |
| Over-Expansion | Scaling beyond the organization's financial or management capacity. | Use strict expansion criteria (minimum women demand threshold) and activate Zonal Coordinators to manage the span of control. |

Policy Guidelines

- No project may commence without approved plan and budget.

- Budgets must align with funding conditions.

- Strategic projects require governing body approval.

- Approved plans form the basis for monitoring and reporting.

- No project shall commence without a written Implementation Plan and a budget approved by the President.

- All project planning must include a cost-recovery or profit-sharing model to ensure hub longevity beyond the donor cycle.

- All annual goals must be informed by baseline surveys and previous implementation learnings captured in the MEL system.

- Project budgets must allocate resources to ensure female and youth-led participation target.

- Every strategic decision and budget adjustment must be recorded in the executive dashboard and tracked via the M&E framework.

- All partner and member data used in proposals must comply with the Nigeria Data Protection Regulation.

HUB ESTABLISHMENT & LAUNCH

Overview of Process

The “Hub Establishment & Launch” process defines the standardized sequence for identifying, setting up and operationalising local mechanisation centres at state, LGA, or community level. It ensures that hubs are strategically located, properly resourced, compliant with WIMA standards, socially accepted, financially viable and operationally ready before service delivery commences.

Scope

This process applies to the establishment of all new hubs, including permanent, semi-permanent, pilot and mobile hubs, regardless of funding source or geographic location.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Location Readiness Checklist - Baseline Survey Data (Crop calendars, equipment gaps) - Approved Expansion Budget - Strategic expansion plan or approved project - Demand assessment and site feasibility data - Community and stakeholder endorsements - Approved hub budget and asset allocation plan | - Trained Hub Personnel/MSPs - Approved hub establishment plan - Signed community or site agreements or hub management agreement - Functional Mechanisation Hub - Asset inventory and Equipment Register - Hub asset and inventory records - Hub launch and readiness report |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Strategic decision to expand WIMA operations - Approval of a project, partnership, or funding that includes hub establishment - Annual Expansion Roadmap activation - Strategic identification of a new "red-zone" or high-demand area - LGA-level demand request from cooperative - Identification of unmet mechanization demand in a target location | - National Coordinator / Project Lead: Strategic approval and oversight of hub establishment - President / Governing Body: Approval of strategic or high-value hub investments - State/Zonal Coordinator: Lead hub establishment at state or zonal level - Community Lead (CL): Local mobilisation, site readiness and community engagement - CFO: Budget control, asset allocation and compliance - GEDSI Officer: Inclusion, safety and accessibility considerations |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA Hub Management System (ERP) - Site Selection & Safety Checklist - Hub Governance Toolkits - Hub feasibility and demand assessment tools - Site inspection and readiness checklists - Hub establishment budget templates - Asset deployment and handover forms - HSE & Safety Equipment | - Number of new hubs launched (based on target). - % of women served per season (based on target). - Time to breakeven (Target: within 18 months). - % of hubs with functional leadership. - Number of hubs established against plan - Time from approval to hub launch - Hub utilisation rate within first season - Community acceptance and participation levels |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Identify Hub Need | Assess mechanization demand and strategic fit. | National / State Coordinator | 10 Days |
|  | Conduct Feasibility Assessment | Assess location, access, security and viability. Conduct baseline surveys on local farming practices, gender roles and equipment gaps. Key Control: Verify "minimum women demand threshold" before proceeding | State Coordinator / Data Officer |  |
|  | Stakeholder Engagement | Engage community, LGAs and traditional leaders. Liaise with LGAs, traditional rulers and religious leaders to secure land access and local legitimacy. | CL / State Coordinator | 7 Days |
|  | Prepare Hub Establishment Plan | Define hub model, services, staffing and assets | State Coordinator | 3 Days |
|  | Develop Hub Budget | Prepare detailed establishment and start-up budget. Seek approval based on documentation. | State Coordinator /CFO |  |
|  | Grant Approval | Grant approval to establish hub. Key Control: Expansion must be based on identified local partners and cleared security access. | National Coordinator | 2 Days |
|  | Site Preparation | Secure site, utilities, storage and basic facilities. Select a secure, accessible location close to farming communities. Ensure basic utilities and disability-friendly access. | CL / State Coordinator | 14 Days |
|  | Recruit & Assign Personnel | Appoint CLs, Sub-CLs, operators and MSPs. | State / National Coordinator/ HR | 10 Days |
|  | Deploy Assets & Equipment | Allocate and deploy machines and tools. Procure and deploy women-friendly machinery (ergonomic design). Register all items in the asset inventory with serial numbers. | Field Compliance Manager / CFO | 7 Days |
|  | Train Hub Personnel | Provide operational, safety and SOP training Appoint a Hub Manager and train MSPs. Where the CL is new, the State Coordinator determines the designated personnel to support with training the hub personnel including the Operations and GEDSI representatives. Key Control: Mandatory safety, GEDSI and operational training must be completed before equipment access. | Ops / GEDSI/CL | 10 Days |
|  | Register & Set Up Records | Establish all hub registers and systems. | Operation/Field Compliance Manager/ State Coordinators | Immediate |
|  | Membership Drive | Launch farmer registration via digital channels and group outreach. Key Control: Ensure female and youth representation. | Community Lead | Ongoing |
|  | Governance Setup | Establish hub management structure including women MSPs and He4She Club members to ensure accountability. | State Coordinator | 5 Days |
|  | Pre-Launch Readiness Review | Confirm operational readiness. | National / State Coordinator | 5 Days to launch |
|  | Official Hub Launch | Conduct formal launch and sensitisation. Gradually rollout services (pay-per-use or hire purchase) aligned with the key agricultural season. | State Coordinator | Launch Day |
|  | Post-Launch Monitoring | Log initial performance data into the ERP dashboard for M&E tracking. Monitor early operations and stabilise hub. | State / MEL Coordinator | 48 hours post-launch |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Low demand | Hub underutilised. | Demand assessment. |
| Community/cultural resistance | Poor acceptance or opposition to women operating heavy machinery in rural areas. | Early engagement. Secure pledges from traditional rulers (e.g., Emirs) and activate He4She champions to legitimize women operators. |
| Security threats | Vulnerability to theft or violence in fragile "red-zone" areas. | Implement "incident reporting" via ERP and use localized communication protocols for risk alerts. |
| Asset misuse | Loss or damage. | Asset controls. |
| Poor readiness | Operational failures. | Readiness review. |
| Equipment breakdown | Loss of revenue due to mechanical failure. | Implement preventive maintenance plans and establish service centres in key regions. |
| Cash handling risks at the hub level | Cash handling risks at the hub level. | Mandate cashless transactions and token-driven service bookings via the MamaTrak platform. |
| Inclusion gaps | Exclusion of women. | GEDSI oversight. |

Policy Guidelines

- No hub shall be launched without approval.

- Assets must not be deployed before site readiness.

- Appropriate community and stakeholder engagement must be carried out with the respective community agreements well documented.

- Hubs must comply with GEDSI standards.

- All hub expansion shall be based on demand-led planning.

- All assets deployed must be appropriately tagged, documented and handed over.

- Hub readiness must be conducted before launch and stabilisation controls must be in place.

- No hub shall operate without basic safety equipment (fire extinguishers, PPE) and a trained Safeguarding Focal Person on site.

- Hub leadership must include quotas for women, including widows, persons with disabilities and marginalized groups.

- All hubs must strictly adhere to WIMA’s formula for repayments and maintenance.

- Hubs must display the WIMA Code of Conduct and have a confidential reporting mechanism for SEAH (Sexual Abuse, Exploitation and Harassment).

- All hubs must maintain environmentally sound waste and energy management practices.

DAILY HUB OPERATIONS MANAGEMENT

Overview of Process

The “Daily Hub Operations Management” process defines the procedures for managing the day-to-day operations of WIMA Hubs to ensure efficient service delivery, equipment utilization, financial discipline, data integrity, safety and inclusion. It provides clear guidance for Community Leads (CLs), Sub-Community Leads (Sub-CLs), MSPs and State/Zonal Coordinators in operating WIMA hubs consistently and sustainably. This process ensures the efficient delivery of shared services such as land preparation, planting and harvesting while maintaining financial discipline, equipment uptime and safeguarding standards.

Scope

This process applies to WIMA hubs across LGAs, states and zones and covers daily operational activities including:

- Hub opening and closing procedures

- Equipment readiness and usage

- Farmer mobilization and service delivery

- Record keeping and reporting

- Financial transactions at hub level

- Health, safety, safeguarding and inclusion practices

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Daily booking schedule - Equipment availability and maintenance status - Approved service pricing - Hub registers and logbooks - Safety and safeguarding guidelines - WIMA Hub SOPs - Annual Operational/Implementation Plan - Member Database (WIMA App/ERP) - Equipment Maintenance Schedules - Approved Service Pricing Models | - Daily operations log - Equipment usage register - Service delivery records - Daily revenue record - Incident and safeguarding reports (if any) - Daily Equipment Inspection Report - Daily Revenue & Remittance Report - Service Completion/Close-out Records - Hub Satisfaction/Feedback Summary |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Opening of hub for daily operations - Receipt of service booking requests - Arrival of equipment, MSPs, or farmers at the hub - Start of the business day/agricultural season - Equipment maintenance or incident alert | - Community Lead (CL): Overall daily hub management, coordination of services, stakeholder engagement, reporting - Sub-Community Lead (Sub-CL): Support daily operations, supervise MSP activities, maintain registers - MSPs: Equipment operation, service delivery, basic maintenance, safety compliance - State/Zonal Coordinator: Oversight, supervision, compliance checks, escalation support |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA booking register / WIMA Operational ERP (Booking & Token System) - Equipment maintenance register - Revenue and cashbook register - Incident & safeguarding register - PPE and safety equipment - GPS Tracking & Remote Monitoring Tools - PPE & Safety Kits (Fire extinguishers, first aid) - Smart devices for data capture | - Number of services delivered per day - Equipment utilization rate - Zero safety or safeguarding violations - Accuracy and completeness of daily registers - Timely submission of daily/weekly reports - Equipment Utilisation Rate - Time to service fulfilment. - % Revenue collected vs. booked (Variance <5%). - Number of women served per day. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Open Hub and Conduct HSE Inspection | Open hub at designated time; ensure cleanliness, safety and readiness Conduct a security sweep. Ensure all safety equipment (fire extinguishers, first aid) is functional and accessible. Key Control: Hub cannot operate if basic HSE standards are unmet. | CL / Sub-CL | Start of day (07:00 – 07:30am) |
|  | Equipment Readiness Check | Inspect equipment condition, fuel levels, basic maintenance. Use the checklist to inspect tractors, harvesters and implements. Check fuel, fluids and tyre pressure. Log status in the Equipment Maintenance Register. Key Control: An equipment check must be done and logged in a register/MamaTrak before it is deployed for use. | MSP / Sub-CL | Daily (07:30 – 08:30am) |
|  | Confirm Bookings | Review daily booking schedule and confirm farmer requests. Confirm service requests via the MamaTrak or in-person. Verify membership status and land acreage. | CL / Sub-CL/ MSP | Daily |
|  | Demand Mobilization | Engage farmers physically and digitally to confirm demand | CL / Sub-CL/ MSP | Daily |
|  | Payment & Token Generation | Process payments via mobile money or digital wallets. Key Control: ERP generates a unique token to activate equipment only after payment confirmation. | Hub Finance Officer / MSP | Pre-service |
|  | Service Allocation | Based on confirmed bookings, assign and dispatch trained MSP(s) and equipment to the field. Ensure all operators are wearing mandatory Personal Protective Equipment (PPE). Key Control: Booking are only confirmed after payment. | CL | Daily |
|  | Service Delivery | Execute mechanized services at hub or on-site farms | MSP | As scheduled |
|  | Monitor Operations | Supervise service quality, safety and inclusion compliance. Track asset locations and idle time via GPS to ensure equipment is used solely for intended purposes and to prevent revenue leakage. Key Control: Critical assets are geo-tagged and monitored for revenue assurance. | CL / Sub-CL/ MEL Coordinator (remote) | Ongoing |
|  | Record Transactions | Capture service delivery, usage hours and revenues. Member signs off on completed work (hectares serviced). MSP logs usage hours and fuel consumption in the ERP. Key Control: All service data must be captured. | Sub-CL/MSP | Real-time |
|  | Incident Handling | Document equipment, safety, or safeguarding incidents. Key Control: All incidents must be captured. | CL/MSP | As required |
|  | Daily Reconciliation | Reconcile services delivered with revenue collected. Verify revenue sharing: % to MSPs/investors, % to WIMA for repayment and maintenance. Ensure all data is synced to ERP. | CL | End of day (5:00 – 6:00pm) |
|  | Close Hub | Secure equipment, registers and cash; close hub. Move equipment to dry, well-ventilated, secure storage. Lock the facility and update the Incident Reporting Register if damages occurred. | CL / Sub-CL | End of day |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Revenue Leakage | Unrecorded cash transactions or equipment misuse. | Mandate cashless payments and token-driven service bookings through the ERP system. |
| Equipment breakdown | Loss of revenue due to service delays. | Strict adherence to preventive maintenance plans and keeping technology spare parts at hubs. |
| Cultural Resistance | Pushback against women operating heavy machinery. | Activate He4She champions and traditional leader endorsements to legitimize operations. |
| Safety Incidents | Injuries to staff or farmers. | Mandatory operational training before equipment access and on-site Safeguarding Focal Persons. |
| Conflict/Insecurity | Threats to life and property in "red-zones". | Use ERP business intelligence for "incident reporting" and follow established Emergency Response Protocols. |

Policy Guidelines

- Only approved pricing and booking procedures must be used.

- Equipment must not be deployed without booking confirmation.

- Bookings are confirmed by full payment for service.

- All revenues must be recorded and receipted.

- PPE usage is mandatory and must be enforced.

- In the event of any incident, the safeguarding focal person must be notified.

- Hubs must be operational within approved hours.

- No cash handling without proper recording on the ERP/WIMA APP (MamaTrak).

- All registers and service records must be updated daily.

- Escalate unresolved issues to State/Zonal Coordinator within 24 hours

- Hubs must maintain a workplace free from discrimination, sexual harassment and bullying. Any violation results in immediate disciplinary action.

- No facilitation payments or bribes shall be accepted or offered.

- All financial transactions must have an audit trail in the ERP.

- Personal information of members (names, addresses, biometric data) must be processed according to the Nigeria Data Protection Regulation.

- All service delivery and training must prioritize WIMA's target of female and youth-led participation.

- Hubs must implement environmentally sound waste management and use climate-smart mechanisation practices.

- Employees/partners under the influence of alcohol or illicit drugs are strictly prohibited from operating machinery and shall face instant dismissal.

BOOKING, SCHEDULING & SERVICE FULFILMENT

Overview of Process

The “Daily Hub Operations Management” process defines the or receiving, validating, scheduling and fulfilling mechanization service requests at WIMA hubs. It ensures transparent access, optimal equipment utilization, revenue protection, service quality and gender-equitable allocation of mechanized services across communities.

Scope

This process applies to all mechanization service bookings made through WIMA hubs, whether manual or digital and covers activities from initial farmer request through service delivery completion and confirmation. It applies to Community Leads (CLs), Sub-Community Leads (Sub-CLs), MSPs and State/Zonal Coordinators.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Service request details (farmer name, location, service type, acreage) - Equipment availability and maintenance status - Approved service pricing - Hub service calendar - Registered Member Records - Equipment Availability Status - Mobile Payment Confirmation | - Approved booking record - Daily and weekly service schedules - Service fulfilment confirmation record/Sign-off Form - Exception and rescheduling log - Service Booking Confirmation - Unique Activation Tokens - Utilisation & Efficiency Reports |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Receipt of a mechanization service request from a WIMA member, farmer, cooperative, or agribusiness - Creation of a daily or forward service schedule - Seasonal agricultural demand | - Community Lead (CL): Overall control of booking, prioritisation, scheduling and service confirmation - Sub-Community Lead (Sub-CL): Receive booking requests, update registers/platform, track fulfilment - MSPs: Confirm availability, deliver assigned services, report completion - State/Zonal Coordinator: Oversight, compliance checks, conflict resolution, escalation |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA booking register / Operational ERP (MamaTrak) booking module - Equipment availability register - Service pricing guide - Token Generation System - GPS Tracking & GIS Mapping - Mobile Payment API | - Percentage of bookings fulfilled as scheduled - Equipment utilization rate - Average booking-to-service lead time - Number of service complaints or disputes - Percentage of women and vulnerable farmers served - Service fulfilment time (Target: <48 hours) - Equipment Utilisation Rate - % Cashless Transactions - Customer satisfaction rating |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Receive Service Request | Collect complete service request details including farmer identity, location, land size, preferred date and service type. | Sub-CL/ CL | Immediate |
|  | Validate Eligibility | Verify farmer eligibility, membership status, priority group (women, smallholders) and service availability | CL | Immediate |
|  | Check Equipment Availability | Confirm availability, condition and location of required equipment. Determine machinery needs based on crop type, acreage and location. Prioritise vulnerable and women-headed households. | Sub-CL / MSP | Immediate |
|  | Confirm Pricing, Payment and Booking | Select service on platform/apply approved "pay-per-service" rates and communicate cost to farmer. Log booking in register/platform with unique reference number. Key Control: Payment must be made via mobile money or digital wallet before scheduling. | CL/Hub Finance Officer | Immediate |
|  | Schedule Service and Allocation | Assign available equipment and a trained operator. Allocate date, time, equipment and MSP based on priority and efficiency. Key Control: Check "Equipment Maintenance Register" to ensure machinery is operational. | CL | Parallel |
|  | Token Generation | ERP generates a unique, time-bound activation token for the specific equipment. This ensures revenue assurance and prevents unrecorded use. | ERP System (Auto) | On Payment |
|  | Confirm with Farmer | Notify farmer of scheduled service details and conditions | Sub-CL |  |
|  | Dispatch Equipment & MSP | Release equipment and assign MSP for service execution. Coordinate transport of machinery to the farm site. Ensure the operator has all necessary PPE and safety kits. | CL | Scheduled date |
|  | Deliver Service | Execute mechanization service according to agreed scope and safety rules. Operator inputs the token to activate equipment. Key Control: Real-time GPS tracking monitors usage and idle time to prevent unauthorised diversion for applicable equipment. | MSP (Operator) | As per booking |
|  | Update Records | Update service hours, acreage covered and completion status. Member signs off on the completed acreage/hours. Capture yield/impact data directly into the ERP field form. Also, expected to capture all other M&E data as applicable. | MSP (Operator) | Post-service |
|  | Confirm Completion | Validate service completion with farmer and MSP | Sub-CL | Post-service |
|  | Fulfilment Review | Review the service completion record and updates the equipment status to "Available". Document delays, cancellations, or disputes and reschedule if needed | CL | 24 Hours |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Revenue leakage | Services delivered without proper booking or pricing, unrecorded cash payments or bypassing the booking system. | Mandatory booking reference and daily reconciliation. Strict enforcement of cashless payments and token-activated equipment; GPS monitoring detects unrecorded movement. |
| Overbooking | More services scheduled than equipment capacity. Multiple farmers requesting the same machine during peak season | Equipment availability check before scheduling. Use the ERP automated scheduling parameters to match demand with the nearest available equipment. Where equipment is not available, the ERP will not allow booking/payment. |
| Technology Gaps | Farmers or operators struggling with the digital booking interface. | Provide blended onboarding (offline support via Community Leads) and stepwise digital literacy training. |
| Elite capture | Powerful farmers crowd out women/smallholders | Enforced priority criteria and oversight |
| Service disputes | Disagreement on service quality or scope | Dual completion confirmation and complaint mechanism |
| Equipment misuse | Unauthorized deployment of machinery | Dispatch control and MSP accountability |
| Logistics Delays | Breakdowns during transport to remote farm sites. | Partner with local transporters and maintain adequate technology spare parts at each hub. |
| Data gaps | Incomplete or late booking records | Same-day register updates and supervision |

Policy Guidelines

- All bookings must be logged before service delivery.

- Only approved pricing and eligibility rules apply.

- Equipment must be dispatched without booking confirmation.

- Dual confirmation (farmer and MSP) required for completion.

- Exceptions and overrides must be documented and approved. Emergency overrides require CL approval and documentation.

- Walk-in services without booking are prohibited.

- Priority must be given to women and vulnerable farmers.

- All deviations must be reported to the State/Zonal Coordinator.

- All bookings, without exception, must be processed through the WIMA ERP system to ensure a clear audit trail.

- No equipment shall be deployed or activated without a confirmed digital payment and a valid system-generated token.

- All member and farm data collected during booking must comply with the Nigeria Data Protection Regulation.

- Hubs must reserve at least 80% of service capacity for women and 20% for youth-led farms.

- Operators must not perform services if the site is deemed unsafe or if the farmer/operator violates the WIMA SEAH (Safeguarding) Policy.

- Any attempt to solicit bribes for "priority scheduling" results in instant dismissal under the Anti-Corruption and Bribery Policy.

- Usage of local transporters shall only be approved by the State Coordinator. Transportation of equipment shall be via approved mean i.e., WIMA vehicle/tricycle, etc.

EQUIPMENT USAGE & OPERATOR MANAGEMENT

Overview of Process

The “Equipment Usage & Operator Management” process the describes the assignment, operation, monitoring and return of WIMA’s mechanised assets. This is the procedures for the authorized use of WIMA-owned or WIMA-managed equipment and the effective management of operators (MSPs) to ensure safety, asset protection, service quality, accountability and optimal equipment utilization across all WIMA hubs.

Scope

This process applies to all mechanized equipment deployed through WIMA hubs and all operators (MSPs) involved in service delivery. It covers operator eligibility, equipment use authorization, operating standards, supervision, incident handling and performance monitoring.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved booking and service schedule - Equipment availability and maintenance status - Maintenance & Safety Checklists - Approved operator roster and certifications - Safety and operating guidelines - Fleet Inventory (Serial Numbers/Insurance) - Operator Certification & Records - System-Generated Activation Tokens | - Daily Equipment Usage & Fuel Log - Operator assignment record - Incident and damage reports - Operator performance summary - GPS Asset Performance & Idle Time Report - Post-Season Equipment Valuation |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Approval of a service booking - Assignment of equipment and operator for service delivery - Commencement of field operation - Confirmed service booking and payment | - Community Lead (CL): Authorize equipment use, assign operators, supervise compliance - Sub-Community Lead (Sub-CL): Monitor daily usage, update registers, verify operator conduct - MSPs (Operators): Operate equipment safely, follow service scope, report issues - State/Zonal Coordinator: Oversight, audits, enforcement, sanctions approval |
| Tools Required | Key Performance Indicators (KPIs) |
| - Equipment usage register / digital platform - Operator roster and certification records - Maintenance and fuel logbooks - PPE and safety equipment - ERP Equipment Management Module - GPS Tracking & Remote Shutdown Tools - Personal Protective Equipment (PPE) - Digital Activation Interface | - Equipment downtime rate - Operator compliance rate - Number of safety incidents - Equipment damage frequency - Services delivered per operator - Machine Utilisation Rate - Equipment Uptime/Availability (%). - Number of Safety Incidents per 1,000 hours. - Revenue variance vs. machine engine hours |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Verify Booking Approval | Confirm that equipment use is tied to an approved booking reference | CL | Daily (Start) |
|  | Select Operator | Assign only trained and certified MSPs approved by WIMA. Ensure no operators are under the influence of illicit drugs or alcohol. Key Control: Verify operator’s license, health status and presence in the WIMA ERP database. | CL | Daily (Start) |
|  | Pre-Use Inspection | Conduct visual and functional checks before operation. Complete the checklist for fuel levels, fluids, tyre pressure and implement security. Log current engine hours in the ERP. | MSP / Sub-CL | 30 Mins |
|  | Authorize Equipment Release | Formally authorize equipment release for service. | CL / Sub-CL | 10 Mins |
|  | Enforce Safety | Ensure PPE usage and safe operating practices. Confirm operator has mandatory PPE (boots, gloves, goggles, high-vis). Check for women-friendly ergonomic adjustments. | CL / Sub-CL |  |
|  | Operate Equipment | Use equipment strictly for approved service and scope. Perform the service (e.g., ploughing) within the geofenced area. Observe climate-smart practices to reduce CO₂ and soil degradation. Key Control: Where applicable, Operator inputs the unique, time-bound system token to unlock and start the machinery. Usage is now tracked against the specific booking. | MSP (Operator) | On-site As booked |
|  | Monitor Usage | Track operating hours, fuel use and service quality. Key Control: Remote support team monitors GPS tracking for unauthorised movement or excessive idle time. Activate remote shutdown if geofence is breached. | Sub-CL/ Data/IT Officer | continuous |
|  | On-site Completion | Verify acreage covered against engine hours. Capture yield and soil condition data directly into the ERP field form. | Sub-CL/MSP | Post-service |
|  | Handle Incidents and Report | Report accidents, breakdowns, or misuse immediately. Key Control: Document any mechanical issues, minor accidents, or security threats in the ERP Incident Module for immediate escalation. | MSP /Sub-CL / CL/ State Coordinator | Immediate |
|  | Post-Use Inspection, Cleaning & Storage | Inspect equipment after service completion. Inspect for damage. Refuel and clean machinery. Store in dry, well-ventilated and locked hub facilities. | MSP (Operator) /Sub-CL | End of Day |
|  | Update Records | Record usage hours, operator name and condition | Sub-CL | Immediate |
|  | Evaluate Operator | Review operator performance and compliance | CL | End of Day |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Equipment damage | Improper or reckless use by operators | Certified operator requirement and inspections |
| Unauthorized usage | Equipment used outside approved bookings; Equipment being used for "side jobs" not captured in the system. | Authorization controls and usage logs. Use GPS-based idle monitoring and mandatory token activation; engine hours must match revenue records. |
| Asset Damage/Accidents/Safety incidents | Accidents or injuries to the operator or permanent damage to machinery. | Mandatory safety training before access; enforce use of PPE and conduct routine safety inspections. |
| Revenue loss | Misuse leading to downtime | Monitoring and rapid maintenance response |
| Operator misconduct | Abuse of authority or poor behaviour or Operators working under the influence. | Code of conduct and sanctions. Zero-tolerance policy; CL/Sub-CL must conduct visual sobriety checks and have the authority for instant dismissal for violations. |
| Data manipulation | Inaccurate usage records | Cross-check logs and supervision |
| Theft or Vandalism | Equipment stolen from the field or hub storage. | Hubs must meet security standards for storage; remote monitoring alerts assigned security vendors for prompt intervention. |

Policy Guidelines

- Equipment usage must strictly be linked to approved bookings.

- Equipment must only be operated by approved MSPs. Only WIMA-certified MSPs who have completed the training module on operation and safety are permitted to handle machinery.

- It is mandatory to carry out pre- and post-use inspections for equipment/machinery.

- There must be continuous supervision during operations either by the Sub-CL or the MSP team lead.

- Zero tolerance for safety or safeguarding violations.

- Operators are financially liable for damage due to negligence.

- Serious incidents must be escalated within 24 hours.

- No equipment shall be operated without functional safety features and a complete on-site first-aid kit.

- Equipment procurement must prioritise women-friendly designs (ergonomics and safety features) to support WIMA’s female participation target.

- Operators must act in the best interest of WIMA, maintaining professional boundaries and preventing misuse of confidential GPS data.

- All operators must abide by climate-smart mechanisation guidelines to minimise fuel waste and soil compaction.

- Operators and supervisors are required to report any suspected cases of sexual harassment or exploitation (SEAH) occurring during field activities immediately through the WIMA channels.

SERVICE COMPLETION VERIFICATION & CLOSE-OUT

Overview of Process

The “Service Completion Verification & Close-Out” process defines the formal steps required to validate that a mechanisation service (e.g., ploughing, harvesting) has been completed to the member's satisfaction. This process ensures data integrity by reconciling manual field reports with GPS tracking data and system tokens, while capturing critical yield and impact metrics for Monitoring and Evaluation (M&E).

Scope

This process applies to all mechanized services delivered by WIMA hubs, from completion of field operations to final service confirmation, documentation, exception handling and handover to finance, M&E and asset management processes.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved booking reference - Service scope and schedule - Equipment usage records - Operator activity logs - Farmer confirmation details - Active Service Token - GPS/GIS acreage data - Machine engine hour logs - Member Registration Detail | - Service completion confirmation record/signed off service completion - Signed or validated service close-out form - Exception or dispute log (if applicable) - Verified service data for billing and reporting - Updated ERP Equipment Status (Available) - Impact/Yield Data Report - Member Feedback/Satisfaction Entry |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Completion of a mechanized service by an MSP - Return of equipment from service location back to hub | - Community Lead (CL): Overall verification, approval of close-out, dispute resolution - Sub-Community Lead (Sub-CL): Field-level verification, record updates, documentation - MSPs (Operators): Declare completion, submit usage details, cooperate with verification - Farmer / Client: Confirm service delivery and satisfaction - State/Zonal Coordinator: Oversight, escalation resolution, compliance review |
| Tools Required | Key Performance Indicators (KPIs) |
| - Service completion / close-out form (manual or digital) - Equipment usage register - Booking and scheduling records - Incident and complaint registers - WIMA App/ERP (Field Form) - GPS Tracking Dashboard - Digital/Paper Sign-off Form - Token Deactivation Interface | - Percentage of services verified within 24 hours - Number of disputed services - Revenue leakage incidents linked to incomplete verification - Customer satisfaction rating - Accuracy of service data submitted - % Variance between GPS and manual acreage (<5%). - Hub Satisfaction Rating (Target: ≥80%). - Average time from work completion to data sync. - % Accuracy in yield data capture. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Declare Service Completion | Inspect the serviced land area. MSP formally notifies hub of service completion. Key Control: MSP must verify that the actual acreage covered or quantity processed matches the service booking before leaving the site. | MSP (Operator) | Immediate |
|  | Capture Service Details | Record acreage covered/quantity processed, hours used, location and date | MSP/Sub-CL | 5 Mins |
|  | Farmer Confirmation | Review work with the farmer. Obtain farmer confirmation of service delivery and satisfaction. Collect/submit satisfaction data via the WIMA app or hub feedback box to guide service improvements. Key Control: Obtain a physical or digital signature confirming the service was performed according to WIMA standards. | Member/Farmer/MSP | Post-service/ 10 Mins |
|  | Impact Data Capture | Capture yield estimates, soil condition and crop type directly into the ERP field form for M&E purposes. | MSP / Sub-CL | 30 Mins |
|  | Technical Logging | Record final engine hours, fuel consumption and any mechanical issues in the Equipment Maintenance Register. | MSP (Operator) | On Hub Return |
|  | Inspect Equipment Post-Use | Verify equipment condition, technical logging and note any damage. Update equipment status to "Available" in the fleet inventory module to allow for new bookings. Key Control: This will always be stated as available after service has been completed. However, if there is any damage, it needs to be flagged on the system as unavailable with appropriate evidence. | Sub-CL |  |
|  | Validate Against Booking | Cross-check delivered service against approved booking. Key Control: CL cross-references manual acreage reports against GPS/GIS data to detect unauthorised usage or revenue leakage. | CL | 2 Hours |
|  | Approve Service Close-Out | Formally approve service as completed and valid. Mark the service token as "Complete" in the ERP. This triggers the automated revenue sharing process (e.g., % to MSP). This may be automatically done by the ERP without human intervention | CL/System (automated) |  |
|  | Handle Exceptions | Document partial delivery, delays, complaints, or disputes | CL |  |
|  | Update Registers | Update service, usage and revenue-related registers | Sub-CL/System (automated) |  |
|  | Release Data to Finance | Submit verified service data for billing and revenue reconciliation | CL/System (automated) |  |
|  | Report & Escalate | Escalate unresolved disputes or incidents | CL |  |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Revenue leakage | Billing for unverified or incomplete services | Mandatory close-out approval |
| Service disputes | Disagreement on scope or quality | Dual confirmation and documentation |
| Data inaccuracies | Incorrect acreage or hours recorded. Intentional or accidental misreporting of land size. | Cross-check booking and usage logs. Mandatory use of GPS tracking and GIS mapping to pinpoint exact movement and acreage covered (where applicable) |
| Equipment damage concealment | Damage not reported post-service. Operators failing to report damage occurred during service. | Post-use inspection controls. Mandatory Daily Equipment Inspection and "Incident Reporting" registers verified by the Hub Manager upon return. |
| Client dissatisfaction | Poor service quality unaddressed | Feedback capture and escalation |
| Delayed reporting | Late submission of service data. MSPs failing to sync field data to the ERP promptly. | Same-day close-out requirement. KPI tracking for data integrity; 90% of data must be submitted via the app to maintain MSP certification. |
| Forced Sign-off | Members being pressured to sign for substandard work. | Implementation of a confidential Whistle Blower Hotline and periodic field audits by the Field Compliance Manager. |

Policy Guidelines

- No service revenue shall be accrued without verified close-out.

- Dual confirmation of service delivery (farmer and MSP) is mandatory. No service is considered complete and no MSP payment will be processed, without a verified member signature.

- Partial services must be clearly documented and backed by evidence.

- Farmers have the right to raise complaints before close-out.

- Repeated disputes shall trigger operator performance review.

- Equipment inspection is required before Hub close-out approval.

- Variances must be documented and approved.

- Only CLs can approve final close-out.

- Any acreage or quantity process discrepancy variance exceeding 10% between GPS data/equipment run time and manual reports must be investigated by the State Coordinator before token close-out.

- All farm-level and yield data collected must be handled according to the Nigeria Data Protection Regulation.

- Any safety incidents or near-misses occurring during service must be logged in the Register of Injuries and Incidents.

- CLs are required to conduct physical spot-checks on 5% of completed services monthly to ensure quality compliance.

- Revenue sharing shall strictly follow the formula (specified % to MSP, % to WIMA for maintenance/repayment) unless otherwise specified by a validated investor contract. This shall be automated on the system.

CUSTOMER FEEDBACK & COMPLAINT MANAGEMENT

Overview of Process

The “Customer Feedback & Complaint Management” process outlines the systematic approach to receiving, documenting, resolving and learning from customer feedback and complaints related to WIMA mechanization services. This process is designed to ensure member/farmer satisfaction, service quality improvement, safeguarding compliance, dispute resolution and protection of WIMA’s reputation, integrity and revenues.

Scope

This process applies to all feedback and complaints received from farmers, cooperatives, agribusiness clients, community members and partners across all WIMA operational locations including the HQ. It covers service-related, financial, equipment, operator conduct, safety and safeguarding complaints.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Feedback or complaint details or feedback from hub-based boxes - Service booking and close-out records - Equipment usage and operator logs - Safeguarding and incident guidelines - Entries from the WIMA App/Portal - SEAH/Whistle blower channels reports - Community village dialogue outcomes | - Feedback/Complaint/Grievance Register (ERP Log) - Resolution and corrective action record - Escalation and appeal log - Periodic customer satisfaction summary - Member Satisfaction/Impact Surveys - State/Regional Improvement Plans |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Receipt of customer feedback (verbal, written, digital) - Lodging of a complaint before, during, or after service delivery - Identification of dissatisfaction during service verification - A low service satisfaction rating in the ERP - An incident reported via the hotline - Strategic review cycle | - Community Lead (CL): First-level resolution for operational issues, primary complaint resolution, approval of actions, reporting - Sub-Community Lead (Sub-CL): Receive and log feedback/complaints, first response - MSPs (Operators): Cooperate in investigations and corrective actions - Safeguarding Focal Person: Handle sensitive, gender, or protection-related complaints - State/Zonal Coordinator: Oversight, appeals, enforcement, escalation - KM & Communications: Analysis of trends for visibility and branding. |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA Hub Feedback Boxes - ERP Feedback & Incident Module - Feedback & complaint register (manual) - Complaint categorization guide - Safeguarding referral pathways - Communication and notification tools - WIMA designed feedback/survey tools | - Percentage of complaints resolved within SLA - Number of repeat complaints - Customer satisfaction score - Number of safeguarding-related incidents - Percentage of feedback acted upon - Member retention rate on the app. - Number of service adjustments based on feedback - Hub Satisfaction Rating (Target: ≥ 80%). - Average Time to Complaint Resolution (< 7 days). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Receive Feedback / Complaint | Capture feedback via multiple channels: hub physical boxes, the WIMA App, or seasonal demonstration events. | Sub-CL/ CL | continuous |
|  | Acknowledge Receipt | Acknowledge receipt to complainant within agreed timeframe | CL | 24 Hours |
|  | Log & Categorise | Record complaint and classify (service, financial, safety, safeguarding). Enter all physical feedback into the ERP Feedback Module to ensure a digital audit trail and national visibility. Key Control: Sort entries into: (A) General Service Feedback, (B) Equipment/Technical issues, or (C) Serious Misconduct (SEAH, Bribery) | CL | Within 48 Hours of receipt |
|  | Initial Assessment | Assess severity, urgency and risk level. Key Control: Any complaint involving SEAH or Corruption must be immediately escalated to the HR/Safeguarding Officer or via the Business Hotline. | CL | 1-2 Days |
|  | Investigate Issue | Review records, interview parties, inspect evidence. Conduct a root-cause analysis for service-related complaints (e.g., machine downtime or operator conduct). | CL / Sub-CL |  |
|  | Determine Resolution | Determine necessary corrective actions, such as equipment repair, staff training, or member refunds/subsidies, redo service, sanction | CL/ State Coordinator | 1 Day |
|  | Implement Action | Execute agreed corrective or preventive actions | CL / MSP | Immediate |
|  | Communicate Outcome | Inform complainant of resolution and actions taken | Sub-CL / MSP | Within 24 Hours of decision |
|  | Close Complaint | Update the ERP status to "Resolved". Verify that yield/impact data reflects any service adjustments. | CL | 24 Hours |
|  | Escalate if Unresolved | Escalate unresolved or sensitive cases | CL | Immediate |
|  | Analyse Trends | Periodically review complaints for systemic issues | KMh/Comm Manager | Monthly |
|  | Continuous Improvement | Use monthly dashboard reviews to integrate feedback into State Improvement Plans and annual strategic priorities. | National Coordinator | Monthly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Unreported complaints | Issues handled informally and lost | Mandatory logging requirement |
| Escalation failure | Serious issues not escalated | Clear escalation timelines |
| Low Member Uptake /Retaliation | Victimization of complainants or fear of retaliation for complaining | Zero-retaliation policy. Use anonymous reporting mechanisms and a confidential whistleblower policy that guarantees protection |
| Reputational damage/ Adverse Publicity | Poor handling of complaints. Unresolved complaints leading to reputational damage. | Timely, transparent resolution. Nominate a spokesperson and implement a crisis management strategy for handling public feedback. |
| Repeat service failures | Same issues recur | Trend analysis and corrective action |
| Safeguarding breaches | Harm to women or vulnerable groups | Confidential handling and referral |
| SEAH Vulnerability | Risks to women and girls during programme activities. | Appoint a trained Safeguarding Focal Person at every Community/hub and display the WIMA Code of Conduct prominently. |
| Data Inaccuracy | Hubs failing to log negative feedback to look better on dashboards. | Conduct periodic field audits and independent satisfaction surveys to verify hub-level data integrity. |

Policy Guidelines

- All feedback and complaints must be formally logged.

- Safeguarding-related complaints must be handled confidentially following the appropriate policy guidelines.

- Resolution authorities and timelines must always be clearly defined and followed.

- It is mandatory for all outcomes to be communicated.

- Retaliation of any form against complainants shall not be tolerated.

- WIMA shall support employees and members who raise issues in good faith.

- WIMA guarantees that employees and members will not be victimised or treated unfairly for raising a complaint.

- Feedback channels must always be accessible, safe and confidential.

- Complaints should be resolved within defined SLAs.

- Safeguarding complaints shall bypass normal hierarchy to the appropriate focal person.

- Anonymous complaints must still be investigated.

- Zero-tolerance for any feedback indicating sexual abuse, exploitation, or harassment (SEAH) results in strict disciplinary action and potential legal proceedings.

- All reports must be handled with the highest level of confidentiality; identity is shared only on a need-to-know basis.

- Personal information captured during surveys must comply with the Nigeria Data Protection Regulation.

- Feedback tools must be available in local languages to ensure accessible reporting for rural communities.

- The Risk Committee will regularly review the risk register and the effectiveness of the complaint resolution process.

REVENUE COLLECTION & VERIFICATION

Overview of Process

The Revenue Collection & Verification process defines the financial controls for securing payments from WIMA members and partners. It describes how collecting, recording, verifying and reporting revenues generated from mechanized services delivered through WIMA hubs is carried out. It ensures revenue integrity, transparency, accurate revenue sharing, prevention of leakage and alignment with WIMA’s financial sustainability and governance requirements.

Scope

This process applies to all revenues generated at WIMA hubs, including payments from farmers, cooperatives, agribusinesses and partners for mechanization services. It covers revenue collection methods, verification against service records, reconciliation, reporting and escalation of discrepancies.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Service booking requests/Verified service completion and close-out records - Approved service pricing schedules - Payment evidence (transfer alerts, receipts) - Revenue collection registers - GPS Machine Usage Data | - Daily revenue collection register/Daily revenue & remittance report - Revenue verification and reconciliation report (booked vs. Collected) - Exception and discrepancy log - Periodic revenue summary report - Verified bank statement reconciliations - Revenue sharing disbursement schedule |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Completion of field operations/Approval of a verified service close-out - Receipt of payment (cashless or approved cash-based exception) - Initiation of a service booking - Daily hub closure | - Community Lead (CL): Authorise revenue collection, verify completeness, submit reports - Sub-Community Lead (Sub-CL): Collect payments, issue receipts, update revenue registers - CFO: National oversight, review reconciliations, approve revenue sharing, maintain controls - State/Zonal Coordinator: State/Zonal level oversight, spot checks, escalation of discrepancies |
| Tools Required | Key Performance Indicators (KPIs) |
| - Revenue and cashbook register / digital platform - Receipt books or digital receipt system/ WIMA ERP (Finance & Booking Modules) - Approved pricing schedule - Bank account statements (hub account) - Mobile Money/Digital Wallet APIs - GPS Asset Tracking Dashboard - Token Generation System | - Percentage of services billed vs verified services - Revenue variance rate - Timeliness of revenue remittance - Number of revenue-related complaints - Compliance with cashless policy - % Cashless Transactions (as per target) - Revenue Variance vs. Engine Hours (<5%). - % of Hubs achieving breakeven within 18 months. - Loan Repayment Rate (Target: ≥92%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Determine Amount Payable | Based on service request, calculate payable amount using approved pricing. Inform client of amount due and payment method. Member can make booking by themselves via booking platform. Selecting the service automatically applies the appropriate pricing. Key Control: Prices must be system-generated to prevent unauthorized discounts. No negotiation allowed. | CL/Sub-CL/MSP | Immediate |
|  | Payment Collection | Direct member to pay via mobile money or digital wallet. Collect payment via approved channel (bank transfer, POS). In the event that cash is being collected, the hub representative is expected to make the equivalent transfer to the designated account as the equipment will still be seen as available on the system until payment is made. Key Control: WIMA enforces a zero-tolerance approach to cash handling to mitigate theft and fraud. Ensure funds are deposited into designated hub account | CL/ Sub-CL / MSP | Pre-service |
|  | Payment Verification | Validate receipt via the Bank Alert API in the ERP. Key Control: The system automatically cross-references the payment with the booking ID. | System (automatic) | Immediate |
|  | Issue Receipt | Issue official WIMA receipt immediately after payment and token where applicable. Generate a unique activation token only after payment confirmation. This token is required to start the machinery. The token may be handed over to the MSP to utilise while delivering the service in the event the member does not have access to the WIMA platform. Key Control: Receipt issuance is mandatory. | CL/ Sub-CL / MSP/System (automatic) | Upon payment verification |
|  | Record Transaction | Record payment details in revenue register/platform | Sub-CL/System (automatic) | Immediate |
|  | Daily Reconciliation | Reconcile receipts with services and collections | CL | End of day |
|  | Usage Cross-Check | Compare engine hours and GPS-tracked acreage against the amount paid. Provide State Coordinator, CL and CFO with report on variances. Key Control: Identify "side jobs" or unrecorded usage via the Equipment Idle Monitoring extension. | Field Compliance Manager/Data Officer | Daily/ Weekly |
|  | Reconciliation | Reconcile hub accounts with WIMA assigned commercial bank statements. All transactions must possess a clear audit trail. Key control: Identification of variances for investigation | System (automatic) | Daily |
|  | Verify Revenue | Cross-check revenue against verified service records. Key control: independent verification | CFO | Daily/ Weekly |
|  | Handle Discrepancies | Investigate and document shortages or overages. Key control: Appropriate investigation to determine leakage | State Coordinator/ CL / CFO | Immediate |
|  | Report Revenue | Submit revenue reports to State/Zonal and National levels | CL | Weekly |
|  | Revenue Sharing | Apply the WIMA formula: % to MSPs, % to WIMA (allocated as % for repayment and % for wages/maintenance). | CFO / ERP | Weekly |
|  | Treasury Sync | Sync all verified data to the Executive Dashboard for national visibility on revenue growth and CAGR. | System (automatic) | Daily |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Revenue leakage | Payments collected but not recorded. Bypassing the digital system to perform "off-book" services for cash. | Mandatory receipts and reconciliation. Mandatory Token Activation and GPS movement tracking; discrepancies result in disciplinary action. |
| Undercharging | Informal price negotiation | Fixed pricing schedule enforcement |
| Cash diversion | Misuse of collected funds. | Cashless policy and prompt remittance. |
| Danger of Fraud/Billing errors | Incorrect amounts charged | Independent verification step |
| Delayed remittance | Funds held at hub | Same/next-day deposit requirement |
| Fraud or collusion | Manipulation of records. Inaccurate manual recording or staff collusion. | Segregation of duties (booking agent vs. finance officer) and automated ERP verification and spot audits |
| Cyber Breach/Phishing | Loss of funds through compromised digital wallets. | Implementation of cyber-security guidance and up-to-date firewall/anti-virus protocols. |
| Payment Default | Failure of members to pay for services delivered on credit. | Enforce Payment-First Policy; utilize "Lease-to-Own" frameworks with strict milestone triggers. |

Policy Guidelines

- WIMA mechanised services is a payment first policy. Service shall not be rendered on credit bases to members. However, advance payment and loading of wallet for future draw down shall be accepted.

- All payment shall be cashless. Therefore, 100% of mechanisation service fees must be collected through approved digital channels. No staff or partner is authorised to accept cash.

- Any form of cash collections requires documented exception approval.

- Revenue discrepancies must be escalated and investigated within 24 hours.

- The approved pricing schedules must be on the system. Only the system price schedule shall be used for all bookings.

- It is mandatory for receipts to be issued for every payment.

- Daily reconciliation between services and revenue must be conducted.

- There shall be an independent verification by finance function as well as a secondary verification based on equipment data obtained remotely as it applies.

- All refunds or service adjustments must be approved based on WIMA's established authorisation limits.

- There shall be no alteration to the revenue sharing formula without written approval from the Board of Trustees.

- No facilitation payments or "priority fees" shall be solicited or accepted. Violations result in instant dismissal.

- Internal Audit must conduct a 100% post-payment audit on a quarterly basis to ensure zero audit infractions.

- All financial records and member payment details must be stored securely in accordance with the Nigeria Data Protection Regulation.

REVENUE SHARING & DISBURSEMENT

Overview of Process

The “Revenue Sharing & Disbursement” process defines the sequence of activities for allocating and releasing funds generated from WIMA’s mechanisation services. This process ensures that all partners (MSPs, investors and referrers) are paid accurately and promptly according to established formulas, while WIMA retains the necessary portions for equipment repayment, wages and hub maintenance.

Scope

This process applies to all revenues verified and cleared under the Revenue Collection & Verification process and covers revenue allocation to operators, hub stakeholders, service providers and WIMA central structures, as applicable.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Verified revenue reports - Approved revenue sharing framework - Operator and beneficiary registers - Bank account details of beneficiaries - Authorized Signatures/Memos | - Revenue sharing computation sheet - Approved disbursement schedule - Payment confirmation records - Exception and adjustment log - Released Funds Receipt/Confirmation - Daily Closing Balance Report |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Completion of revenue verification and reconciliation - Availability of cleared funds in designated WIMA hub accounts - Automated verification of payment in ERP - Approved payment/settlement instruction | - CFO: National oversight and final financial accountability, calculate revenue shares, prepare disbursement schedules - Community Lead (CL): Validate beneficiary lists and service records, daily reconciliation. - State/Zonal Coordinator: Review and approve disbursement summaries - National Coordinator: Final oversight and exception approvals - Internal Audit: Validation of correctness before release |
| Tools Required | Key Performance Indicators (KPIs) |
| - Revenue sharing template / spreadsheet - Approved revenue sharing policy - Banking and payment platforms - Disbursement registers - ERP Finance & Revenue Module - WIMA Official Payment Memo/Vouchers - Digital Wallet APIs | - Timeliness of revenue disbursement - Accuracy of revenue sharing calculations - Number of revenue-sharing disputes - Percentage of disbursements made cashless - % Error rate in disbursements (Target: 0%). - Disbursement turnaround time (Target: <24 hours). - Zero Audit Infractions. - % Revenue collected vs. share disbursed. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Revenue Verification | Confirm only verified and reconciled revenue is shareable. Cross-reference daily bank alerts with completed service tokens in the ERP. Ensure 100% of the service fee is in the WIMA account before calculating shares. | ERP (Auto) / CFO | Daily (Morning) |
|  | Apply Sharing Formula | Apply approved revenue sharing ratios | ERP (Auto) / CFO | Daily/ Weekly (based on disbursement routine) |
|  | Prepare Disbursement Schedule | Compile amounts payable per beneficiary. Generate an approved instruction for payment/settlement. Key Control: The memo must contain full particulars of the payment and the specific booking IDs involved. | ERP (Auto) / CFO | 1 – 2 Hours |
|  | Verify & Validate Approval | Review beneficiary list and amounts. Key Control: Validate approval based on authorization limits. Ensure the approver has the mandate for the specific value of the transaction. | Internal Control / Audit | Within 30 mins |
|  | Determine Transfer Medium | Select between the Online Banking Platform (for immediate settlement) or Manual Bank Instruction (for accounts requiring physical letterhead signatures). | CFO | Immediate |
|  | Disbursement Authorization | Signatories authorize the transfer using hardware tokens. Signatories must respond to authorization requests within 30 minutes to avoid delays. Where physical cheques, it is signed. Key Control: application of authorisation before disbursement of fund. | Authorized Signatories | Within 30 mins |
|  | Execute & Confirm Transfer | Upload details to the e-banking platform or transmit signed letters to the bank. Monitor the account to confirm the successful debit of funds. | CFO | Immediate |
|  | Record Payments | Update disbursement registers/pass entry to indicate payments done on ERP | CFO |  |
|  | Notify Beneficiaries | Send automated payment confirmations via SMS or email to MSPs/Investors through the ERP Messaging module. | CFO/ERP | Post-transfer |
|  | Daily Reconciliation | Obtain closing bank balances and sync with the Executive Dashboard. Ensure the daily liquid position of the hub is communicated to the National Coordinator. | ERP (Auto) / CFO | Close of Day |
|  | Handle Exceptions | Resolve disputes or adjustments. | CFO / State Coordinator |  |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Incorrect sharing | Errors in calculations | Standard templates and reviews |
| Revenue Leakage | Bypassing the formula to pay MSPs in cash. | Zero-tolerance for cash handling; all payments must originate from the WIMA hub account via digital channels. |
| Unauthorized payments | Payments to ineligible parties | Register-based validation |
| Delayed payments | Operational bottlenecks, Delays in authorization leading to MSP dissatisfaction or reduced equipment uptime. | Disbursement timelines enforced. Mandatory 30-minute response time for signatories; utilize mobile e-banking apps for remote approval. |
| Collusion or favouritism | Manipulation of beneficiary lists | Separation of duties and oversight |
| Disputes | Disagreement on shares | Transparent communication and logs |
| Incorrect Formula Application | Paying the wrong percentage due to manual error. | Use the ERP automated revenue sharing module to calculate splits based on pre-set parameters. |
| Fraudulent Beneficiaries | Diverting funds to accounts not registered in the system. | Enrolment Module Control; payments can only be made to verified partner/MSP bank accounts registered in the master data. |

Policy Guidelines

- All revenue sharing must follow approved policy.

- Standard formula for disbursement shall be approved by the Board of Trustees. For example, it may be something like X% to MSPs/Investors; X% to WIMA (X% for equipment repayment, X% for wages/hub maintenance). Adjust for Referral (X%) or Booking Agency (X% to Investor) as per the contract.

- All transaction instruments must possess clear audit trails in the ERP. No manual payments outside the system are permitted.

- Sharing formula shall be automated and any manual override must obtain documented approval.

- It shall be reviewed periodically based on impact, finding and other research that indicate a need for revision.

- Revenue shall only be shared after full verification.

- Approved sharing formulas shall not be altered at state or hub level.

- There shall be appropriate segregation of duties as it relates to revenue calculation, approval and payment.

- The individual who records service completion cannot be the same individual who authorizes the disbursement of shares.

- A revenue sharing disbursement shall be cashless. No cash disbursement permitted

- No disbursement above the established threshold shall be processed without the National Coordinator’s written approval.

- Disbursement disputes must be escalated within 48 hours and all exceptions shall be investigated, handled and documented.

- Internal Audit must conduct a 100% post-payment audit quarterly to ensure zero infractions.

- No alterations to disbursement amounts (words or figures) on existing instruments are allowed. A new voucher must be prepared if errors occur.

- Any staff soliciting "processing fees" from MSPs to release their revenue share shall instant be dismissed under the Anti-Corruption Policy.

- This process shall be periodically or following audit findings, changes in revenue-sharing arrangements or strategic adjustments approved by WIMA leadership.

BUDGET DEVELOPMENT & FINANCIAL CONTROL

Overview of Process

The “Budget Development and Financial Control” process defines the cycle for designing, approving and monitoring WIMA’s financial resources. This process is essential for ensuring accountability, reducing donor dependency and maintaining the revenue sharing formula required for hub sustainability. It ensures financial discipline, alignment with strategic priorities, cost efficiency, accountability and compliance with approved financial policies.

Scope

This process applies to all WIMA budgets, including annual organizational budgets, project-specific budgets, hub operational budgets and donor-funded programme budgets. It covers budget planning, approval, expenditure control, monitoring, variance management and reporting.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Strategic plan and annual work plans - Approved projects and activity plans - Historical financial data - Revenue forecasts and funding commitments - Hub performance data (Asset utilization/Yields) - Implementation Roadmap and Learnings - Market Intelligence & Crop Calendars | - Approved annual and project budgets - Budget implementation plans - Budget variance and performance reports - Approved Annual Operational Budget/budget revisions (where applicable) - Audited Financial Statements - Cost-Recovery & Sustainability Plans |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Annual planning cycle - Approval of a new project or funding agreement - Significant operational or strategic change requiring budget revision - Monthly operational review | - National Coordinator / Project Lead: Overall budget leadership and strategic alignment - CFO: Accountability, national oversight handling budget preparation, controls, monitoring and reporting - State/Zonal Coordinator: Develop and manage state/regional budgets - Community Lead (CL): Prepare hub-level operational budgets and track spending - Board of Trustees / President: Fiduciary oversight, review and approve consolidated budgets |
| Tools Required | Key Performance Indicators (KPIs) |
| - Budget templates and financial models - Accounting and financial management systems/ERP Finance & Reporting Modules - Approved chart of accounts - Budget tracking and variance analysis tools - Business Intelligence (BI) Dashboards - Revenue Sharing Formulas - Authorization Limit Schedules | - Budget Variance vs. Actual Spend (<5%). - Percentage of expenditures within approved budget - Timeliness of budget preparation and approval - Cost efficiency indicators - % of hubs achieving breakeven within 18 months. - Loan Repayment Rate (Target: ≥92%). - Annual Governance Audit Score (≥85%) |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Baseline & Trend Analysis | Extract data from the ERP to analyse historical hub revenue, asset utilization and cost efficiency. Review learnings from the previous implementation cycle to inform new priorities. | CFO / MEL Coordinator | 2nd week of the year (Annual) |
|  | Define Budget Assumptions | Establish planning assumptions, timelines and ceilings Key Control: Draft budgets must apply the split (% MSPs/Investors, % Repayment, % Wages/Maintenance). Align allocations with the four strategic pillars: Expansion, Revenue, Structure and Digital Transformation. | National Coordinator / CFO |  |
|  | Prepare Draft Budgets | Develop draft budgets at national, state and hub levels. The CFO supports with templates and guidelines to ensure submission quality. | CFO / State / CL | 3rd week of the year |
|  | Consolidate Budgets | Consolidate all unit budgets into a master budget | CFO | 4th week of the year |
|  | Review Budget | Review for alignment with strategy and funding. Review the draft for cost optimization and adherence to the Anti-Corruption and Bribery Policy. Ensure funds are allocated for preventive maintenance and revolving funds to recapitalise hubs. | Executive Team | 48 Hours |
|  | Approve Budget | Formal approval of budgets. Key Control: Formally present the budget to the Board of Trustees for fiduciary oversight and sign-off. No project may commence without a BOT-approved implementation plan and budget. | Board of Trustees | 6th week of the year |
|  | Communicate Budget | Share approved budgets and limits | CFO | Immediate |
|  | Control Expenditure | Ensure spending stays within approved limits. Key Control: Release funds according to established authorisation limits. | CFO/ Signatories | Ongoing |
|  | Real-time Monitoring | Track actuals against budget periodically. Use ERP dashboards to track engine hours vs revenue collected to detect leakage or inefficiencies. Review "Revenue Variance" monthly to ensure collection targets are met. | CFO | Monthly |
|  | Analyse Variances | Identify and explain variances | CFO / Budget Holders | Monthly/ Quarterly |
|  | Report Budget Performance | Submit periodic budget performance reports to State Coordinator and President | CFO | Monthly/ Quarterly |
|  | Quarterly Audit & Risk Review | Carry out audit and risk review. Key Control: Internal Audit conducts a 100% post-payment audit and reviews compliance with financial controls. Present risk exposures and corrective action plans to the BOT Finance Committee. | Internal Audit | Quarterly |
|  | Implement Corrective Actions | Adjust activities or request revisions, refine financial strategies based on evidence from the MEL system and market information. Update the Strategic Initiative Matrix to reflect resource reallocation. | National / State Coordinator | Quarterly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Overspending | Expenditure exceeds budget | Pre-approval controls and monitoring |
| Poor budgeting | Unrealistic cost estimates | Use historical data and review |
| Revenue Shortfalls | Hubs fail to generate enough income to cover maintenance or repayments. | Diversify income streams through training fees, consultancy and equipment sales. |
| Theft or Fraud | Unauthorised diversion of funds or unrecorded cash transactions. | Zero-tolerance for cash handling; mandate 100% cashless transactions via mobile money and token-activated equipment. |
| Misalignment | Budget not aligned to strategy | Strategic review step |
| Dependency Risk | Relying too heavily on a single donor or income source. | Implement an adequate reserves policy and identify new co-funding partners. |
| Unauthorized spending | Expenses incurred without approval | Defined approval thresholds |
| Weak monitoring | Late detection of variances | Periodic reporting |
| Over-Expansion | Scaling to new states without adequate financial buffers. | Enforce milestone triggers and foundational imperatives (e.g., minimum women demand threshold) before fund release. |

Policy Guidelines

- No expenditure without approved budget. Budgets must be approved before expenditure.

- There must be clear guidelines provided by the CFO, such as clear budget ownership and ceilings which shall influence budget implementation.

- All expenditure above pre-set thresholds require written approval from the National Coordinator or BOT.

- All expenditures shall be pre-approved.

- The CFO shall conduct regular variance analysis and report them accordingly.

- Any budget reallocation shall require approval.

- All emergency spending must be documented and ratified.

- Budget performance shall be reviewed quarterly.

- Personnel who record service completion cannot be the same individuals who approve budget disbursements.

- All financial transactions, budget adjustments and approvals must be captured in the ERP to ensure a clear audit trail.

- All budgets must demonstrate a path to hub break-even within 18 months of launch.

- Fees must be processed via the WIMA digital platform; no staff member is authorised to accept cash for services.

- WIMA will produce annual public reports and audited financials to maintain stakeholder and investor confidence.

FINANCIAL ACCOUNTABILITY & INTERNAL CONTROLS

Overview of Process

The “Financial Accountability & Internal Controls” process establishes the internal control framework and accountability mechanisms governing WIMA’s financial operations. It defines how financial responsibilities are segregated, monitored, reviewed and enforced to safeguard assets, prevent fraud and misuse, ensure compliance with approved policies and promote transparency across all levels of the association.

Scope

This process applies to all financial activities undertaken by WIMA at national, state/zonal and hub levels, including revenue handling, expenditures, budgeting, fund transfers, revenue sharing, procurement and financial reporting.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved financial policies and SOPs - Financial records and registers - Audit reports and management letters - Exception and incident reports - Approved Annual Budgets - Bank Statements - Service Completion records - Authorization Limit Schedules | - Internal control compliance reports - Financial exception and incident logs - Audit findings and corrective action plans - Periodic financial governance reports - Monthly Budget Performance Reports - Audited Financial Statements - Revenue Sharing Disbursement Logs |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Commencement of any financial transaction or activity - Periodic financial reviews and audits - Detection of financial irregularities or control breaches - Initiation of any expenditure or disbursement - Quarterly audit cycle | - National Coordinator / Project Lead: Overall accountability for financial governance - CFO: Overall financial strategy, accountability and national oversight. Design, implementation and monitoring of internal controls - State/Zonal Coordinator: First-line oversight and enforcement at regional level - Community Lead (CL): Compliance with controls at hub level - Board of Trustees / President: Fiduciary/independent oversight and enforcement - Internal Audit: Validation of controls and post-payment audits. |
| Tools Required | Key Performance Indicators (KPIs) |
| - Financial policies and SOP repository - Accounting and reporting systems/ WIMA ERP (Finance & Audit Modules) - Control checklists - Audit and review templates - Business Intelligence (BI) Dashboards - Token Generation System - Whistle-blower Hotline | - Number of control breaches reported - Timeliness of issue resolution - Audit compliance score - Frequency of financial reviews - % Cashless Transactions - Revenue Variance vs. Engine Hours (<5%). - Loan Repayment Rate (Target: ≥92%). - Annual Governance Audit Score (≥85%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Define Control Framework | Establish segregation of duties and control structure | CFO | Continuous |
|  | Assign Financial Roles | Assign and document financial responsibilities at the state and hub level | State Coordinator/ CL | As required |
|  | Implement Authorization Limits | Apply approval thresholds for transactions | CFO | Continuous |
|  | Enforce Segregation | Ensure no single person controls end-to-end transactions. Ensure the person who initiates a booking or records work is never the same person who authorises the disbursement of funds. | All Levels/Internal Auditor | Continuous |
|  | Authorization Check | Validate authorisations for transaction Key Control: Validate all payment requests against established authorisation limits. Any expenditure above pre-set thresholds require BOT sign-off. | Internal Auditor | Within 24 Hours/ process SLA |
|  | Revenue Verification | Cross-reference bank alerts with system-generated service tokens/service completion records. Ensure the revenue matches the machine engine hours and acreage logged in the ERP. Key Control: for revenue assurance | Internal Control/Field Compliance/ Data Officer | Daily |
|  | Conduct Routine Reviews | Perform periodic checks on transactions and records. Review and detect any exception, deviation or irregularities Key Control: Conduct a 100% post-payment audit quarterly to verify the validity of disbursements and compliance with policies. | Internal Auditor | Periodically (monthly) |
| 6b | Asset Monitoring | Review and detect any exception, deviation or irregularities. Use GPS tracking and remote monitoring to identify "side jobs" or unrecorded usage that leads to revenue leakage. | Field Compliance Manager | Real-time |
|  | Investigate Issues | Investigate control breaches | Internal Auditor / CFO/ Field Compliance Manager | Immediate |
|  | Report Governance Status | Report internal control effectiveness | CFO/Internal Auditor | Quarterly/At BOT meetings |
|  | Reporting & Review | Present performance metrics via BI dashboards to the BOT, highlighting budget variances and hub break-even status. | CFO / National Coordinator | Monthly |
|  | Apply Corrective Actions | Implement sanctions or process fixes | National Coordinator / Board of Trustees | Immediate |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Fraud or misappropriation | Intentional misuse of funds | Segregation and oversight |
| Control override | Bypassing approvals | Approval hierarchies and audits |
| Revenue Leakage | Bypassing the system to perform services for cash. | Mandatory token activation for machinery; engine hours must match revenue records. |
| Weak enforcement | Controls not applied | Governance oversight |
| Collusion | Coordinated manipulation | Independent reviews |
| Poor documentation | Incomplete records | Mandatory record-keeping |
| Danger of Fraud or Error | Collusion or inaccurate manual recording. | Use segregated duties and automated ERP verification of payments via Bank Alert APIs. |
| Cyber Breach (Phishing) | Loss of funds or sensitive data via digital platforms. | Maintain up-to-date firewalls and anti-virus software and provide staff with cyber-security guidance. |
| Dependency Risk | Over-reliance on a single funding source | Diversify income via value-added services (training, consultancy) and maintain a reserves policy. |

Policy Guidelines

- There must be clear segregation of duties enforced within WIMA.

- There shall be defined authorization and approval limits set out by the Board of Trustees.

- Independent review and oversight shall be carried out on transactions. The Internal Auditor shall represent the Board of Trustees in this regard.

- Every financial transaction, from booking to disbursement, must possess a clear, unalterable audit trail in the ERP.

- No individual shall control authorization, execution and recording

- All financial controls are mandatory.

- Control breaches must be reported within 24 hours.

- Sanctions shall be applied in line with WIMA policies.

- No facilitation payments, bribes, or kickbacks shall be offered or accepted. Violations result in instant dismissal.

- 100% of revenue must be processed via the WIMA digital platform. Staff are strictly prohibited from accepting cash for services.

- Employees must report suspected corruption to the designated Compliance Officer or via the whistleblowing channel; WIMA guarantees protection from retaliation.

- All financial and member records must be stored securely, complying with the Nigeria Data Protection Regulation.

- WIMA shall operate in accordance with Central Bank policies, identifying and reporting anomalies involving Politically Exposed Persons (PEPs) as applicable to organisations of its nature.

COST OPTIMISATION & EXPENSE APPROVAL

Overview of Process

The “Cost Optimisation & Expense Approval” process is for planning, reviewing, approving and controlling expenditures across WIMA to ensure cost efficiency, value for money and alignment with approved budgets and strategic priorities. It embeds cost optimisation principles into day-to-day decision-making while enforcing strong expense approval controls.

Scope

This process applies to all operational and programme-related expenditures incurred at national, state/zonal and hub levels, including administrative costs, operational expenses, maintenance costs, travel and project expenditures.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved annual operational budgets and cost ceilings - Expense requests and supporting documentation - Purchase Requisitions (via ERP) - Supplier/Vendor Quotations - Approved vendor rates and cost benchmarks - Historical expenditure data - Market Intelligence & Price Lists | - Approved expense requests - Expense approval logs - Cost optimisation review reports - Variance and savings reports - Approved Payment Vouchers and Memos - Cost Efficiency & Hub Profitability Analytics - Audited Financial Statements |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Identification of a spending need - Submission of an expense or procurement request - Periodic cost review and optimisation exercises - Requirement for equipment, parts or services - Start of a monthly operational expense cycle - Request for hub-level maintenance or repairs | - National Coordinator / Project Lead: Oversight of cost efficiency and policy enforcement. Project-level budget planning and implementation. - CFO: Overall accountability for cost efficiency and budget handling. Review, approve and monitor expenses - State/Zonal Coordinator: Validate and approve state-level expenses - Community Lead (CL): Initiate expense requests and ensure value for money - Board of Trustees / President: Oversight of high-value or exceptional expenses |
| Tools Required | Key Performance Indicators (KPIs) |
| - Expense request and approval templates - Budget tracking system - Approved vendor and rate lists - Cost benchmarking tools - WIMA ERP (Finance & Procurement Modules) - Authorisation Limit Schedule - Business Intelligence (BI) Dashboard - Official Payment Tokens/Hardware | - Percentage of expenses within budget - Cost savings achieved through optimisation - Timeliness of expense approvals - Number of rejected or escalated expenses - % Reduction in hub admin costs via automation. - Budget Variance vs. Actual Spend (Target: <5%). - % Procurement via open competition (for >N100k). - % Hubs achieving break-even within 18 months |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Identify Expense Need | Define purpose, scope and justification for expense | CL / State Coordinator |  |
|  | Check Budget Availability | Confirm expense is within approved budget. Key Control: Requisitions must be mapped to a specific budget line and strategic pillar (e.g., Expansion). | CL / CFO | Immediate |
|  | Prepare Expense Request | Complete expense request with documentation | CL / State Coordinator |  |
|  | Submit for Approval | Submit request to appropriate authority | CL |  |
|  | Review & Approve | Review necessity, cost and compliance | State/ National Coordinator | 1-2 Hours |
|  | Review Cost Options | Assess alternatives and cost-saving options (competitive sourcing). Reviews requests for efficiency. For logistics or services exceeding N100,000, conduct an open competition. Prioritise women-owned or minority-owned vendors. Key Control: To ensure financial prudence. Verify if volume pricing discounts are available (e.g., for hardware pr equipment or mobile plans) | Operations | 1-3 Days |
|  | Sign off | Ensure that appropriate authorisation has been obtained, request is aligned with budget and sourcing/cost options are in the best interest of WIMA Key Control: Vet third parties for SEAH violations and corruption risks. Ensure proposed vendors understand WIMA’s zero-tolerance policies. | Internal Auditor | Within 24 Hours |
|  | Authorisation | Grant authorisation to make payment Key Control: Validate against authorisation limits. Expenditure above thresholds requires President or Board of Trustees (BOT) sign-off. | President/ National Coordinator | 24 Hours |
|  | Execution & Payment | Process payment via cashless channels (Mobile Money/Online Bank). Log approved expense on ERP as disbursed Key Control: Signatories | CFO | 4 Hours |
|  | Asset/ Inventory Update | If the expense involves hardware or spares, register the item in the Master Asset Register or Warehouse inventory. | Field Compliance Officer/Operations | Post-purchase |
|  | Post-Payment Audit | Conduct audit of payment within the period. Key Control: Internal Audit conducts a 100% post-payment audit quarterly to verify the validity of all disbursements. | Internal Audit | Quarterly |
|  | Escalate Exceptions | Escalate over-budget or unusual expenses | Internal Audit | Immediate |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Cost overruns | Spending exceeds budget. Hub expenses exceeding the 30% maintenance/wage allocation. | Pre-approval and monitoring. Use real-time BI dashboards to track engine hours vs. revenue and implement automated "stop-spend" alerts in the ERP. |
| Wasteful spending | Poor value for money | Cost comparison and review |
| Revenue Leakage/Theft | Unauthorised diversion of funds or unrecorded cash transactions. | Mandate 100% cashless transactions and maintain strict segregation of duties between initiators and approvers. |
| Bribery and Kickbacks | Pressure to award contracts to unvetted vendors in exchange for improper benefits. | Enforce the Anti-Corruption and Bribery Policy; require open competitive bidding for all significant logistics services. |
| Unauthorized expenses | Expenses incurred without approval | Approval hierarchy enforcement |
| Delays | Slow approval affecting operations | Defined timelines |
| Collusion | Inflated or biased costs | Independent review and benchmarks |
| Conflict of Interest | Staff or contractors engaging in activities that personally benefit themselves or relatives. | Mandatory declaration of interest and immediate reporting of potential conflicts to management. |

Policy Guidelines

- It shall be mandatory to have a business justification for all expenses.

- Budget availability checks shall be done before approval.

- The process shall comply with the defined approval thresholds.

- There shall be dual review for higher-value expenses.

- The CFO shall continuously carry out post-spend monitoring and review of expenses.

- There shall be no expense without prior approval.

- Cost optimisation must be seen as a shared responsibility throughout the organisation. Therefore, cost optimising options must have been explored and presented during the approval.

- Every emergency expense shall require post-approval.

- Expense approvals must align with approved budget lines.

- No staff member or partner is authorised to accept or handle cash for WIMA services or expenses.

- The person who initiates a purchase or records a service completion cannot be the same person who authorises the payment.

- WIMA shall make every effort to contract services from women-owned enterprises to support regional economic empowerment.

- All operational expenses must be vetted against the hub's path to break-even within 18 months.

- All transactions must possess an unalterable digital audit trail in the ERP; alterations to payment instruments are strictly prohibited.

- Any suspected financial misconduct must be reported via the Business Hotline; WIMA shall protect whistleblowers from any form of retaliation.

EQUIPMENT ALLOCATION & DEPLOYMENT

Overview of Process

The “Equipment Allocation & Deployment” process describes the sequence of activities for planning, approving, allocating, deploying and tracking WIMA-owned or managed mechanized equipment across hubs, states and service locations. It ensures optimal utilization, equitable access, asset protection, transparency and alignment with operational demand and strategic priorities.

Scope

This process applies to all tractors, implements and mechanized equipment managed by WIMA, including equipment assigned to hubs, temporarily deployed across LGAs or states or used for pilot projects and demonstrations.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Equipment inventory and asset register - Service demand forecasts and booking data - Approved project and seasonal plans - Equipment condition and maintenance status - WIMA Expansion Roadmap & Hub Needs Assessments - Asset Register (Master Data) - Logistics Policy & Procurement Guidelines - Hub Location Readiness Checklist | - Equipment allocation and deployment plan - Equipment movement, handover and Inspection records - Updated ERP asset and deployment registers - Exception and incident reports - Signed Delivery Notes and Contracts - Insurance Certificates for Transit |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Approved service demand or project plan - Establishment/activation of a new hub - Seasonal demand surge or redeployment need - Equipment procurement, acquisition or return | - National Coordinator / Project Lead: Strategic allocation and inter-state deployment approval - State/Zonal Coordinator: State-level allocation planning and oversight - Community Lead (CL): Hub-level deployment planning and custody - Sub-Community Lead (Sub-CL): Day-to-day tracking and coordination - Field Compliance/ Operations Manager: Asset records and deployment controls |
| Tools Required | Key Performance Indicators (KPIs) |
| - Equipment asset register - Deployment and movement forms - Booking and scheduling system - GPS or tracking tools (where available) - ERP Logistics & Deployment Module - Asset Tags - Journey Management Forms | - Equipment utilization rate - Downtime due to poor allocation - Number of unauthorized deployments - Incidents of loss or damage during deployment - Average time from allocation to hub arrival. - % of assets insured during transit (Target: 100%). - Number of transit-related damage incidents. - % Hubs with confirmed equipment inventory sync |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Assess Equipment Demand | Analyse service bookings and seasonal needs | CL / State Coordinator | 1-2 Days |
|  | Review Equipment Availability | Check inventory, condition and location. Key Control: This must align with ERP asset status and location | State Coordinator / Operations |  |
|  | Prepare Allocation Plan | Match equipment to hubs or service areas and send details to operations. This may also include redeployment of equipment for maximum utilisation. | State Coordinator |  |
|  | Finalise Allocation Planning | Review allocation planning of states and determine equipment requirements based on minimum women demand thresholds and regional crop calendars. Take into consideration planned equipment purchase and expansion drive. | National Coordinator/ Operations | 1-2 Days |
|  | Approve Distribution | Approve based on deployment scope. Key Control: National Coordinator must formally sign off on the movement of machinery across states and zones. | National Coordinator | Within 48 Hours |
|  | Schedule Deployment | Plan timing, transport and operators. The deployment of new equipment is done by HQ operations while inter/intra state is done by the CL custodian. Key Control: Use approved means i.e., WIMA designated transport or Select transport providers via an open competition for services exceeding N100,000 to ensure value for money. | CL/Operations | 1-2 Days |
|  | Conduct Pre-Deployment Inspection | Inspect equipment condition before movement | CL / Sub-CL/ Operations | 24 Hours |
|  | Dispatch & ERP Logging | Move equipment to assigned location. Record the "Movement to/from Hub" details in the ERP Logistics module, including driver details and estimated arrival. | Operations | Immediate |
|  | Real-time Tracking | Monitor movement using the ERP "Journey Management" and GPS plug-ins to pinpoint asset location in real-time (where applicable). | Operations/Data Officer | Ongoing |
|  | Hub Arrival & Inspection | Document receipt and condition at destination Key Control: CL must physically inspect equipment upon arrival, verifying serial numbers and condition against delivery notes. Dual sign-off | Receiving CL | Upon Arrival |
|  | Inventory Update | Register the equipment in the local hub asset inventory. Update status to "operational" or "available" in the system core. | CL | Same day |
|  | Secure Storage | Move machinery to dry, well-ventilated and secure storage facilities that meet WIMA safety standards. | Sub-CL | Immediate |
|  | Monitor Utilisation | Track usage against plan | CL / State Coordinator | Ongoing |
|  | Redeploy or Return | Reassign or return equipment post-use via appropriate process and approval (using the steps described above) | State Coordinator / CL |  |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Equipment misuse | Use outside approved deployment | Authorization controls |
| Poor utilization | Equipment idle or mismatched | Demand analysis |
| Loss, transit damage or theft: | Damage or Loss of high-value assets during movement to remote "red-zone" areas. | Mandatory insurance coverage and real-time GPS journey management monitoring. Inspection and handover |
| Conflict | Disputes over allocation | Transparent criteria |
| Weak tracking | Unknown equipment location | Updated registers |
| Conflict of Interest in Logistics | Awarding transport contracts to unvetted relatives or associates. | Strict adherence to open competitive bidding and the Anti-Corruption Policy. |
| Asset Diversion | Equipment being diverted for unauthorized use during delivery. | Use of delivery notes and automated ERP alerts for geofence breaches during transit. |
| Inadequate Site Readiness | Equipment arriving at a hub without secure storage or trained operators. | Mandatory use of the Location Readiness Checklist before dispatch. |

Policy Guidelines

- Equipment allocation and deployment must be demand-driven only.

- Approval must be obtained for inter-hub or inter-state deployment.

- There must be pre- and post-deployment inspections to ascertain the state of the equipment.

- There must be dual sign-off on handover i.e., the deliverer and the receiver.

- The asset register must be updated real-time.

- Any equipment movement without approval is prohibited.

- All allocation decisions must prioritize demand and equity.

- All deployments must be documented.

- Equipment custodianship is assigned and enforced.

- WIMA shall make every effort to contract logistics services from women-owned and minority-owned enterprises.

- All movement of assets, whether between hubs or from manufacturers, must be documented with contracts and delivery notes for audit purposes.

- No equipment shall be transported without verified insurance and adherence to established HSE and safety standards to minimize risks.

- Staff or contractors found engaging in the unauthorized use of equipment during deployment shall face instant dismissal and potential legal action.

- All asset locations and movement logs must be updated in the ERP within 24 hours to ensure national visibility.

- Machinery must only be deployed to hubs that provide dry, well-ventilated storage to prevent rust and deterioration.

- This process shall be reviewed periodically or following asset loss, major deployment issues, or changes in operational strategy approved by WIMA leadership.

EQUIPMENT MAINTENANCE & DOWNTIME MANAGEMENT

Overview of Process

The “Equipment Maintenance & Downtime Management” process is for preventive maintenance, corrective maintenance, breakdown response and downtime management of all WIMA-owned or managed mechanized equipment. It ensures equipment reliability, safety, optimal utilization, cost control and protection of WIMA’s asset value while minimizing service disruption.

Scope

This process applies to all tractors, implements and mechanized equipment managed by WIMA, including equipment including equipment under active service, temporarily idle equipment and equipment undergoing repair or servicing.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Equipment maintenance schedules - Pre- and post-use inspection reports - Breakdown and incident reports - Maintenance contracts and vendor lists | - Preventive maintenance logs - Breakdown and repair reports - Downtime tracking reports - Maintenance cost reports |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Scheduled preventive maintenance timeline/ Reach of engine hour milestone for PPM - Equipment fault, damage, or unexpected field breakdown - Post-deployment or post-service inspection outcome - Safety incident or abnormal equipment performance - Daily pre-operational check failure - Quarterly technology audit | - National Coordinator / Project Lead: Oversight of maintenance strategy and major repairs - State/Zonal Coordinator: Approval of major maintenance and downtime decisions - Community Lead (CL): Ensure routine maintenance and reporting at hub level - Sub-Community Lead (Sub-CL): Daily checks, fault reporting and maintenance logs - MSP (Operator): Proper use, basic checks and immediate fault reporting - MSP (Mechanic): Performing technical repairs and inspections. - CFO: Cost control, vendor coordination and asset records - Field Compliance Manager: Monitor adherence to field equipment handling and maintenance procedures and logs - Operations: Inventory control of spare parts. |
| Tools Required | Key Performance Indicators (KPIs) |
| - Maintenance schedule and checklist - Equipment maintenance register - Fault reporting forms - Approved maintenance vendors list - ERP Maintenance Management Module - Machine & Equipment Tracker (GPS) - Preventive Maintenance (PPM) Planning Tool - Toolkits for repair & parts fabrication | - Equipment uptime percentage/availability rate - Frequency of breakdowns - Average downtime per incident - Maintenance cost per equipment unit - Equipment downtime reduced by % - Number of hubs with adequate spare parts - Maintenance costs within the 30% budget |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Schedule Preventive Maintenance | Establish maintenance calendar per equipment | Operations / CL |  |
|  | Conduct Daily Equipment Checks | Perform routine checks before and after use. Conduct pre-op checks using the ERP checklist (fluids, tyres, safety guards). Key Control: Equipment cannot be activated via token if a "critical failure" is logged. | MSP Operator / Sub-CL | Daily (07:30) |
| 2b | Anomaly Detection | Use GPS and remote monitoring to detect engine overheating or unusual idle patterns that indicate mechanical stress. | Data Officer/Field Compliance | Real-time |
|  | Identify Fault or Wear | Detect abnormal performance or damage | MSP Operator / Sub-CL |  |
|  | Log Fault | Record issue in maintenance register on ERP. The ERP flags it as unavailable for booking | Sub-CL | Immediate |
|  | Manage Downtime | Reallocate equipment or reschedule services | CL | Immediate |
|  | Assess Severity | Determine minor vs major repair need. Determine if the repair is within the capacity of the MSP mechanic. | CL / State Coordinator | Within 24 Hours |
| 6b | Approve Repair | Obtain approval for repair costs where such cannot be handled by the MSP mechanic Key Control: To ensure that the cost is within approved threshold. Also to validate need for repair based on possible previous or recent repair of same equipment | State / National Coordinator |  |
|  | Maintenance Scheduling | Based on status, schedule equipment for maintenance/repair and assign to designated MSP or vendor. Key Control: ERP automatically flags equipment for PPM based on engine hours or calendar dates. CL assigns a mechanic. | CL/ERP | Weekly |
|  | Spare Parts Requisition | Request for parts. Key Control: If parts are needed, check the local hub warehouse. For purchases, initiate competitive sourcing or engagement with designated vendor. | Operations | 24 Hours |
|  | Repair Execution | Perform repairs or servicing at the hub workshop or onsite. Ensure all work complies with OHSS (Safety) standards and PPE is worn. | MSP (Mechanic)/ Vendor | As required |
|  | Technical Validation | Post-repair inspection to ensure functionality. Update the machine status from unavailable status to "Operational" in the ERP. The MSP operator and CL validate this. Key Control: To confirm repair/service was appropriately carried out and equipment/machine is functioning properly | MSP (Operator)/CL | Post-Repair |
|  | Documentation | Update maintenance and downtime logs Key Control: Capture detailed records of the repair, parts used and costs in the Equipment Maintenance Register. | MSP (Mechanic)/ Sub-CL / Operations | Immediate |
|  | Financial Sync | Reconcile maintenance costs against the hub's % allocation for wages and maintenance where applicable. | ERP | Monthly |
|  | Review Maintenance Trends | Analyse patterns and recurring issues | Operations/MEL Coordinator | Quarterly |
|  | Audit & Review | Conduct quarterly audits of maintenance logs to verify compliance with WIMA’s longevity and efficiency goals. Key Control: to ensure adherence to maintenance and equipment longevity procedure. | Internal Auditor/Field Compliance Manager | Quarterly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Frequent breakdowns | Poor maintenance discipline | Preventive schedules |
| Safety incidents | Equipment failure during use | Daily checks |
| Asset Degradation (Rust/Deterioration) | Equipment stored in poor conditions. Deferred maintenance | Mandate storage in dry, well-ventilated areas as per the Logistics Policy. Maintenance monitoring |
| Excessive downtime | Delayed repairs | Vendor SLAs |
| High repair costs | Poor cost control | Approval thresholds |
| / Safety Hazards during Repair | Injuries to maintenance personnel. | Strict adherence to the OHSS Policy; mandatory use of PPE and fire extinguishers in workshops. |
| Unauthorised Repairs | Use of unvetted mechanics or sub-standard parts. | Only WIMA-certified mechanics (including trained MSP/youth) may perform repairs; parts must be sourced from approved vendors. |
| Maintenance Budget Overruns | Repair costs exceeding the 30% revenue share. | Implement preventive maintenance plans to avoid costly emergency breakdowns |
| Theft of Spares | Unrecorded removal of high-value parts from the hub. | Maintain an accurate inventory system with regular audits and secure storage facilities. |

Policy Guidelines

- It is mandatory that all equipment and machines have preventive maintenance schedules.

- All faults must be reported and logged immediately.

- Where repairs or maintenance shall require payment, it shall be approved based on the thresholds for repair costs

- Only approved vendors can be engaged for repairs and maintenance.

- All equipment and machines must be inspected and verified to be functioning and operations before returning equipment back to service in the field.

- Equipment must not be used if deemed unsafe.

- Unauthorized repairs are prohibited.

- Preventive maintenance is mandatory. Non-adherence and deference shall be sanctionable.

- All hubs must maintain a revolving fund (from the % repayment/% maintenance split) to ensure long-term recapitalisation and repair capacity.

- No staff member or MSP shall operate or attempt to repair machinery while under the influence of alcohol or illicit drugs; violations shall result in instant dismissal.

- Where possible, WIMA shall prioritise training local women/youth in repair and parts fabrication to build community-based technical resilience.

- Procurement for maintenance services must follow Anti-Corruption guidelines; no facilitation payments shall be made to speed up repairs.

- All maintenance logs must be registered on the Asset Register and synced with the ERP within 24 hours.

- Hubs must ensure environmentally sound waste management (e.g., proper disposal of used oil and batteries) during maintenance activities.

ASSET & INVENTORY CONTROL

Overview of Process

The “Asset & Inventory Control” process establishes the framework for tracking, securing and managing WIMA’s high-value mechanised and technical assets. It describes the activities for identifying, recording, safeguarding, tracking, reconciling and reporting all WIMA assets and inventories. It ensures asset accountability, prevents loss and misuse, supports accurate financial reporting and enables efficient operational planning across national, state/zonal and hub levels.

Scope

This process applies to all WIMA-owned, leased, or donated assets and inventories, including mechanized equipment, tools, spare parts, consumables, ICT equipment and other physical assets held at national offices, state/zonal offices and hubs.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Asset acquisition documents, delivery notes and contracts - Manufacturer details and specifications - Equipment serial numbers and ID tags - Insurance documents and warranties - Inventory purchase records - Asset and inventory registers - Transfer, deployment and disposal approvals | - Updated asset and inventory registers - Asset verification and reconciliation reports - Inventory stock status reports - Asset loss, damage, or disposal reports |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Acquisition or receipt of an asset or inventory item - Transfer, deployment, or redeployment of assets - Seasonal equipment redistribution across hubs - Periodic stock counts and asset verification - Asset loss, damage, or disposal - Quarterly machinery audit cycle | - National Coordinator / Project Lead: Oversight of asset governance and policy enforcement - CFO: Asset register management and reconciliation - State/Zonal Coordinator: Regional asset oversight and verification - Community Lead (CL): Hub-level custody and inventory control - Sub-Community Lead (Sub-CL): Day-to-day inventory tracking and updates - Operations: Central inventory control and audits |
| Tools Required | Key Performance Indicators (KPIs) |
| - Centralised Asset Repository on ERP - Asset tagging or labelling tools (Asset Tags and RFID/Barcode Scanners) - Stock cards and inventory count sheets - Reconciliation and verification checklists - ERP Warehouse & Admin Modules - GPS Machine and Equipment Tracker | - Asset register/inventory accuracy rate - Inventory variance rate - Frequency of asset verification exercises - Number of asset loss or damage incidents - % Reduction in asset loss/theft. - Hub Audit Score (≥85%) |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
| NATIONAL/CENTRAL |  |  |  |  |
|  | Receive Asset/ Inventory | Verify delivery against documents. Key Control: Verify all incoming assets against delivery notes to ensure completeness and accuracy of delivery | CL/Operations | Upon Receipt |
|  | Physical Tagging | Assign unique identification number. Apply weather-resistant asset tags to all machinery and hardware. Ensure serial numbers are captured in the inventory register. Where such asset requires registration i.e., tractor, vehicle, etc. this is also done and the registration data captured. Key Control: For new items, Operations assigns unique identification numbers. Visible tag for ownership distinction | Operations | 48 Hours |
|  | Master Register Update | Log asset particulars, including type, engine capacity and insurance details, into the IT Asset Register. | Operations |  |
|  | Secure Storage & Conditioning | Move assets to designated storage areas. Key Control: Machinery must be kept in dry, well-ventilated areas to prevent rust and deterioration. | Operations | Immediate |
|  | GPS Integration | Activate the Machine and Equipment Tracker to allow real-time monitoring of asset performance and location from any device. Key Control: For security and revenue assurance purposes. | Operations | 24 Hours |
|  | Issuance & Movement | Record any transfer of assets from central, between hubs or to the field in the module designated for Logistics & Deployment. This is done according to the approve deployment schedule. Key Control: Approval required for deployment of assets to hub. | Operations | During Movement |
|  | Inventory Audit | Conduct a quarterly asset audit to ensure all items match the ERP records. Perform physical verification. Compare physical count to registers. Investigate shortages or overages Key Control: To validate the state of all the assets in WIMA | Internal Auditor / Field Compliance Officer | Quarterly |
|  | Utilisation and management | Deploy asset for field services. Assess the functional state of assets (Operational vs. Grounded) and update maintenance schedules accordingly. | CL / MSP | Ongoing |
|  | Asset Valuation & Review | Conduct regular valuation of asset for financial recording and determine decision. This will be dependent on the reports from inventory audit, operational status and depreciation. | CFO | Annually |
|  | Decommissioning, Disposal or Write-off | Process the removal of obsolete or unrepairable assets. For IT assets, ensure sensitive data on technical hardware is irrecoverably deleted. Finance handles approved disposals. Key Control: Approval is required for asset decommission and ultimate disposal. It must follow due process | Field Compliance Officer/CFO | As required |
| STATE & HUB LEVEL |  |  |  |  |
|  | Receive Asset/ Inventory | Verify delivery against documents. Key Control: Verify all incoming assets against delivery notes to ensure completeness and accuracy of delivery | CL / Sub-CL | Upon Receipt |
|  | Store Inventory | Store items securely | Sub-CL | Immediate |
|  | Register Asset/ Inventory | Record item in hub asset or inventory register. Make status as available for booking. Key Control: For new items, Operations assigns unique identification numbers and register them in the appropriate module. | CL / Sub-CL | Within 24 Hours |
|  | Assign Operator | Allocate custody/operator responsibility. It is expected that all the operators are trained on how to operate the machinery. | CL / Sub-CL | Ongoing |
|  | Issue Inventory | Release inventory for approved use | CL |  |
|  | Update Records | Update registers after movement or use | CL / Sub-CL |  |
|  | Conduct Periodic Verification | Perform physical verification and compare physical count to registers | State Coordinator/CL | Monthly/ Quarterly |
|  | Report & Escalate | Report significant issues | State Coordinator/CL | Immediate |
|  | Investigate Variances | Investigate asset verification issues and present report to National Coordinator for decision making. | Field Compliance/Operations/ State Coordinator | Immediate |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Asset loss | Theft or misplacement | Custodian assignment and tagging |
| Inventory shrinkage | Unrecorded usage | Issue controls and stock counts |
| Inaccurate records/ Inventory Inaccuracy | Poor register updates. Discrepancies between the ERP records and physical stock at hubs. | Same-day updates. Conduct 100% quarterly audits and require monthly data submissions from hub managers. |
| Asset Theft or Diversion | High-value equipment being moved without authorisation. | Mandatory GPS tracking and geofencing; periodic field audits and use of system-generated activation tokens |
| Environmental Degradation | Machinery rusting due to poor storage conditions. | Strict adherence to the Logistics Policy regarding dry, well-ventilated storage facilities. |
| Unauthorized disposal | Informal write-offs | Approval controls |
| Weak oversight | Lack of verification | Periodic audits |

Policy Guidelines

- It is mandatory to register and tag all assets.

- All assets must be assigned a custodian and it must be adequately acknowledged.

- All assets must be kept in a secure storage location with controlled access.

- There must be scheduled periodic independent verification of asset location and status. It must be conducted at least once a year.

- There must be a formal authorisation and documentation for all asset disposal or write-off.

- All inventory issues require appropriate authorization.

- Asset decommissioning, disposal and write-off shall follow the appropriate process and must be approved by the President/Board of Trustees.

- WIMA remains the registered owner of all purchased software, hardware and machinery; personal use of WIMA assets is strictly prohibited.

- All asset movements and maintenance logs must be synced with the ERP within 24 hours to ensure transparency.

- Staff found falsifying inventory records or turning a blind eye to asset misuse shall face termination under the Anti-Corruption Policy.

- When procuring new inventory, WIMA shall prioritise machinery with ergonomic safety features suitable for women operators.

- No high-value asset shall be deployed or transported without verified transit or operational insurance coverage.

EQUIPMENT INCIDENT & DAMAGE REPORTING

Overview of Process

The “Equipment Incident & Damage Reporting” process establishes the steps for reporting, documenting, investigating and resolving incidents, accidents, damage, loss, or misuse involving WIMA-owned or managed mechanized equipment. It ensures prompt response, accountability, asset protection, safety compliance, insurance readiness and continuous improvement in equipment management.

Scope

This process applies to all incidents involving tractors, implements and mechanized equipment at WIMA hubs or during deployment, transportation, operation, maintenance, or storage, including accidents, breakdown-related damage, theft, fire, misuse and safety-related incidents.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Incident notification or verbal report - Equipment inspection and maintenance records - Photographic or video evidence - Witness statements (where applicable) - GPS movement/idle data - Daily Equipment Inspection Report - Operator/MSP field logs | - Incident report - Damage assessment and cost estimate - Corrective action and resolution report - Insurance or recovery claim documentation - Grounded asset status update |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Occurrence or discovery of an equipment-related incident or damage - Safety incident involving operators or third parties - Suspected misuse, loss, vandalism or theft of equipment | - Operator / MSP: Immediate incident reporting and site safety - Sub-Community Lead (Sub-CL): Initial documentation and notification - Community Lead (CL): Verification, escalation and preliminary assessment - State/Zonal Coordinator: Oversight, investigation approval and escalation - CFO: Asset, cost and insurance documentation - Field Compliance Manager: Oversight and investigation. - National Coordinator / Project Lead: Major incident oversight and final decisions |
| Tools Required | Key Performance Indicators (KPIs) |
| - Incident reporting forms /WIMA ERP (Incident & Security Module) - Equipment inspection checklist - Incident register and tracking log - Camera or mobile device for evidence capture - Register of Injuries, Incidents and Near Misses - GPS Machine Tracker - Emergency Response Protocols | - Incident reporting timeliness /Time to report (Target: <1 hour from event). - Number of repeated incidents per equipment - Average incident resolution time - Cost recovered vs cost incurred - % of incidents with completed investigations. - Avg. repair turnaround time. - Reduction in unrecorded damage (%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Secure Site & Equipment | Stop operations, ensure safety, prevent further damage. In the event of physical harm, prioritise medical attention if injuries occurred. Administer first aid or call for an ambulance. Ensure the site is safe to prevent further damage | MSP (Operator) | Immediate |
|  | Immediate Notification | Report incident within stipulated time. Report the incident immediately to the CL and/or Safeguarding Focal Person. Do not confront third parties in volatile areas. Key control: Appropriate parties must be notified of all incidents. | MSP / Sub-CL | < 30 Mins |
|  | Initial Documentation | Record basic details and capture evidence. Enter details into the ERP Incident Module. Include: Name, date/time, exact location, cause, part of the body/machine affected and witness names. Key control: All incidents must be documented. | Sub-CL/ CL | < 2 Hours |
|  | Verify Incident and Asset Status | Confirm facts and severity. Update the equipment status to "grounded or unavailable" in the Booking System to prevent further use and stop new bookings. | CL | Immediate |
|  | Escalate Incident | Escalate based on severity and value. If the incident involves security threats or theft, use the ERP to alert assigned security vendors and the National Coordinator. | CL / State Coordinator | Immediate |
|  | Assess Damage | Conduct technical and cost assessment. Hub mechanic inspects the damage. Determine if the cause was "Wear and Tear," "Negligence," or "External Force". | MSP (mechanic) / Vendor | 24 Hours |
|  | Determine Responsibility | Identify cause and accountability | State / National Coordinator | 24 Hours |
|  | Approve Corrective Action | Approve repair, recovery, or disciplinary action. Key control: All corrective actions must be approved to ensure that the best course of action is taken. | State / National Coordinator |  |
|  | Implement Resolution | Carry out repairs or recovery actions | Operations / Vendor | Immediate |
| 9b | Insurance Trigger | If damage exceeds the deductible, compile the incident report, delivery notes and photos to initiate an insurance claim. | CFO | 48 Hours |
| 9c | Investigation & Review | Conduct a root-cause analysis for serious incidents (accidents/SEAH). Document findings in a formal report. | Field Compliance Manager | 5 Days |
|  | Update Records | Update asset, maintenance and incident registers | Operations / Sub-CL | Immediate |
|  | Close Incident | Document resolution and lessons learned | CL | Post Repair |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Delayed reporting | Incidents concealed or forgotten | Reporting timelines |
| Evidence loss | Poor documentation | Mandatory evidence capture |
| Volatile "Red-Zone" Conflicts | Incidents occurring in areas where reporting might endanger staff. | Use Emergency Community Response guidelines; engage local traditional leaders for mediation. |
| Unclear accountability | Disputes over responsibility | Investigation protocol |
| Repeat incidents | Root causes not addressed | Lessons learned review |
| Financial loss | Unrecovered repair costs | Insurance and recovery processes |
| Concealment of Damage | Operators failing to report minor damage to avoid sanctions. | Mandatory Daily Pre-Op and Post-Op inspections; cross-reference GPS idle data to detect mechanical stress. |
| Fraudulent Claims | Reporting existing damage as a new incident to secure insurance funds. | Maintain a detailed Asset Register with time-stamped photos of all equipment at hub arrival. |

Policy Guidelines

- It is mandatory to report all incidents and it must be done in a timely manner i.e., immediately after occurrence.

- All possible evidence must be captured and documented including images and eyewitness accounts where applicable.

- There must be a separation between investigation and resolution roles.

- A formal incident closure process must be carried out to ensure resolution.

- There shall be no repair without documented approval.

- Safety incidents shall take priority over operations.

- Disciplinary actions shall apply where negligence is confirmed.

- Operators found to have caused damage while under the influence of alcohol or illicit drugs shall face instant dismissal.

- All "near misses" (events that could have caused damage or injury) must be logged to improve future safety protocols.

- If the incident involves SEAH (Sexual Abuse/Harassment), the identity of the survivor and accused must be protected; reports shall only be shared on a need-to-know basis.

- No hub shall operate without functional fire extinguishers, first-aid kits and mandatory PPE in use at all times.

- Falsifying an incident report or witness statement shall result in disciplinary action under the Anti-Corruption and Bribery Policy.

- All incident records involving personal data must be stored securely, adhering to the Nigeria Data Protection Regulation.

HUB REGISTER & RECORD-KEEPING

Overview of Process

The “Hub Register & Record-Keeping” process establishes the framework for capturing and maintaining all operational, financial and member-related data at the hub level.

Scope

This process applies to all physical and digital records maintained at WIMA hubs, including records related to assets, services, revenues, expenses, personnel, members, farmers and stakeholders at community, LGA, state/zonal and national levels.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved WIMA register templates - Record/information input portal on ERP - Operational transactions and activities - Asset movements and service records - Financial transactions and approvals - Equipment Serial Numbers & Specs - Service Activation Tokens | - Archiving & Disposal Schedule - Master hub register/record (digital/physical) - Complete and up-to-date hub registers/records - Asset & Equipment - Equipment Usage Log - Booking & Service Fulfilment - Revenue Collection & Receipt - Expense & Petty Cash - Operator & MSP - Member/Farmer - Incident & Damage - Maintenance & Downtime - Complaints & Feedback - Attendance & Duty Roster - Verified data for monitoring and evaluation - M&E Performance Dashboards/Periodic hub performance and compliance reports - Audit-ready documentation |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Establishment and launch of a new hub - Commencement of daily hub operations - Requirement for monitoring, reporting, audit, or compliance review - Onboarding of a new member - Deployment or maintenance of an asset - Occurrence of a service or incident | - National Coordinator / Project Lead: Oversight of record-keeping standards and compliance - State/Zonal Coordinator: Oversight and validation of state-wide data. Supervision and periodic review of hub registers - Community Lead (CL): Overall daily record integrity and coordination. Primary custodian of hub registers and records - Sub-Community Lead/MSP: Day-to-day data capture and updates - CFO: Financial records oversight and reconciliation - MEL Coordinator: Data quality assurance and reporting integration |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA ERP (Enrolment & Admin Modules) - Secure Storage Cabinets (for physical files) - Data capture devices (digital tablets/ smartphones) or logbooks - Standard WIMA register templates (physical and/or digital) - Secure storage (lockable cabinets, password-protected systems) - Register review and audit checklists | - Percentage of mandatory registers maintained - % Hubs submitting data monthly (≥90%). - Timeliness of record updates - Number of data inconsistencies identified - Data accuracy/Integrity score. - Audit and compliance findings related to records - % Records with clear audit trails (100%). - Time to sync field data to ERP (Target: <24 hours) |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Establish Registers | Set up all mandatory registers at hub launch. For digital register this is done by the ERP once the Hub has been created on the system. | CL/Field Compliance Manager/ MEL Coordinator | Pre-launch of hub |
|  | Assign Custody/ Responsibility | Assign register custodians and backups Where such as physical. Otherwise, educate the data capture person(s) on how to capture the data for the respective form on the ERP | CL |  |
|  | Daily Data Capture | Record all transactions and activities daily. Upload all manual field logs into the digital ERP platform. Key Control: Ensure data quality and completeness before submission. | Sub-CL / MSP | Immediate |
|  | Review & Verification | Review entries for completeness and accuracy Key control: To ensure that the data has indeed been captured and capture accurately | CL/ MEL Coordinator | Within 24 Hours |
|  | Financial Reconciliation | Match financial records with cash and receipts | ERP (automatic) | Real-time |
|  | Secure Storage | Store records securely (for physical records) Key Control: All physical records must be stored in an access-controlled cabinet. All partners are expected to secure all data capture devices appropriately with passwords to prevent breach. | CL | Daily |
|  | Periodic Reporting | Extract data for reports. The ERP automatically uses the datasets to develop appropriate reports | MEL Coordinator / CL/ERP (automatic) | Daily/ Monthly/ Quarterly |
|  | Supervisory Review | Review records monthly via the BI dashboard to detect anomalies or revenue leakage. Provide feedback where applicable Key Control: Supervisory oversight | State / National Coordinator | Weekly/ Monthly/ Quarterly |
|  | Correct Errors | Rectify discrepancies promptly | CL / Sub-CL | Immediate |
|  | Archiving Records & Disposal | Store physical records in dry, secure areas. Process old data for archiving or disposal of physical records as per the Data Policy. | Field Compliance / CL | Annual Review |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Missing records | Incomplete documentation | Mandatory registers |
| Data manipulation | Altered or falsified records | Supervisory reviews |
| Loss of records | Physical or digital loss. Destruction of paper registers due to fire, floods, or poor storage. | Secure storage & backups. Mandate storage in dry, well-ventilated areas and prioritize immediate digital entry into the cloud-based ERP. |
| Inconsistent data | Poor reporting quality | Standard templates |
| Audit failure | Non-compliance | Periodic audits |
| Data Inaccuracy | Misreporting of hectares or fuel usage leading to financial loss. | Cross-reference manual logs with GPS tracking and token activation data in the ERP. |
| Data Breach | Unauthorized access to sensitive member or financial data. | Implement user rights/privileges and strictly follow the Nigeria Data Protection Regulation. |
| Non-Compliance by Partners | Self-funded partners failing to maintain registers. | Tie hub operational status to successful compliance audits and dashboard submission rates. |

Policy Guidelines

- All data must be capture via the approved template or platform.

- All transactions recording must be same-day recording of transactions.

- There must be separation of duties in terms of data capture and review.

- All data shall be in a secure storage with appropriate access restriction.

- All data captured shall be supervised accordingly with periodic audit reviews.

- All hubs must maintain mandatory registers/records.

- Registers must be updated daily

- Unauthorized alteration of records is prohibited.

- Every register/record or data capture must have a designated "Responsible Person" to ensure ongoing policy compliance.

- All records must be retained in line with WIMA’s data policy.

- 100% of strategic initiatives must be tracked with KPIs. The data must be accurate and submitted on time.

- Personal data must be shared only on a need-to-know basis.

- All transaction instruments and registers must possess a clear, unalterable audit trail. No manual alterations shall be permitted.

- Where necessary, templates in local-language shall be used for initial data gathering in rural communities.

- Data shall be kept only as long as necessary for its specific purpose, followed by secure archiving or deletion.

- All deletion or disposal of records must be authorised and signed off.

STATE/ZONAL REGISTER (RECORD) OVERSIGHT

Overview of Process

The “State/Zonal Register Oversight” process defines how State and Zonal Coordinators provide oversight, verification, consolidation and quality assurance of all WIMA hub registers and records within their jurisdiction.

Scope

This process applies to the supervision, review, consolidation and reporting of all hub-level registers maintained within a state or zone, including operational, financial, asset, service delivery and compliance-related records.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Hub-level registers (Digital/Physical) - Periodic hub reports - Review and audit checklists - Exception and variance reports - ERP Hub Data Submissions - GPS & Token Usage Logs - Financial Remittance Records | - Consolidated state/zonal register summaries - Data quality and compliance reports - Exception and escalation logs - Inputs into national dashboards and reports - Monthly State Performance Summary - Zonal Data Integrity Audit - Validated Master Member List - KPI Variance Analysis Report |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Commencement of hub operations within a state or zone - Periodic reporting cycles (weekly, monthly, quarterly) - Detection of data inconsistencies, control breaches, or audit requirements | - National Coordinator / Project Lead: Strategic oversight and escalation resolution - Zonal Coordinator: Manages span of control across states. - State Coordinator: Oversight of state-level data quality. Primary owner of register oversight and consolidation - Community Leads (CLs): Submission and clarification of hub registers - CFO: Financial and asset data validation - MEL Coordinator: Designing indicators, data quality assurance and reporting integration |
| Tools Required | Key Performance Indicators (KPIs) |
| - Standard hub register templates - Register review and audit checklists - Consolidation and reporting tools/WIMA ERP (Executive Dashboard) - Issue tracking and escalation logs - GPS Machine and Equipment Tracker - Mobile Payment Verification API | - Timeliness of hub register submissions - Number of data discrepancies identified - Resolution rate of register-related issues - Compliance rate of hubs with register standards - % Hubs submitting data monthly - % Records with a clear audit trail (100%). - Data sync turnaround time (Target: hours). - % Decision-making informed by M&E data |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Communicate Register Standards | Share register requirements and timelines with hubs | State/Zonal Coordinator | Periodically |
|  | Hub Data Submission | Upload all local registers (member, service and maintenance) to the ERP. | CL / Sub-CL/ MSP | Daily/ Weekly |
|  | Initial Completeness Check | Confirm all mandatory registers/records are submitted. Key Control: State Coordinator reviews records for completeness. Verify that registered members match token generation and bank alerts as well as other transaction alignment. | State/Zonal Coordinator | Daily/ Weekly |
|  | Detailed Review & Verification | Review accuracy, consistency and supporting evidence. Flag variances and send for investigation. Key Control: Revenue assurance | CFO / MEL Coordinator/ Field Compliance Manager | Within 48 Hours |
|  | Identify Exceptions | Flag discrepancies, variances, or control breaches. Investigate any variance between GPS-tracked acreage and manual logs. Flag "unauthorised movement" for immediate resolution. Key Control: Revenue assurance | State/Zonal Coordinator | Immediate |
|  | Engage Hubs for Clarification | Request explanations or corrections. Escalate unresolved or serious issues to Zonal/National level | State/Zonal Coordinator | Immediate |
|  | Validate Corrections | Confirm issues are resolved | State Coordinator / CFO / MEL Coordinator/ | Within 24 Hours |
|  | Consolidate & Submit Report | Aggregate hub data at state/zonal level via ERP. Submit consolidated reports to national level. State consolidates and submits to Zonal. Zonal consolidates and submits to National Coordinator | State/Zonal Coordinator | Monthly/ Quarterly |
|  | Executive Review | National Coordinator and President review the Executive Dashboard to identify underperforming regions or high-risk hubs. | National Coordinator | Monthly |
|  | Corrective Action | Issue improvement plans for hubs with data integrity or low service utilisation rates. | Zonal Coordinator | Post-review |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Late submissions | Delayed reporting | Submission calendar |
| Inaccurate data | Poor decision-making | Verification checks |
| Data Falsification | Partners or Hub Managers inflating numbers to meet KPIs. | Use automated equipment logs (GPS) and token-driven service bookings to create an unalterable audit trail. |
| Concealed issues | Reputational or financial risk | Independent review |
| Weak enforcement | Repeated non-compliance | Escalation protocols |
| Data overload | Ineffective analysis | Standard summaries |
| Overwhelmed Span of Control | National Coordinator unable to manage data from 36 states. | Activation of the Zonal layer reporting to the National level. |
| Technology Gaps | State Coordinators lacking the skills to use the BI Toolkit. | Mandatory Manage-and-Hub-Manager training and provision of necessary digital tools. |
| Data Breach | Exposure of sensitive member information during state-to-national transmission. | Strict adherence to the Nigeria Data Protection Regulation and use of secure, cloud-based ERP modules. |

Policy Guidelines

- All hubs must submit registers/records as scheduled. All records and transactions shall be submitted on the same day.

- The ERP shall provide avenues to review reports real-time.

- There shall be separation of duties for hub data capture and state review.

- Where there are unresolved gaps and material issues must be escalated promptly. A formal escalation and issue tracking must be carried out.

- All feedback must be documented and are expected to form part of performance review discussions.

- State/Zonal Coordinators shall be accountable for data quality.

- Consolidated records form the basis for national reporting.

- State Coordinator shall at least once in a month ensure that all hubs within the state have accurate and complete records. This shall be use for hub audit and compliance status verifiable by the Internal Auditor or Field Compliance Manager.

- Any hub providing services without a system-generated token (where applicable) or recorded service shall face immediate "Unavailable" status in the ERP.

- All registers/record capturing forms must track WIMA key data such as quota of female and youth-led participation.

- Every state register/record must have a designated "Responsible Person" who is accountable for WIMA ongoing compliance.

DATA COLLECTION, VALIDATION & SUBMISSION

Overview of Process

The “Data Collection, Validation & Submission” process defines the end-to-end workflow for collecting, validating, approving and submitting operational, financial and performance data across WIMA’s hubs, state/zonal structures and national office. It ensures data accuracy, completeness, timeliness, integrity and consistency for decision-making, monitoring, reporting, donor compliance and audit purposes.

Scope

This process applies to all data generated and reported by WIMA, including operational data, service delivery data, financial data, asset data, GEDSI-related data and monitoring and evaluation (M&E) indicators at hub, state/zonal and national levels.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Hub registers and source documents - Approved indicator definitions and data collection tools - Reporting templates and submission schedules - Member Registration Forms (Digital/Manual) - GPS & GIS Machine Usage Data - Service Activation Tokens - Yield/Impact surveys and field logs | - Validated data submissions - Consolidated state/zonal datasets - National performance and donor reports - Data quality and exception reports - Validated Master Member List - Monthly State Performance Dashboards - Data Integrity Audit Reports - KPI Variance Analysis Report |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Routine data reporting cycles (daily, weekly, monthly, quarterly) - Project, donor or partner reporting requirements - Ad-hoc data requests from management, donors, or auditors - New member onboarding or service delivery - End of daily/weekly hub operational cycle - Monthly reporting deadline | - Community Lead (CL): Primary data capture and first-level validation - Sub-Community Lead: Daily data recording and submission support - State/Zonal Coordinator: Secondary validation and consolidation - MEL Coordinator: Data quality assurance, indicator management, verification and reporting - CFO: Financial and asset data validation - National Coordinator / Project Lead: Oversight, approval and escalation resolution |
| Tools Required | Key Performance Indicators (KPIs) |
| - Standard data collection tools and templates - Indicator reference sheets and data dictionaries - Validation and review checklists - WIMA ERP (M&E and Data Capture Module) - Power BI Business Intelligence Toolkit - GPS Machine and Equipment Tracker | - Timeliness of data submissions/Data sync turnaround time (<24 hours). - Percentage of data submissions passing validation checks - Number of data discrepancies identified - Data rework and correction rates - % Hubs submitting data monthly (≥90%). - % Decisions informed by M&E data (100%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Capture Data at Source | Record data from daily operations into registers. e.g., Record member info, machine engine hours, fuel consumption during service, etc. Upload manual field logs and registration data into the ERP Cloud. Use smartphones/tablets to sync data in real-time or within 24 hours. Key Control: Data capture must be same day recording/capture. | Sub-CL / CL/ MSP | Immediate |
|  | Automated Verification and Aggregation | Conduct verification and syncing where applicable. Aggregate hub data at state/zonal level The data is synced with the key parameters i.e., hub data, member data, equipment data, service, payment, etc Key Control: The ERP cross-references manual acreage reports against GPS/GIS data to detect "side jobs" or unauthorised movement. Flag exceptions in reconciliation module | System (Auto) | Real-time |
|  | First-Level Validation | Check entries for completeness and clarity. Verify accuracy against source records where applicable. Key Control: Review consistency and trends. | CL | Daily |
|  | Secondary Validation | Review hubs/states submissions for completeness and accuracy. Investigate any variance between engine hours and revenue collected. Key Control: Review consistency and trends. | State/Zonal Coordinator | Weekly |
|  | Flag Exceptions | Identify gaps, inconsistencies, or anomalies | State/Zonal | Immediate |
|  | Correct & Resubmit | Address issues and resubmit corrected data Key Control: Amendments require appropriate authorisation and support from backend to effect. | CL / Sub-CL | Within 24 Hours |
|  | MEL Analysis | Review KPIs to measure productivity, membership growth, gender inclusion and other indicators | MEL Coordinator | Monthly (Day 1-3) |
|  | National QA Review | Conduct final quality assurance on validated datasets | National Coordinator | Monthly (Day 4-5) |
|  | Final Executive Submission | Submit the validated data to the President and BOT for strategic review and adaptive planning. | National Coordinator | Monthly (Day 7) |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Inaccurate data, Falsification or Data manipulation | Errors or misreporting, Intentional misstatement, misreporting to meet KPIs or hide revenue leakage | Multi-level validation, independent review. Use automated equipment logs (GPS) and token-driven bookings to create an unalterable audit trail. |
| Late submissions | Missed reporting deadlines | Submission calendar |
| Data Breach/Unauthorised Access | Exposure of sensitive member biometrics or financial details. | Strict adherence to the Nigeria Data Protection Regulation and role-based user rights. |
| Digital Literacy Gaps | Field staff unable to use digital capture tools effectively | Implement a stepwise training approach and provide blended (offline/online) onboarding support. |
| Infrastructure Failure | Loss of data due to limited internet access or device malfunction. | Enable offline data capture and periodic syncing; maintain cloud-based backups for disaster recovery |
| Inconsistent indicators | Misinterpretation | Data dictionary |
| Data loss | Loss of records | Secure storage & backups |

Policy Guidelines

- Data submissions must follow approved organisational timelines. All submissions must be defined with clear calendar timelines.

- There must be separation of duties for data capture, validation and approval on the ERP.

- Standardized templates and indicator definitions must be clear to all involved with data capture.

- All exceptions must be adequately logged and corrections tracked.

- All data must originate from approved registers or mapped from the appropriate data field on the ERP.

- Data must be validated before submission. Once submitted it is assumed that the data is validated and accurate.

- Unauthorized data alteration is prohibited.

- No manual alterations to digital records are permitted. All changes must possess a clear system audit trail.

- 100% of strategic initiatives must be tracked with KPIs. Submissions must be accurate and on time.

- All personal data must be processed lawfully and held no longer than necessary, as per the WIMA Data Protection Policy.

- States failing to meet the 90% hub submission rate monthly shall be flagged for immediate corrective action.

- All data collection tools must explicitly track the 80% female and 20% youth participation targets.

- Every register/reporting form must have a designated "Responsible Person" accountable for ongoing data policy compliance.

DIGITAL SYSTEM USAGE & DATA GOVERNANCE

Overview of Process

The “Digital System Usage & Data Governance” process defines the standards, rules and procedures governing the use of digital systems and the management, protection and governance of data across WIMA.

Scope

This process applies to all digital systems, platforms, devices and databases used by WIMA, including data collection tools, financial systems, asset management systems, communication platforms, cloud storage and any third-party digital solutions adopted at hub, state/zonal, or national levels.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved digital systems and tools - Data governance policies and classifications - User access requests and approvals - Data collection and reporting requirements - Nigeria Data Protection Regulation - Member & Farm Baseline Data - Approved Hardware/Software Lists | - Approved system access records - Secure and validated digital datasets - System usage and access logs - Data governance and compliance reports - Quarterly Technology Audit Report - IT Asset Register (Software/Hardware) - Real-time Performance Dashboards - Data Breach/Incident Logs |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Deployment or use of any digital system or platform - Collection, storage, processing, or sharing of WIMA data - Introduction of new digital tools or system upgrades - Data access requests or data-sharing requirements - Onboarding of new staff or partner | - National Coordinator / Project Lead: Oversight of digital governance and compliance - CFO: Administration of financial systems - MEL Coordinator: Governance of performance and reporting data - Data Officer: Data analytics. - State/Zonal Coordinator: Enforcement of digital usage standards at field level - Community Lead (CL): Responsible use of digital tools and data capture - System Administrator / IT Consultant: User access management, system maintenance and security |
| Tools Required | Key Performance Indicators (KPIs) |
| - Approved digital platforms and applications - User access and role management tools - Data backup and recovery tools - Security and audit logging tools - WIMA ERP (Cloud-based Modules) - GPS & Machine Tracking Plug-ins - Antivirus & Firewall Software - Power BI Business Intelligence Toolkit | - Percentage of users trained on digital systems - System uptime and availability - Number of data breaches or incidents (zero) - Compliance with data governance standards - % Hubs on digital system - Data sync turnaround time (Target: <24 hours). - % Decision-making informed by M&E data (Target: 100%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Approve Digital Systems | Approve systems for organisational use Key Control: Approval is based on clear business case | President/Board of Trustees | As required |
|  | System Installation | Installation of system according to specification. This involves engagement of proposed users and other engagement to finalise functionality and acceptance. Key Control: Only software approved and registered by WIMA can be installed. Unauthorised duplicating or loading of "home software" is strictly prohibited. All modifications must be signed off appropriately. | IT Consultant | Based on timeline |
|  | Grant User Access | Assign role-based system access Key Control: Assign role-based privileges (e.g., National Coord., MEL, CL, etc) to ensure data integrity and prevent unauthorised access. | IT Consultant/ Operations | Onboard/ Exit |
|  | Train Users | Train users on system use and data rules | Ops / MEL Coordinator | Onboard/As required |
|  | Capture Data Digitally | Capture member, field and service information. Key Control: Data capture must be same day recording/capture. | CL / Sub-CL/MSP | Immediate |
|  | Store & Secure Data | Store data in approved repositories | System | Real-time |
|  | Monitor System Usage | Track access, changes and activity | IT Consultant / Field Compliance Manager | Daily |
|  | Validate Digital Data | Conduct quality checks Key Control: Review consistency and trends. | State/Zonal MEL Coordinator / CFO | Periodical |
|  | Share Data | Share data based on approvals Key Control: All WIMA data are confidential and only shared based on approval i.e., from the president which may have been given at the signing of donor contracts or when reviewed for completeness and accuracy. | National Coordinator | As required |
|  | Backup & Recovery | Perform routine backups. Key Control: All systems must have automatic cloud backup features for WIMA data. | IT Consultant | Daily/ weekly |
|  | Archiving & Removal | Move old data to secure archives. Key Control: Approval is obtained for the period to be archived or removed. When deleting personal data, ensure it is irrecoverable to protect privacy. | IT Consultant | Annual Review |
|  | Incident Management | Respond to data or system incidents | IT Consultant | When it arises |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Data breach/ Phishing | Unauthorized access, Loss of funds or sensitive data. | Implement mandatory cyber-security guidance, hardware tokens for finance and up-to-date firewall/antivirus software. |
| Data loss | System failure or deletion | Regular backups |
| Shadow IT/Unauthorised Software | Use of vulnerable third-party apps. | Zero-tolerance policy for unapproved software; all installations must be performed solely by the IT Officer. |
| Inconsistent data | Poor data quality | Validation checks |
| System misuse | Unapproved use | User training & monitoring |
| Compliance failure | Donor or legal breaches | Governance enforcement |
| Data Falsification | Hubs inflating numbers to meet KPIs. | Use automated equipment logs (GPS) and token-driven activation to create an unalterable audit trail |
| Infrastructure Failure | Loss of data in remote zones with poor connectivity. | Enable offline data capture and periodic syncing once connectivity is restored; maintain cloud-based backups. |

Policy Guidelines

- Only approved systems and tools can be deployed for use in WIMA.

- All systems shall have role-based access and authentication.

- Each system must have a clearly documented data classification and handling rules.

- There must be regular backups for all WIMA data and audit logs.

- In the event of an incident, the appropriate incident response procedures must be followed.

- Data sharing of any kind must be authorised. All WIMA generated data is solely for the use of WIMA. No part of it may be circulated, quoted, or reproduced for distribution outside WIMA without prior written approval from WIMA even after it has been shared by WIMA.

- WIMA is the registered owner of all hardware, software (including MamaTrak) and data. Personal use of WIMA digital assets is prohibited.

- Personal data must be processed lawfully, fairly and transparently, adhering to the NDPR.

- No manual alterations to digital records are permitted. All changes must possess a clear, unalterable system audit trail.

- Falsifying data or turning a blind eye to unauthorised system access shall result in instant dismissal.

- Any loss or unauthorised disclosure of data must be reported to the President immediately and, if applicable, to NITDA.

- Field staff and members must be provided with stepwise digital literacy training to bridge technology adoption gaps.

SUPERVISION OF COMMUNITY & SUB-COMMUNITY LEADS

Overview of Process

The “Supervision of Community & Sub-Community Leads” process establishes the framework for managing WIMA’s decentralised partner network. a structured framework for supervising, supporting and holding Community Leads (CLs) and Sub-Community Leads (Sub-CLs) accountable for the effective delivery of WIMA operations at hub, LGA and ward levels. It ensures clarity of roles, consistent performance management, early identification of issues, capacity development and alignment with WIMA’s operational, financial, data and governance standards.

Scope

This process applies to the supervision and management of all Community Leads and Sub-Community Leads engaged by WIMA across all hubs, LGAs, states and zones, regardless of project or funding source.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved role descriptions and SOPs - Performance targets and KPIs - Hub registers and operational reports - Supervision and monitoring tools - Farmer Mobilisation Targets - GPS Tracking and Usage Data - Community Engagement Logs | - Supervision visit reports - Performance review records - Lead Performance Appraisals - Corrective action/improvement plans - Escalation and disciplinary records - Validated State Improvement Plans |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Appointment or onboarding of a CL or Sub-CL - Commencement of hub, activation of a new LGA hub - or project operations - Routine supervision, performance review, or issue escalation cycles - End of the monthly reporting cycle - Seasonal service demand peak | - State/Zonal Coordinator: Primary supervisor of CLs and Sub-CLs within jurisdiction - National Coordinator / Project Lead: Oversight of supervision standards and escalation - Community Lead (CL): Day-to-day supervision of Sub-CLs - Sub-Community Lead (Sub-CL): Supervise MSP field activities. - CFO: Oversight of financial compliance - Field Compliance Manager: Oversight on operational compliance - MEL Coordinator: Performance data verification and reporting |
| Tools Required | Key Performance Indicators (KPIs) |
| - Supervision and monitoring checklists - Performance scorecards and KPIs/WIMA ERP (Performance Mgt Module) - Issue and escalation logs - Training and coaching materials - Executive Power BI Dashboards - Accountability Audit Checklists - WIMA Business Hotline | - Compliance rate with SOPs and registers - Hub operational performance indicators - Timeliness and quality of reporting - Resolution rate of identified issues - Hub Satisfaction Rating. - Data submission rate. - % Inclusion (Target: 80% Female/20% Youth). - Reduction in service delivery delays. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Onboard CLs & Sub-CLs | Provide orientation on roles, SOPs and expectations Key Control: Applicable job descriptions and SOPs must be handed to lead | State Coordinator | At point of engagement |
|  | Set Performance Targets | Agree KPIs and deliverables. Translate state-level objectives (membership growth and land coverage) into specific hub-level targets. Key Control: All performance related discussions must be documented | State Coordinator / CL | Annual/ Seasonal |
|  | Routine Supervision | Conduct scheduled field and virtual supervision Key Control: All supervisory visits must be documented | State Coordinator / CL | Weekly/ Monthly |
|  | Stakeholder Engagement Audit | Review records of engagements with traditional rulers and religious leaders to ensure local legitimacy and cultural buy-in. | State Coordinator | Monthly |
|  | Review Registers & Reports | Verify accuracy and completeness of records. Key Control: Physically or digitally verify all WIMA registers (member, service and finance) at the hub levels for accuracy. | State Coordinator | Monthly |
|  | Provide Coaching | Offer guidance and problem-solving support | State Coordinator / CL | As required |
|  | Identify Issues | Detect performance gaps or non-compliance | State Coordinator / CL |  |
|  | Implement Corrective Actions | Agree and implement improvement actions | CL / Sub-CL | Over specified period |
|  | Monitor Improvement | Track implementation of corrective actions | State Coordinator / CL | Within the month |
|  | Escalate Serious Issues | Escalate material issues to national level. Key Control: Immediately escalate any reports of SEAH, corruption, or security threats through the built-in ERP module. | State Coordinator / CL | Immediate |
|  | Performance Review | Conduct periodic formal performance reviews. Host quarterly joint reviews to assess effectiveness, share learnings and adjust mobilisation strategies for future expansion. | State/National Coordinator | Quarterly |
|  | Recognition or Sanctions | Apply rewards, retraining, or disciplinary measures Identify underperforming hubs (e.g., data integrity) and provide targeted leadership training or technical support. | State/National Coordinator | Over the next cycle |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Data Falsification | Leads inflating farmer numbers or service hours to meet KPIs. | Use automated equipment logs (GPS) and mandatory token-driven bookings to create an unalterable audit trail. |
| Weak supervision | Declining hub performance | Supervision schedules |
| Role confusion | Duplication or gaps | Clear role definitions |
| Capacity Gaps | Leads lacking the digital literacy to manage ERP reporting. | Utilise a stepwise training approach and engage consultants for "hand-holding" during immediate expansion phases. |
| Unreported issues | Escalation failures | Issue tracking |
| Demotivation | Poor morale | Coaching and recognition |
| Non-compliance | Governance breaches | Enforcement protocols |
| Lack of Cooperation | Potential friction between partner leads and national directives. | Clearly communicate the purpose of initiatives and maintain frequent engagement sessions to secure stakeholder buy-in. |
| Unauthorised Usage | Machinery used for unrecorded tasks by lead-supervised operators. | Implement remote monitoring to pinpoint asset locations and monitor idle time. |

Policy Guidelines

- There shall be a clear organisation structure which is understood by all persons within the WIMA operation. It shall communicate the appropriate supervisory hierarchy.

- All supervisory and performance reviews must be documented.

- There shall be a clear framework/process to guide formal escalation and issue resolution.

- All SOPs/process documents must be complied with.

- All serious issues must be escalated promptly

- Performance management must be fair and transparent according to the HR policy.

- All persons responsible for work activities are accountable for identifying injurious conditions and ensuring workers use PPE correctly.

- Any lead found soliciting bribes or engaging in SEAH shall face instant dismissal and potential legal action.

- Hub registers/digital data must be updated and synced with ERP cloud within 24 hours to ensure visibility.

- Personal data of members and whistleblowers must be protected according to the NDPR.

- Leads are prohibited from engaging in activities that personally benefit themselves or their relatives at WIMA’s expense.

- Data sharing of any kind must be authorised. All WIMA generated data is solely for the use of WIMA. No part of it may be circulated, quoted, or reproduced for distribution outside WIMA without prior written approval.

STATE/ZONAL OPERATIONAL OVERSIGHT

Overview of Process

The “State/Zonal Operational Oversight” process defines how WIMA manages its expanding footprint through a decentralised structure. It establishes how State/Zonal Coordinators exercise managerial, operational, financial, asset and performance oversight over hubs, Community Leads (CLs), Sub-Community Leads (Sub-CLs) and projects within their jurisdiction to ensure alignment with WIMA’s strategy, standards and business objectives. To prevent the National Coordinator’s span of control from being overwhelmed as the association scales toward 36 states, a Zonal layer is activated.

Scope

This process applies to all State and Zonal Coordinators overseeing WIMA operations, hubs, projects, personnel, assets and finances across states and zones.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved strategic and operational plans - SOPs, policies and guidelines - Hub operational, financial and asset reports - Supervision and performance reports/Monthly State Performance Summaries - Hub Audit Results (Compliance Scores) - ERP Executive Dashboard Data - Feedback from Hub | - State/Zonal operational performance reports/analytics - Consolidated hub performance dashboards - Risk and issue escalation reports/quarterly risk exposure reports - Corrective action and improvement plans - Zonal Budget Variance Analysis |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Commencement of operations in a state or zone - Launch of a new hub or project - Monthly or quarterly oversight cycles - Escalation of operational, financial, or compliance issues - Quarterly risk review cycle | - State/Zonal Coordinator: Primary oversight and control of state/zonal operations - National Coordinator / Project Lead: Strategic oversight, approvals and escalation - Community Leads (CLs): Execute hub-level operations and reporting - CFO: Financial oversight and compliance - Monitoring & Evaluation Manager: Performance monitoring and data validation - Field Compliance Manager: Conducts accountability audits and verifies SOP adherence. |
| Tools Required | Key Performance Indicators (KPIs) |
| - Operational oversight checklists - Performance dashboards and scorecards - Financial and asset registers - Issue escalation and tracking logs - ERP Dashboard - GPS Machine Tracking Plug-ins - WIMA Business Hotline | - Hub performance compliance rate - Timeliness and accuracy of reports - Asset utilisation and downtime rates - Revenue and cost performance vs budget - Issue resolution turnaround time - % of decisions executed at the state level (Target: High). - Reduction in service delivery delays - % of hubs passing quarterly compliance audits. - Average hub satisfaction rating |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Establish Oversight Framework | Define oversight calendar, reporting templates and review cadence with State Coordinators | Zonal Coordinator | At start |
|  | Review Operations | Analyse operational performance and service delivery. Use BI dashboards to review aggregated data for assigned states. Verify that state/zonal-level activities (mechanisation access and training) align with the inclusion quotas | Zonal/ National Coordinator | Weekly |
|  | Financial Oversight | Review revenues, expenses and revenue sharing Key Control: Reconcile machine engine hours against collected revenue. Ensure the revenue split is maintained to fund hub recapitalisation. | Zonal Coordinator/ CFO | Weekly |
|  | Asset & Equipment Oversight | Monitor allocation, utilisation and maintenance Key Control: Conduct physical spot-checks to verify asset existence against the digital Asset Register and ensure safety equipment is functional. | Zonal/ Field Compliance Manager | Quarterly |
|  | Supervise ZCs & SCs | Conduct supervision and performance reviews Key Control: Identify underperforming regions instantly via the Executive Dashboard. | Zonal/ National Coordinator | Weekly |
|  | Validate Data & Reports | Verify accuracy and completeness of submitted data | Zonal/ National Coordinator / MEL Coordinator | Weekly/ Monthly |
|  | Identify Risks & Issues | Detect operational, financial, or compliance risks | Zonal/ National Coordinator | Immediate |
|  | Implement Corrective Actions | Direct corrective actions at state or personnel level. Review feedback for state improvement plans and provide technical support or resource reallocation to lagging states. | Zonal Coordinator | Immediate |
|  | Escalate Material Issues | Escalate unresolved or material issues Key Control: Review the ERP Incident Module for unresolved SEAH or security threats. Alert assigned security vendors for prompt intervention where required. | Zonal Coordinator → National Coordinator | Immediate |
|  | Consolidate Zonal Reports | Prepare and submit oversight reports. Aggregate zonal performance for the President/Board of Trustees (BOT). Refine national/regional strategies based on evidence from the MEL system. | National Coordinator | Monthly |
|  | Review & Improve Operations | Use lessons learned to improve operations | State/Zonal / National Coordinator | Monthly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Weak oversight | Poor hub performance | Oversight calendar |
| Financial leakages | Revenue or cost inefficiencies. Cash handling at the local level bypassing the percentage split. | Regular reconciliations. Mandate 100% cashless transactions via digital wallets integrated into the ERP. |
| Data Falsification | Partner-led hubs misreporting usage to hit KPIs. | Enforce automated equipment logs (GPS) and token-driven activation to create an unalterable audit trail. |
| Asset misuse | Equipment loss or abuse | Asset tracking |
| Data manipulation | Inaccurate reporting | Independent validation |
| Delayed escalation | Prolonged issues | Escalation timelines |
| Span of Control Overwhelm | National level unable to manage 36 state coordinators directly. | Activate the Zonal layer; limit Zonal Coordinators to a maximum of six direct reports. |
| Cultural or Advocacy Pushback | Resistance to women operating heavy machinery in traditional zones. | Secure formal pledges from traditional rulers (e.g., Emirs) to legitimise women operators via the He4She Club. |

Policy Guidelines

- There must be clear authority and accountability structure.

- All state and zonal coordinators must follow the standardised reporting and review cycles.

- There must be clear separation of oversight and execution roles.

- Material issues must be escalated promptly via formal escalation and approval thresholds

- State/Zonal Coordinators shall be accountable for operational integrity.

- All oversight activities must be documented.

- All strategic initiatives must be tracked with KPIs, with a focus on empowering state-level execution.

- Any report of bribery or "speed money" (facilitation payments) shall result in instant dismissal and potential legal action.

- All reports of SEAH must be handled with 100% confidentiality and reported to the National Coordinator/Safeguarding Officer immediately.

- All member and farm data must be handled according to the NDPR.

- Signatories and coordinators must respond to authorisation requests within 30 minutes to maintain equipment uptime and hub service delivery.

COMPLIANCE MONITORING & FIELD AUDIT

Overview of Process

The “Compliance Monitoring & Field Audit” process defines the approach for compliance monitoring and field audits across all WIMA operations. It ensures that hubs, projects, personnel, assets, financial activities and data management practices comply with approved SOPs, policies, contractual obligations and governance standards. The process supports early detection of non-compliance, risk mitigation, continuous improvement and accountability across all operational levels.

Scope

This process applies to all WIMA operations at national, state/zonal, hub, LGA and ward levels, including Community Leads (CLs), Sub-Community Leads (Sub-CLs), operators, MSPs and partner-supported projects.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved SOPs, policies and guidelines - Hub, financial, asset and data registers - Previous audit reports and action plans - Compliance checklists and audit tools - IT Asset Register (Hardware/Machinery) - ERP Financial & Token Logs | - Compliance monitoring reports - Field audit findings and ratings/hub compliance scorecard - Non-compliance and risk registers - Corrective and preventive action plans - Quarterly Accountability Audit Report - Verified Asset Inventory Summary |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Routine compliance monitoring cycles (monthly/quarterly) - Planned or unannounced field audits - Donor, partner, or regulatory audit requirements - Escalation of suspected non-compliance or risk incidents - "Red Flag" alert from ERP Dashboard (e.g., GPS variance) - New hub establishment/activation | - National Coordinator / Project Lead: Overall compliance governance and approvals - State/Zonal Coordinator: First-line compliance oversight and field audits - Monitoring & Evaluation Coordinator: Data, performance and reporting audits - CFO: Financial, asset and process compliance - Community & Sub-Community Leads: Provide access to records and operations - Field Compliance Manager: Oversight of physical spot-checks and HSE verification. - Internal Audit: Validation of financial controls and post-payment audits. |
| Tools Required | Key Performance Indicators (KPIs) |
| - Compliance monitoring checklists - Field audit templates - Risk assessment tools - Issue tracking and escalation logs - WIMA ERP (Executive Dashboard) - GPS Machine and Equipment Tracker - Accountability Audit Checklists - Smart devices with GIS mapping | - Compliance rate with SOPs - Number and severity of audit findings - Timeliness of corrective action closure/Average time to resolve non-compliance - Recurrence rate of non-compliance issues - Annual Governance Audit Score - % Hubs passing quarterly audits. - 100% Post-payment audit completion. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Develop Compliance Plan | Define audit scope, frequency and methodology. Use the ERP dashboard to identify hubs with low data integrity or high GPS/revenue variance for priority auditing. | Field Compliance Manager | Quarterly (Week 1) |
|  | Notify or Conduct Surprise Audit | Issue notification or perform unannounced visit State/Zonal Coordinators can conduct audit visits outside those carried out by the field compliance function. They may choose to announce or not announce visit. | National / State Coordinator/ Field Compliance Manager | 1 – 3 Days |
|  | Conduct Field Audit | Review operations, assets, finances and records | Audit Team | On-site 1 – 2 Days |
|  | Verify Records | Cross-check registers, systems and physical assets Key Control: Physically verify every machine against the serial numbers in the IT Asset Register. Ensure GPS trackers are functional and untampered. | Audit Team |  |
|  | Interview Personnel | Validate processes and controls. Observe daily hub operations to confirm use of system-generated tokens, mandatory PPE and completion of pre-op inspection checklists, etc. | Audit Team |  |
|  | Document Findings | Record compliance gaps and risks. Inspect storage facilities to ensure they are dry and well-ventilated. Verify that fire extinguishers and first-aid kits are accessible and unexpired. Verify that the WIMA Code of Conduct and anonymous reporting hotline are prominently displayed, etc Key Control: Perform a 100% post-payment audit of recent services. Reconcile bank alerts with service tokens and the 20/50/30 revenue split. | Audit Team |  |
|  | Rate Compliance | Assign risk and severity ratings | Audit Team |  |
|  | Audit Debrief & Reporting | Present findings to the CL. Issue a "Non-Conformance Report" for any critical failures (e.g., missing assets or SEAH violations). | Audit Team | Within 48 Hours |
|  | Escalate Material Issues | Escalate serious findings (where applicable) | Field Compliance Manager → National | Immediate |
|  | Develop Action Plan | Agree corrective and preventive actions | State Coordinator/ CLs | 1 – 2 Days |
|  | Monitor Closure | Track implementation of actions. Monitor the hub's implementation of improvement plans. Conduct a follow-up visit if the compliance score remains below 85%. | State / Zonal Coordinators | Next 30 Days |
|  | Report & Learn | Consolidate reports and lessons learned. Aggregate state-level results for the President/BOT | National Coordinator | Monthly (Day 7) |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Undetected non-compliance | Weak controls | Routine audits |
| Collusion or bias or Conflict of Interest | Compromised audits. Auditors having personal relationships with hub partners. | Independent teams. Enforce rotation of audit teams and mandatory declarations of interest as per the Anti-Corruption Policy. |
| Record manipulation | Falsified data. Staff or partners altering records before the audit team arrives. | Physical verification. Use system-generated tokens and bank alert APIs that create an unalterable audit trail in the ERP. |
| Delayed action | Persistent issues | Closure deadlines |
| Audit fatigue | Reduced cooperation | Clear communication |
| Asset Theft or Concealment | Missing machinery being reported as out on service. | Mandatory GPS journey management to pinpoint live locations; no asset is verified without physical sighting. |
| Security Risks in "Red-Zones" | Audits being delayed due to insecurity | Use ERP incident reporting to assess safety; engage local traditional leaders (He4She Club) for safe passage |

Policy Guidelines

- Where applicable, an audit team shall be formed and coordinated by the Field Compliance Manager.

- Compliance audits are mandatory.

- Independent audit and verification must be carried out in all hubs.

- A standardised compliance checklists shall be developed by the Field compliance function to guide audit teams for consistency.

- All audit reports must be evidence-based and not speculation.

- The appropriately defined escalation shall be used to address issues or serious findings.

- All State/Zonal coordinators must ensure that appropriate follow-up and closure tracking is done for exceptions.

- All hub personnel must give their full cooperation to the audit team as required.

- Findings must lead to action

- Any form of retaliation against whistleblowers is prohibited.

- Internal Audit must conduct a 100% audit of all financial disbursements quarterly to ensure zero infractions.

- Any evidence of bribery, "speed money," or SEAH discovered during an audit shall result in instant dismissal.

- Every hub must display the Safeguarding Policy and WIMA Code of Conduct to maintain its operational status.

- All audit findings must be digitised and synced with the ERP within 24 hours of completion.

- The Field Compliance Manager has the authority to "Ground" any machinery found to be in an unsafe condition or being used for "off-book" services.

- If an audit uncovers sensitive information (e.g., SEAH survivors or whistleblowers), details must be shared only on a need-to-know basis.

ISSUE ESCALATION & RISK REPORTING

Overview of Process

The “Issue Escalation & Risk Reporting” process defines the formal mechanism for identifying, documenting, escalating and reporting operational, financial, asset, safety, reputational, compliance and strategic risks and issues across WIMA operations.

Scope

This process applies to all WIMA personnel, hubs, projects, partners and operational levels including National, State/Zonal, Community and Sub-Community levels.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Issue and risk reports - Supervision and audit findings - Incident and complaint records - Financial and operational reports - GPS movement and equipment idle data - Witness statements and field logs - Member feedback and whistleblower entries - Daily equipment inspection reports | - Issue logs and escalation records - Risk registers (state/zonal and national) - Risk mitigation and response plans - Management risk reports - Escalation alerts to security/legal vendors - Quarterly risk exposure reports - Incident investigation root-cause analysis |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Identification of an operational, compliance issue, near-miss events, complaint, potential threat or incident - Detection of a potential or emerging risk - Field audit or supervision findings - Report of SEAH or corruption | - All WIMA Personnel: Identify and report issues and risks - Community & Sub-Community Leads: First-line issue logging and escalation - State/Zonal Coordinator: Risk assessment, mitigation and escalation - National Coordinator / Project Lead: Oversight of material risks and decisions - Finance & Operations Officer: Financial and asset risk reporting - MEL Coordinator: Data and performance risk tracking - Field Compliance Manager: Oversight of physical audits and root-cause investigations. |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA ERP (Incident & Security Module) - Anonymous Reporting Hotline - Risk Assessment Matrix (Likelihood x Impact) - Whistleblower Protection Mechanism | - Time to report critical incidents (Target: <1 hour). - % of high-rated risks with active mitigation plans. - Annual Governance Audit Score (). - Zero unaddressed safeguarding (SEAH) cases. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Identify Issue or Risk | Observe, detect, or receive issue/risk | All Staff/Partners | Real-time |
|  | Log Issue or Risk | Document in issue/risk register. Enter incident details into the ERP Incident Module, including time, location, cause and witnesses. | CL / Sub-CL | <2 Hours |
|  | Preliminary Assessment | Assess severity and urgency | CL / State Coordinator | Immediate |
|  | Immediate Containment | Take immediate actions if required | CL / State Coordinator | Immediate |
|  | Escalate to State/Zonal | Submit issue/risk for review | CL → State → Zonal | Within 24 Hours |
|  | State/Zonal Review | Validate, classify and assign actions | State/Zonal Coordinator |  |
|  | Escalate Material Risks | Escalate high-risk issues. Key Control: Any report of Corruption, SEAH, or Security Threats must be escalated instantly to the President and Safeguarding focal person. | State → National Coordinator | Immediate |
|  | Develop Mitigation Plan | Define corrective or preventive actions | State / National Coordinator | Immediate |
|  | Implement Actions | Execute mitigation measures. Implement the pre-defined "Steps to Mitigate" from the Risk Register (e.g., grounding equipment or alerting security vendors). | Assigned roles | As per severity |
|  | Investigation | Conduct a root-cause analysis for serious incidents. Key Control: The Safeguarding or Ethics Committee oversees sensitive cases to ensure fairness and due process. | Field Compliance | 5 Days |
|  | Monitor & Update | Track status and update registers | State / MEL Coordinator/ Field Compliance Manager | As per plan |
|  | Close or Reclassify | Close resolved issues or re-rate risks. Verify that corrective actions are complete. Update the ERP status and inform the whistleblower/survivor of the outcome. | State /National Coordinator | 7 Days |
|  | Report to Management | Consolidate and submit risk reports to the President | National Coordinator | Monthly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Under-reporting | Issues hidden or delayed | Awareness and protection |
| Data Falsification | Hubs concealing incidents to maintain their compliance score. | Cross-reference manual reports with automated equipment logs (GPS) and remote monitoring tools. |
| Delayed escalation | Delays in approving mitigation steps for time-bound risks. Issues worsen | Escalation timelines. Persons must respond to escalation within 30 minutes as per WIMA’s accountability mandate. |
| Poor risk assessment | Wrong prioritisation | Risk matrix |
| No follow-up | Unresolved risks | Tracking registers |
| Retaliation fears | Silence. Members or staff failing to report serious misconduct due to pressure | Strict enforcement of the Whistleblower Policy, providing anonymous reporting channels and private rewards for confirmed declarations. Whistleblower protection |
| Volatile "Red-Zone" Access | Reporting or investigating in areas with high security threats. | Engage local traditional and religious leaders for mediation and abide by the Emergency Community Response & Safeguarding Guide. |

Policy Guidelines

- WIMA must have a standardised risk identification and rating framework.

- The defined escalation response timeline is 30 minutes.

- There must be a formal approval for risk closure.

- There must be a separation between risk reporting and decision-making regarding resolution.

- All material issues must be reported accordingly and capture in the incident module of the ERP.

- Escalation is mandatory, not optional.

- All incidents deemed as serious must be investigated to determine their root cause for appropriate mitigation for future occurrences.

- Retaliation of any form against good-faith reporting shall not be tolerated.

- Risk ownership must be assigned appropriately assigned.

- WIMA prohibits all forms of corruption, bribery and SEAH; violations shall result in instant dismissal and potential legal action.

- All incident reports, especially those involving personal data or SEAH survivors, are shared only on a need-to-know basis.

- All employees, partners and stakeholders have an obligation to report suspected misconduct immediately.

- In extortion situations involving threats to life or liberty, employees and partners must use their best judgment; WIMA shall support them after the report is made.

- No asset shall be moved or used after an incident report is logged until it is technically cleared and updated to "Operational" status in the ERP.

- Feedback from past cases must be incorporated into annual reviews of the Risk Register and SOPs.

KPI & INDICATOR MANAGEMENT

Overview of Process

The “KPI & Indicator Management” process defines how to identify, track, validate, report and use Key Performance Indicators (KPIs) across national, zonal, state, hub and community levels. The process ensures consistent performance measurement, accountability, evidence-based decision-making and alignment with WIMA’s strategic plan.

Scope

This process applies to national, zonal, state and hub-level operations. It also applies to various functions and teams.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved Strategic Plan and Implementation Roadmap - Approved Results Framework and KPI Dictionary - Hub operational data (services, utilization, revenue) - Membership and training records - Digital platform and ERP system data - Financial and audit reports - Farmer baseline/impact surveys | - KPI dashboards (national, zonal, state, hub levels) - Monthly, quarterly and annual performance reports - Performance variance and exception reports - Evidence for donor, partner and board reporting - Inputs into planning, budgeting and corrective actions - Annual M&E/Impact reports |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Approval of WIMA Strategic Plan or annual workplan - Commencement of a new program, hub, or initiative - Start of a reporting cycle (monthly, quarterly, annual) - Identification of performance gaps or risk signals | - Board Of Trustees / President: Oversight of strategic KPIs and accountability - National Coordinator: Overall performance coordination and escalation - MEL Coordinator: KPI framework design, data quality, analysis, reporting - Zonal Coordinator: Consolidation and validation of state-level KPIs - State Coordinator: State performance tracking and hub reporting - Community & Sub-Community Leads: Primary data capture and validation - CFO: Financial KPIs, revenue assurance, cost recovery - Field Compliance Manager: Compliance, audit and exception monitoring - IT / Data Team: System availability, dashboards, data integrity |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA Digital Hub Management System / ERP - Mobile data collection tools - KPI dashboards - Standard reporting templates - KPI Dictionary and Indicator Reference Guide | - % of hubs submitting complete data monthly (Target ≥ 90%) - Timeliness of KPI reporting (Target: within agreed timelines) - Data error/variance rate (Target ≤ 5%) - % of strategic initiatives tracked with KPIs (Target: 100%) - % of management decisions informed by KPI data |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Define KPIs & Indicators | Align KPIs to strategic pillars, initiatives and annual targets. Define KPIs based on the four strategic pillars: Expansion, Revenue, Structure and Digital. Align with SDG targets (2, 5, 8, 12, 13, 17). | MEL / National Coordinator | Annual / As needed |
|  | Approve KPI Framework | Review and approve KPI list and definitions | President / Board | Annual |
|  | Communicate KPIs | Cascade KPIs to zonal, state, hub and community levels | National / Zonal Coordinators | Annual / Quarterly |
|  | Baseline Data Capture | Gather initial data to inform future growth targets. | MEL Coordinator / Data Officer | As needed |
|  | Data Collection/ Submission | Capture operational, financial, digital and impact data. Upload field data to the cloud-based ERP. The system uses the ERP-generated tokens and GPS logs to automate the tracking of tractor hours and acreage serviced. | Sub-CL/ CL / MSPs | Daily / weekly |
|  | Data Validation | Verify accuracy and completeness of submitted data | State / Zonal Coordinators | Weekly/ Monthly |
|  | Analysis & Dashboarding | Generate dashboards and performance summaries | ERP (Automated) MEL Coordinator / Data Officer | Daily/ Monthly / Quarterly |
|  | Impact Evaluation | Utilise date capture during operations to calculate other impact metrics. Conduct annual surveys to measure other impact areas where data is not capture regularly during the field operations such household incomes, etc. | MEL Coordinator | Quarterly/ Annual |
|  | Performance Review | Review results, identify gaps and trends. | Management | Monthly / Quarterly |
|  | Escalation & Action | Escalate underperformance and agree corrective actions | National Coordinator | As required |
|  | Reporting | Produce formal reports for leadership and partners | MEL Coordinator / KM | Quarterly / Annual |
|  | Adaptive Planning | Use evidence-based insights to refine regional strategies and adjust State Improvement Plans. | National Coordinator | Quarterly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Inaccurate KPI definitions | KPIs interpreted differently across zones, states, or hubs | Approved KPI Dictionary with standardized definitions and measurement methods |
| Data manipulation, falsification or inflation | Hubs or partners inflating figures and intentional misreporting to meet targets. | Multi-level validation, system audit trails and random field audits. Use automated equipment logs (GPS) and token-driven bookings to create an unalterable audit trail. |
| Delayed data submission | Late reporting affects timely decision-making | Automated reminders, reporting deadlines and escalation for non-compliance |
| Data gaps | Incomplete or missing KPI records from hubs or communities | Mandatory monthly submissions, completeness checks and supervisory follow-up. Build data capture forms into the mobile ERP; enable offline syncing for areas with poor connectivity. |
| Retaliation Fears | Staff, partners or survivors fearing to report incidents of gender violence (SEAH). | Use an anonymous reporting hotline and guarantee protection for whistleblowers. |
| Poor data quality | Errors due to low capacity or manual entry | Training, validation rules and digital data capture tools |
| KPI overload | Measuring too many indicators dilute focus, accountability and leading to management fatigue | Annual KPI rationalization and prioritization. Automation for calculating metric from existing typical field reports/upload without additional burdens. |
| Limited data use | KPIs collected but not used for decisions | Mandatory performance review meetings and action tracking |
| System downtime | Digital platform unavailability disrupts reporting | System redundancy, offline capture options and IT support protocols |

Policy Guidelines

- The M&E function must develop standard KPI definitions and measurement methods.

- The system shall ensure role-based access to KPI systems.

- All hub activities must be linked to a verifiable KPI in the ERP to ensure transparency and accountability.

- There must be mandatory validation before data submission.

- The ERP system must be capable of providing automated audit trails.

- No manual alterations to digital M&E records are permitted; any changes must possess a clear system audit trail.

- Independent compliance and field audits shall be done by the MEL or Field Compliance function.

- Only approved KPIs shall be tracked and reported.

- All hubs must submit data within agreed timelines.

- Performance data must be evidence-based and auditable.

- KPI results shall inform planning, budgeting and accountability reviews.

- Non-compliance with reporting requirements shall trigger escalation and lead to sanctions.

- Every indicator must be disaggregated by gender and age (where applicable) to ensure the female and youth inclusion targets are met and reported.

- National and hub leadership will be assessed against an Annual Governance Audit Score ≥ 85%.

- Every indicator must have a designated Responsible Person to ensure ongoing compliance and reporting.

PERFORMANCE MONITORING & REPORTING

Overview of Process

The “Performance Monitoring & Reporting” process defines how WIMA tracks performance against approved plans, KPIs and targets; reviews result at different governance levels; and reports performance to management, the Board, partners and stakeholders. It establishes a structured and consistent approach for:

- Monitoring progress against strategic, operational and financial targets

- Reviewing performance trends and variances

- Reporting accurate, timely and decision-relevant performance information

- Driving corrective actions and continuous improvement

Scope

This process applies to national, zonal, state and hub-level operations. It also applies to various functions and teams as it relates to internal and external performance reporting.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Validated KPI and indicator data - Approved annual workplans and budgets - Financial and management accounts - Hub and program progress reports - Compliance and audit findings | - Performance dashboards - Monthly, quarterly and annual performance reports - Management briefing notes and scorecards - Exception, variance and corrective action reports - Donor, partner and regulatory reports |
| Process Trigger | Process Owner(s) and Responsibilities |
| - End of a reporting period (monthly, quarterly, annual) - Management or Board performance review meetings - Donor or partner reporting requirements - Identification of performance risks, underperformance, or exceptions | - Board of Trustees: Oversight of strategic performance and accountability - President: Overall performance leadership and decisions - National Coordinator: Consolidated performance monitoring and escalation. Alignment with strategic objectives and initiatives - MEL Coordinator: Performance analysis, reporting, and learning - Zonal Coordinator: Zonal performance review and consolidation - State Coordinator: State-level monitoring and hub reporting - Community Lead: Hub performance tracking and reporting - CFO: Financial performance and budget variance reporting - Field Compliance Manager: Verification, exception tracking, and assurance |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA Digital Hub Management System / ERP - KPI dashboards and analytics tools - Standard performance report templates - Meeting minutes and action-tracking logs - Document management and knowledge repository | - Timeliness of performance reporting (Target: within agreed timelines) - Data error/variance rate (Target ≤ 5%) - % of strategic initiatives tracked with KPIs (Target: 100%) - % of management decisions informed by performance data |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Data Consolidation | Consolidate validated KPI, financial, and operational data | MEL Coordinator / Data Team | Monthly |
|  | Performance Analysis | Analyze trends, variances, and risks | MEL Coordinator | Monthly / Quarterly |
|  | Dashboard Update | Update performance dashboards and scorecards | IT / MEL Coordinator | Monthly |
|  | Internal Review | Conduct hub, state, and zonal performance reviews Key control: Audit trails for changes to reported data | State & Zonal Coordinators | Monthly / Quarterly |
|  | Exception Identification | Flag underperformance and risk indicators | MEL Coordinator / Field Compliance Manager | Monthly |
|  | Management Review | Review results and agree corrective actions | National Management | Quarterly |
|  | Action Tracking | Document and monitor agreed actions | MEL Coordinator | Ongoing |
|  | Reporting | Prepare and submit formal performance reports | MEL Coordinator / KM | Quarterly / Annual |
|  | External Reporting | Submit donor/partner reports as required Key control: Management sign-off for external reports | MEL Coordinator/ CFO | As required |

Performance Monitoring Cadence

| Level | Review Frequency | Focus |
| --- | --- | --- |
| Hub | Weekly / Monthly | Service delivery, utilization, revenue, issues |
| State | Monthly | Hub performance, data quality, exceptions |
| Zonal | Quarterly | Regional trends, risks, and escalations |
| National Management | Quarterly | Strategic progress, financial health |
| Board | Bi-annual / Annual | Strategic outcomes and impact |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Delayed reporting | Reports submitted after agreed timelines | Reporting calendar, automated reminders, escalation |
| Inaccurate reporting | Errors in consolidated performance data | Validation checks and independent reviews |
| Selective reporting | Focus on positive results while omitting issues | Mandatory exception and variance reporting |
| Weak follow-through | Agreed actions not implemented | Action tracker with ownership and deadlines |
| Information overload | Reports too complex or lengthy | Executive summaries and standardized dashboards |
| Misalignment with strategy | Reports not linked to strategic priorities | Strategy-led reporting framework |

Policy Guidelines

- The system shall ensure role-based access to KPI/performance data.

- All hub activities must be linked to a verifiable KPI in the ERP to ensure transparency and accountability.

- The ERP system must be capable of providing automated audit trails.

- No manual alterations to digital M&E/performance records are permitted; any changes must possess a clear system audit trail.

- All performance reports must be evidence-based and traceable.

- Exceptions and underperformance must be reported transparently.

- Performance reviews shall inform planning, budgeting, and resource allocation.

- External performance reports require executive approval.

- Failure to report or act on performance issues shall trigger the appropriate escalation.

LEARNING, ADAPTATION & CORRECTIVE ACTION

Overview of Process

The “Learning, Adaptation & Corrective Action” process defines how WIMA tracks performance against approved plans, KPIs and targets; reviews result at different governance levels; and reports performance to management, the Board, partners and stakeholders.

Scope

This process applies to all WIMA programmes, hubs and initiatives. It also applies to various functions and teams as it relates to internal learning process and external evaluations.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Performance monitoring and reporting outputs - KPI dashboards and variance analyses - Audit and compliance reports - Field supervision findings - Stakeholder feedback and complaints - Lessons from pilots and innovation initiatives - Quarterly M&E and Impact Reports - Market Intelligence and Implementation Learnings - Customer Satisfaction Surveys and Feedback | - Documented lessons learned - Approved corrective action and implementation plans - Adapted operational guidelines or SOP updates - Strategy or workplan adjustments - Knowledge products and learning briefs |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Performance reviews indicating underperformance or risks - Findings from compliance audits or field assessments - Feedback from members, beneficiaries, or partners - External evaluations, pilots, or proof-of-concept reviews - Significant contextual or operational changes - Completion of a quarterly performance review - Reach of a seasonal milestone or crop cycle - Detection of a critical KPI variance (e.g., <90% data submission) | - Board of Trustees: Oversight of major adaptations and accountability - President: Approval of significant corrective actions - National Coordinator: Coordination of learning and corrective action processes. Translation of learning into strategy and plans - MEL Coordinator/KM: Learning synthesis, analysis, and documentation - Zonal Coordinator: Regional learning reviews and action follow-up - State Coordinator: Implementation and monitoring of corrective actions - Community Lead: Identification of issues and execution of actions - Field Compliance Manager: Independent validation of corrective actions |
| Tools Required | Key Performance Indicators (KPIs) |
| - Performance dashboards and reports - Corrective Action Register - Learning logs and after-action review templates - Stakeholder feedback and grievance systems - Knowledge management repository | - % of management decisions informed by performance data and learnings - % Decisions informed by M&E data (Target: 100%). - Post-training performance improvement - % Hubs achieving break-even within 18 months. - Average time to resolve non-compliance. |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Identify Issues | Flag performance gaps, risks, or lessons. Extract findings from the MEL system, focusing on yield impacts, revenue CAGRs, and machine utilisation rates | MEL Coordinator | Ongoing |
|  | Analyze Root Causes | Conduct root cause and gap analysis Conduct focus groups or field audits for hubs with low satisfaction or high equipment downtime to identify systemic barriers. | MEL Coordinator | As needed |
|  | Document Learning | Capture lessons and insights | MEL Coordinator / KM | Quarterly |
|  | Propose Actions | Develop corrective or adaptive actions. Where applicable, meet with the President to assess what is working and what must be done differently based on implementation learnings (particularly where it is a major change to operating model) | National Coordinator | As needed |
|  | Approve Actions | Review and approve corrective actions Key Control: All corrective actions based on learnings must be approved | President | As required |
|  | Corrective Action Implementation | Execute State Improvement Plans, providing targeted leadership training or technical "hand-holding" to lagging hubs. | State Coordinator/ CL | Ongoing |
|  | Track Actions | Monitor progress against action plans | MEL Coordinator | Monthly |
|  | Update SOPs / Plans | Revise documents based on learning Communicate changes and "what is ending" (old processes) to staff and partners to encourage adoption and cultural buy-in. Key Control: Formally update operational procedures based on lessons learned to ensure standardisation across the 36-state expansion. | Operations/ Process Owner/ KM & Comm. | As required |
|  | Validate Effectiveness | Confirm actions resolved issues | Field Compliance Manager / MEL Coordinator | Quarterly |

Learning and Adaptation Cadence

| Activity | Frequency | Focus |
| --- | --- | --- |
| After-Action Reviews | After key activities | What worked, what didn’t, why |
| Hub Learning Sessions | Quarterly | Operational improvements |
| State/Zonal Learning Reviews | Bi-annual | Patterns, risks, and adaptations |
| National Learning Review | Annual | Strategic learning and pivots |
| External Evaluations | As required | Independent learning and validation |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Learning not acted upon | Insights documented but ignored | Mandatory action plans with ownership |
| Repeated mistakes | Same issues recur across cycles | Root cause analysis and tracking |
| Retrospective Bias | Only looking at past data rather than proactive trends. | Use Real-time dashboards to identify issues instantly rather than waiting for annual reports |
| Resistance to change | Staff or partners adhering to old, inefficient processes or adapt practices | Leadership sponsorship and communication. Clearly communicate the purpose of initiatives and provide stepwise digital literacy and leadership training. |
| Weak accountability | Corrective actions not implemented | Escalation and performance linkage |
| Poor documentation | Lessons lost or fragmented | Standard learning and action templates |
| Data Falsification | Hubs hiding failures to avoid corrective action. | Independent verification. Use automated equipment logs (GPS) and token-driven verification to ensure an unalterable audit trail. |
| Metric Fatigue | Teams becoming overwhelmed by too many corrective requirements. | Narrow the focus to no more than two crucial goals at a time. |

Policy Guidelines

- It is mandatory to document lessons and corrective actions.

- There must be clear ownership and timelines for corrective actions.

- There must be an independent validation of corrective actions to ensure they are required and appropriate.

- Updated SOPs shall override previous versions.

- All updated SOPs and plans must have adequate version control and communication.

- The National Coordinator shall perform oversight of unresolved issues via the support of the Field Compliance and Internal Auditor.

- Learning from lessons is mandatory, not optional, at all levels.

- Adaptations shall be evidence-based and approved.

- Persistent non-resolve action shall trigger the appropriate escalation.

- 100% of strategic decisions must be informed by M&E data by 2026 to ensure transparency and accountability.

- Standard Operating Procedures must be reviewed at least annually and updated based on lessons learned and stakeholder feedback.

- WIMA shall conduct strategy revision sessions if there is a change in leadership direction or evolving business environments.

- Findings from Social Return on Investment (SROI) and gender-sensitive metrics must be used to refine any current roadmap where applicable.

- State and Zonal Coordinators are empowered to execute 100% of operational decisions at the local level using validated field data.

- Feedback involving sensitive issues like SEAH or whistleblower reports must be handled with total confidentiality during the learning process.

SAFE PARTICIPATION & SAFEGUARDING

Overview of Process

The “Safe Participation & Safeguarding” process establishes how WIMA ensures that all members, beneficiaries, staff, partners and community participants; particularly women, youth and vulnerable groups; can engage in WIMA activities safely, with dignity and without fear of harm, exploitation, harassment, or abuse. As a women-led association, WIMA enforces a zero-tolerance policy toward Sexual Abuse, Exploitation, and Harassment (SEAH) and bullying. This process ensures a prompt, fair, and sensitive response to incidents while maintaining 100% confidentiality to protect survivors.

Scope

This process applies to all WIMA staff, elected officers, consultants, volunteers, State Coordinators, MSPs, Community and Sub-Community Leads, 	Members, trainees, beneficiaries, participants, partners, vendors and service providers engaged by WIMA.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - WIMA Safeguarding Policy and Code of Conduct - Participant registers and engagement records - Training attendance and induction records - Complaints and grievance submissions - Survivor statements & evidence - Field supervision and audit findings - WIMA Code of Conduct and SEAH Policy - Child protection & behavioural policies - Background check/vetting records | - Safe participation environments and practices - Safeguarding induction and training records - Documented safeguarding reports and actions - Corrective and disciplinary actions where required - Periodic safeguarding compliance reports - Incident investigation reports - Support referral documentation |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Engagement of new staff, partners, MSPs, or volunteers - Commencement of trainings, hub operations, or field activities - Receipt of a safeguarding complaint or allegation - Identification of safeguarding risks in new hubs, during operations or audits - Detection of workplace bullying or discrimination | - Board of Trustees/ President: Oversight of safeguarding governance and compliance - National Coordinator: Integration of safeguarding into operations. Enforcement of safeguarding standards and zero tolerance - Safeguarding Focal Person: Safeguarding coordination, case management, reporting - Zonal / State Coordinators: Local safeguarding oversight and escalation - CL / Sub-CL / MSP: Ensuring safe environments at hub level - MEL Coordinator / Field Compliance: Monitoring safeguarding indicators and audits - All Staff & Partners: Adherence to safeguarding rules and reporting concerns |
| Tools Required | Key Performance Indicators (KPIs) |
| - Anonymous Hotline - Confidential Reporting Email - ERP Incident & Security Module - Vetting & Screening Checklists | - Zero unaddressed safeguarding (SEAH) cases. - % of staff/partners trained on SEAH (Target: 100%). - Time to provide survivor support (Target: Immediate). - % Hubs with displayed Code of Conduct (Target: 100%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Risk Identification | Identify safeguarding risks in activities | Safeguarding Focal Person / Coordinators | Ongoing |
|  | Prevention Measures | Enforce codes of conduct and safety rules Key Control: Mandatory vetting and background checks for all staff and partners. | All Managers | Ongoing |
|  | Induction & Training | Conduct safeguarding orientation Key Control: Conduct regular training on identifying and reporting SEAH and child abuse. | Safeguarding Focal Person | Onboarding |
|  | Detection & Reporting | Identify and report case Key Control: Any employee or stakeholder aware of a concern must report it immediately via the hotline, email, or to a focal person. Confidentiality is strictly maintained. | All Staff / Members | Immediate |
|  | Immediate Response | Receive complaints via approved channels. Prioritise the safety and well-being of the survivor. Do not confront the accused directly to avoid escalation or tampering with evidence. | Safeguarding Focal Person | Within 2 Hours |
|  | Logging and Assessment | Record the report in the ERP Incident Module with specific details of the event. A preliminary review determines credibility and immediate protective steps. Key control: All cases must be logged. | Safeguarding Focal Person | Less than 24 Hours |
|  | Protective Measures | Take protective measure If necessary, place the accused on administrative leave to ensure the safety of the survivor and the integrity of the investigation | Safeguarding Committee | Immediate |
|  | Survivor Support | Provide survivor support and referrals Key Control: Provide or refer survivors to essential medical, psychological, and legal assistance services. | Safeguarding Focal Person | Within 24 Hours |
|  | Investigation | Conduct prompt and sensitive interviews with all involved parties. Document all evidence in a secure, non-judgmental manner. Key Control: Investigation must be conducted confidentially | Safeguarding Committee | 5 Days |
|  | Resolution & Action | If allegations are substantiated, apply strict disciplinary actions, including termination of employment or partnership and potential legal proceedings. | National Coordinator | 7 Days |
|  | Closure & Learning | Close case and capture lessons. Incorporate feedback from past cases into annual policy and SOP updates to improve future prevention and response. | Safeguarding Focal Person / MEL Coordinator | As required/ Annual |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Under-reporting | Fear of retaliation or stigma | Anonymous reporting and protection policy |
| Retaliation | Harm to complainants or witnesses. Whistleblowers or survivors fearing discrimination for reporting high-ranking officials. | Zero tolerance and disciplinary action. Strict enforcement of the Whistleblower Policy and anonymous reporting channels; WIMA guarantees protection against retaliation. |
| Inadequate Vetting | Hiring individuals with a history of abuse who then work with women or children. | Mandatory screening and vetting of all employees, volunteers, and partners for past SEAH violations before engagement. |
| Poor case handling | Breach of confidentiality or delays | Trained focal persons and timelines |
| Cultural resistance | Norms that discourage reporting. Communities or leaders dismissing harassment as "local custom". | Continuous sensitization and leadership tone. Engage the He4She Club and traditional rulers to legitimise women’s rights and formalise local backing for safeguarding policies. |
| Partner non-compliance | Vendors or MSPs violate standards | Contractual safeguarding clauses |
| Confidentiality Breaches | Sensitive details leaking, leading to survivor re-traumatisation or stigma. | Information shared strictly on a need-to-know basis with encrypted storage of all case records. |

Policy Guidelines

- This safeguarding obligations of WIMA apply to everyone, without exception

- All employees have a formal obligation to report suspected misconduct; turning a blind eye shall result in disciplinary action.

- There shall be zero tolerance for abuse, exploitation and harassment.

- WIMA’s safeguarding process shall be survivor-centred and confidential handling of cases.

- All survivor and whistleblowers shall be protected from retaliation.

- Inclusion, equity, and respect for dignity

- There shall be appropriate accountability at all levels

- WIMA shall have a dedicated safeguarding email or hotline. There shall be anonymous reporting mechanisms where possible.

- All allegations must be reported and assessed.

- All reporting to Safeguarding Focal Person must be confidential and treated as such.

- All severe cases must be escalated to executive leadership. Child safeguarding violations require immediate escalation.

- There must be a mandatory safeguarding induction for all personnel and partners.

- All staff and partners must sign the WIMA Code of Conduct which shall include the appropriate safeguarding clauses.

- There must be a separation of roles between reporting, investigation and decision-making

- A secure storage of safeguarding records must be provided with adequate encryption and control access.

- Safeguarding breaches shall attract disciplinary and legal action as applicable.

- WIMA shall not tolerate bribery, corruption, bullying, or any form of sexual abuse and exploitation.

- The welfare of the child is the primary consideration in all activities involving persons under 18.

- Staff, partners and volunteers must maintain clear professional boundaries at all times when interacting with beneficiaries.

- Parental or guardian consent must be obtained before engaging in any activities specifically involving children.

- Every report must be treated with the highest level of confidentiality to protect the rights of all parties.

EQUAL ACCESS TO MECHANISATION SERVICES

Overview of Process

The “Equal Access to Mechanisation Services” process defines how WIMA ensures fair, transparent, and inclusive access to mechanisation services for women farmers, youth, smallholders, and other underserved groups, while balancing commercial sustainability and operational efficiency.  This process operationalises the Gender Equity, Disability and Social Inclusion (GEDSI) strategy by removing structural barriers such as lack of collateral, male-dominated supply chains, and cultural restrictions.

Scope

This process applies to all WIMA mechanisation hubs and service points, Hub Managers (CLs and Sub-CLs), MSPs, farmers, cooperatives, agribusiness clients, digital booking, scheduling and service delivery processes.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Approved service/member eligibility and prioritization criteria - Booking requests and service registers - Equipment availability schedules - Pricing and subsidy guidelines - Community-level beneficiary data | - Service Allocation Logs - Disaggregated service delivery records - Priority-group service utilization reports - Resolved access complaints - Evidence of inclusive service delivery - Hub Impact Metric Summaries |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Service booking requests - Seasonal service demand peaks - Introduction of new hubs or equipment - Complaints or disputes relating to access | - Board / President: Oversight of equity and inclusion objectives - National Coordinator: Policy enforcement and escalation - Zonal / State Coordinators: Oversight of hub-level access practices - MSP: Adherence to approved schedules - Community & Sub-Community Leads: Fair scheduling and service delivery. Demand aggregation and beneficiary validation - MEL Coordinator / Field Compliance Manager: Monitoring access indicators and audits |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA App & Booking Module - Vulnerability-Adjusted Finance Model - He4She Consultative Panels - Mobile Crèche Facilities | - % Smallholder members accessing services (Target: High). - % Participation of marginalised groups (Target: ≥25%). - % Members reporting better land/finance access (Target: ≥40%). - Average cost reduction per farmer (Target: ≥20%). |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Member Enrolment & Profiling | Enrolment of members. Validate beneficiary eligibility and priority status Key Control: Register farmers via the WIMA App, capturing gender, age, disability status, and farm size to enable targeted support. | CL / Sub-CL | Continuous |
|  | Engagement and Advocacy | Carry out engagement to remove service uptake barriers Conduct focus groups to identify local barriers to mechanisation, such as cultural norms or lack of credit. Enlighten them on pooled service models and cost-sharing schemes to reduce the individual burden for women-headed households Engage traditional rulers and husbands via the He4She Club to legitimise women operators and reduce local resistance. | GESI Lead / State Coordinator / CL | Pre-Season/ Quarterly for H4She |
|  | Scheduling | Allocate services based on priority and capacity. Key Control: This is done via the booking platform. It is automated and based on payment. | CL / Sub-CL/ MSP/ ERP (automated) | Daily/ Weekly |
|  | Notification | Communicate service schedules and pricing Key Control: This is done via the booking platform. It is automated and based on payment. | CL / Sub-CL/ MSP/ ERP (automated) | Before service |
|  | Service Delivery | Deliver mechanisation services as scheduled | MSP | As scheduled |
|  | Supportive Infrastructure | Deploy mobile crèches during service delivery to facilitate full participation. | MSP | Service/ Engagement Day |
|  | Confirmation | Provide service completion confirmation | Member / Farmer | Same day |
|  | Complaint Handling | Address access-related complaints | State Coordinator / Safeguarding | As required |
|  | Impact Tracking | Monitor GEDSI compliance by reporting the quantity of food produced and household income uplift for marginalised members and other applicable indicators. | MEL Coordinator | Quarterly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Elite capture | Powerful farmers crowd out priority groups for hub machine hours | Enforced priority criteria and oversight. Enforce mandatory smallholder prioritisation and transparent digital booking via the ERP. |
| Discriminatory practices | Bias in service allocation | Transparent rules and audits |
| Cultural Pushback | Resistance to women operating heavy machinery in traditional zones. | Formalise pledges from traditional rulers (Emirs) and engage the He4She Club as "champions" for women’s leadership. |
| Revenue pressure | Prioritization affects profitability | Cross-subsidy and seasonal balancing |
| Financial Exclusion | Women failing to access services due to a lack of collateral. | Use vulnerability-adjusted financing and lease-to-own models through women-focused agro-leasing cooperatives. |
| Service disputes | Disagreement over access or scheduling | Clear communication and grievance mechanisms |
| Data gaps | Poor records of beneficiary access | Mandatory digital registers and validation |
| Physical Safety Risks | Women or children facing harm during programme activities. | Strict adherence to the SEAH and Child Protection Policies; appoint trained Safeguarding Focal Persons at every hub. |

Policy Guidelines

- WIMA shall deploy a digital booking and scheduling system accessible to all partners and members.

- There must be transparency in booking, pricing and scheduling of all services. Therefore, all bookings for services must be done via the ERP/booking platform.

- Where possible, priority access will be provided for defined target groups i.e., women, youth, persons with disabilities, etc

- Accountability and traceability shall be entrenched in all hub activities.

- WIMA shall balance between inclusion and sustainability.

- Membership enrolment shall follow the approved eligibility and prioritization criteria.

- It is mandatory for members and MSP to confirm service delivery.

- The MEL Coordinator shall provide disaggregated reporting by gender and group.

- Independent compliance and field audits shall be conducted to ensure equal access to WIMA services.

- All access-related complaints must be documented and resolved.

- Equity indicators shall be tracked and reported periodically.

- All hubs must maintain a participation rate of at least 80% female and 20% youth-led members.

- WIMA shall provide specific accessibility measures, including subsidies (if any) for women with disabilities were possible.

- Hubs must ensure safe spaces and maintain a zero-tolerance policy for harassment, exploitation, or discrimination.

- Service pricing and subsidies (if any) must be communicated clearly via the WIMA App to prevent improper influence or bribery.

- All outreach, engagement and training materials must be available in local languages to ensure accessibility for rural communities.

- Parental consent is mandatory for activities involving persons under 18, and childcare facilities must be provided for mothers during training.

GENDER-BASED RISK IDENTIFICATION & RESPONSE

Overview of Process

The “Gender-Based Risk Identification & Response” process defines how WIMA systematically identifies, assesses, mitigates, and responds to gender-specific risks that may arise from participation in mechanisation services, training, finance, and field operations. The process ensures that WIMA’s interventions do not expose women and girls to harm, backlash, exclusion, or increased vulnerability, and that risks are proactively managed across all levels.

Scope

This process applies to all WIMA programmes, hubs, mechanisation services, trainings, demonstrations, field operations, community engagement, financing, service delivery models, staff, partners, MSPs, members and beneficiaries.

| Inputs | Key Reports/Outputs |
| --- | --- |
| - Gender and social inclusion analysis - Community profiles and stakeholder mapping - Safeguarding and grievance reports - Field supervision and compliance findings - Feedback from women members and beneficiaries - WIMA SEAH & Behavioural Policies - He4She Community Pledges - Survivor Statements & Evidence | - Gender risk registers and mitigation plans/Monthly gender risk assessment - Documented responses to gender-related incidents - Adapted operational approaches to reduce risk - Gender risk monitoring indicators - Learning briefs on gender risk management - Incident investigation reports - Safeguarding compliance scorecards - Support referral documentation |
| Process Trigger | Process Owner(s) and Responsibilities |
| - Design or rollout of new services, hubs, or pilots - Community entry and sensitization activities - Reports of incidents, complaints, suspected SEAH or discrimination - Changes in context, seasonality, or operating environment - Entry into a new "red-zone" or volatile community - Discovery of cultural or advocacy pushback | - Board of Trustees/President: Oversight of gender risk governance. Approval of high-risk responses and adaptations - Gender & Safeguarding Focal Person: Gender risk assessment and response coordination - National Coordinator: Integration into operations and escalation - Zonal / State Coordinators: Local risk identification and response - Community Leads (CLs): Early warning and community feedback - CL / Sub-CL / MSP: Day-to-day risk monitoring and reporting - MEL Coordinator/ Field Compliance: Monitoring indicators and assurance |
| Tools Required | Key Performance Indicators (KPIs) |
| - WIMA ERP (Incident & Security Module) - Anonymous Hotline - Vulnerability Scoring Data - He4She Consultative Panels | - Zero unaddressed safeguarding (SEAH) cases. - % Members reporting safe service access. - % Staff/Partners trained on GESI. - Time to provide survivor support (Target: Immediate) |

Business Process Flow Diagram

Business Process Flow Description

| No. | Activity | Task/Description | Responsibility | Timeline/ Duration |
| --- | --- | --- | --- | --- |
|  | Proactive Risk Mapping | Conduct a gender analysis as part of all pre-entry assessments to identify local barriers like gender-biased land laws. | GESI Lead / CL | Pre-Season |
|  | Advocacy Neutralisation | Engage traditional rulers and husbands via the He4She Club to legitimise women operators and reduce local resistance. | State Coordinator | Ongoing |
|  | Safe Space Setup | Setup appropriately Key Control: Hubs must display the WIMA Code of Conduct and safeguarding mechanisms to maintain "Operational" status. | CL | Immediate |
|  | Risk Identification | Identify potential gender-based risks | CL | Ongoing |
|  | Risk Assessment | Assess severity, likelihood, and impact | Gender / MEL | As needed |
|  | Mitigation Planning | Develop risk mitigation measures | State / National Coordinator | Before rollout |
|  | Prevention Actions | Implement sensitization and safeguards | CL / Sub-CL / MSPs | Ongoing |
|  | Monitoring | Track risks and effectiveness of measures | MEL Coordinator / Field Compliance | Monthly |
|  | Incident Reporting | Report gender-related incidents Key Control: Any employee aware of a concern must report it immediately via the anonymous hotline or ERP | All staff/ members | Immediate |
|  | Response & Support | Provide survivor-centred response Prioritise survivor safety. Update equipment status to "Grounded" in the ERP if the incident occurred during service delivery. | Safeguarding / Gender Focal Person | < 2 Hours |
|  | Escalation | Escalate high-risk cases Key Control: Any SEAH or security threat is instantly escalated to the President for prompt vendor or legal intervention. | National Coordinator / President | Immediate |
|  | Formal Investigation | Conduct prompt, sensitive and confidential interviews. | Safeguarding or Ethics Committee | 5 Days |
|  | Resolution & Action | Apply strict disciplinary measures for substantiated claims, including contract termination or legal proceedings. | President/ Board of Trustees | 7 Days |
|  | Adaptation | Adjust operations based on learning. Incorporate findings into annual SOP reviews and State Improvement Plans to prevent reoccurrence. | National Coordinator/ KM & Comms | As required/ Quarterly |

Risks and Mitigations

| Risk | Description | Mitigation |
| --- | --- | --- |
| Community backlash | Resistance to women’s participation | Community sensitization and male engagement |
| Increased safety risks | Travel or field exposure | Scheduling, buddy systems, safe locations |
| Cultural "Side-Lining" | Local leaders dismissing harassment as a cultural norm. | Secure formal pledges from traditional rulers (e.g., Emirs) to formalise backing for WIMA’s safety standards. |
| Confidentiality Breaches | Sensitive details leaking, leading to survivor re-traumatisation. | Strictly limit information access on a need-to-know basis using encrypted ERP user rights. |
| Financial control risks | Women lose control of benefits | Direct payment mechanisms and awareness |
| Under-reporting | Fear or stigma prevents reporting | Confidential channels and trusted focal persons |
| Program withdrawal | Women drop out due to pressure | Flexible participation and follow-up support |
| Fear of Retaliation | Survivors or staff failing to report misconduct by influential figures. | Enforce the Whistleblower Policy with anonymous channels and private rewards for confirmed declarations. |
| Physical Vulnerability in Red-Zones | Field staff facing threats while investigating incidents. | Abide by the Emergency Community Response & Safeguarding Guide; never endanger lives for data. |

Policy Guidelines

- Gender risk management is mandatory for all activities.

- WIMA shall abide by confidential reporting and case management practices.

- WIMA shall conduct regular gender risk reviews.

- No activity shall proceed where risks are unmanaged.

- Survivor safety and consent shall be considered paramount.

- All high-risk cases must have appropriate executive oversight.

- Gender risk data shall inform all planning and adaptation.

- WIMA prohibits all forms of corruption, bullying, and sexual abuse; violations shall result in instant dismissal.

- Hub leadership must maintain a quota for women to ensure inclusive governance and safe reporting lines.

- The survivor’s safety and medical/legal needs shall and must be the primary consideration in every response.

- All personal data regarding incidents must be processed lawfully and securely under the Nigeria Data Protection Regulation.

- Every employee, partner and stakeholder are obligated to report suspected misconduct; turning a blind eye is a disciplinary/sanctionable offence.

- Community entry shall not be complete without harmonising the He4She Charter with local traditional nuances.